DELHI DEVELOPMENT AUTHORITY

NORTHERN DIVISION NO. 5

List of Activities

1.	Details of Pending Final Bills and Non-refund of Security Deposits.

Details of Pending Final Bills for the Month Ending July, 2007

| Sl. No. | Name of work | Agency | Agreement No. | Stipulated date of Start/ Completion | Actual date of Completion | Date of Payment of Final Bill | Reasons for delay in payment of Final Bill |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | D/o land for CHBS, Pitampura, (Saraswati Vihar). SH: C/o Sumpwell at Kanjhawala Road near Avantika. | M/s. S.N. Nandi & Co. | 29/EE/ND-5/DDA/92-93 | 06.09.92/ 5.12.92 | 25.12.94 | 30.09.07 | Under Process |
| 2. | D/o Community Centre along Road No.44, Pitampura. SH: C/o Kiosk including internal development. | M/s. Sushil Kumar & co. | 12/EE/ND-5/ DDA/ 2002-03 | 30.06.02/ 29.03.03 | 20.10.03 | 25.09.07 | Under Process |
| 3. | D/o Community Centre along Road No.44, Pitampura SH: C/o Pavement in Upper Ground level. | M/s. En Vee Kay Constn. Co. | 5/EE/ND-5/ DDA/2003-04 | 15.06.03 14.09.03 | 08.12.03 | 30.09.07 | Under Process |
| 4. | C/o 216 SFS DU’s Cat-III (M.S.) at Pitampura. SH: Providing Bored cast in Situ RCC Piles, Pile Caps, and Grade beams with RMC of M-25. | M/s. Cengrs Geotechnica Pvt. Ltd. | 10/EE/ND-5 / DDA/2003-04 | 23.06.03/ 22.12.03 | 20.06.05 | 15.09.07 | Under Process |

2.	Present Status of works

List of works costing more than Rs.2.00 lacs for the quarter ending September, 2007

| S.No. | Name of work | Agency | Estt.Cost/ Tendered Amt. (in lacs) | Stipulated date of start / Completion | Physical Progress | Actual Date of Completion | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | M/o Completed scheme of North Zone. SH: C/o Sump Well of 1.00 lac litre (Approx). Capacity of RCC box drain of 656 MIG houses at Jahangirpuri. | M/s. K.P. Rana | 10.94/ 15.90 | 03.06.06/ 02.09.06 | 97% | - | Work in progress |
| 2. | N/W- C/o 216 MIG DU’s (MS) at Pitampura (Near T.V. Tower. (i) SH: C/o 72 MIG DU’s (M/S) superstructure including sanitary installation, water supply Sewerage, Drainage, Roads and Paths and Int. Electrification all complete. | M/s. Ved Prakash Mithal and Sons. | 557.52/ 713.73 | 25.10.06/ 24.10.08 | 41% | -- | Work in progress |
| 3. | N/W –do- C/o 144 MIG DU’s (MS) Superstructure including sanitary installation, W/S and Int. Electrification all complete Group-II & III. | M/s. Winner Constn. (P) Ltd. | 1040.30/ 1389.15 | 14.12.06/ 13.12.08 | 35.25% | -- | Work in progress |
| 4. | N/W –do- M/o Sports Complex at Pitampura. (i) SH: Relaying of Wooden flooring in Squash Court. | M/s. Khalsa Gymnastic Works. | 6.13/ 4.61 | 05.12.06/ 04.03.07 | 80% | -- | Work in progress. |
| 5. | N/W –do- SH: Providing house keeping arrangement and house keeping material at Sports Complex. | M/s. Veenus Associates | 4.63/ 2.95 | 08.02.07/ 07.02.08 | 65% | -- | Work in progress. |
| 6. | N/W –do- C/o Cricket Pavillion at R.S.K.P. Pitampura, Near TV Tower. | M/s. K.P. Rana | 45.47/ 58.09 | 10.07.07/ 09.11.07 | -- | -- | Work yet to be started. |
| 7. | N/W M/O completed scheme under Nazul A/C II (North Zone) SH- Filling of earth in low lying area at Rajdhani Enclave and Lok Vihar park at PitamPura | M/S Jai Hanuman Cons. Co. | Rs. 5,51,429/- Rs. 3,52,296/- | 17.7.07 38.8.07 | 70% |  |  |
| 8. | N/W D/O 16.92 Hact of Land a North of Model town. SH- Raising of 12M. R/W along plot no 41,42,43 o 52 and approach o Buddha society temple | Sh. Jagdish Pd. Sharma | Rs. 3,45,179/- Rs. 5,96,696/- | 18.8.07 28.8.07 | 15% |  |  |

3.	Projects held up due to Court Case	:	LSC Harsh Vihar, Pitampura

……….. Respective Court with Case No.	:	Pertain to LM/DDA.

………  Date of Next Hearing	:	Pertain to LM/DDA.

4.	Rain Water harvesting :

……….. Already provided	:	Nil

……….. Proposed	:	Nil

5.	Water Bodies:

……… identified, status and under 	:	Nil

Encroachment

6.	Details of Deposit Works:

(a)	In hand (b) Under approval

Status	:	N/A

7.	Details of deviation in works:

Details of deviations in works for the quarter ending September, 2007

| S.No. | Name of work | Name of Agency | Amount (in lacs) | Deviation |
| --- | --- | --- | --- | --- |
| ----------------- Nil ----------------- |  |  |  |  |

8	Restricted Call of Tenders.

Details of Restricted Call of Tenders for the quarter ending September, 2007

| S.No. | Name of work | Name of Agency | Amount (in lacs) |
| --- | --- | --- | --- |
| ----------------- Nil ----------------- |  |  |  |

9.	Rescinded Works:

Details of Rescinded Works – Status as on September, .2007

| Sl. No. | Name of work | Agency | Agmt. No. | Stipulated Date of Start/ Completion | Provisional extension granted upto | Date of rescission of work | Date of Award of Balance work | Remarks. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |
|  | ------------------------ Nil ------------------ |  |  |  |  |  |  |  |

10.	Arbitration & Related Court Cases

(a)	Pending Arbitration Case as on September, 2007

| Sl. No. | Name of work/Agreement No./ Agency | Arbitrator | Present Position | Next date of Hearing | Remarks |
| --- | --- | --- | --- | --- | --- |
| 1 | C/o 208 SFS Cat-II and III Houses at Shalimar Bagh, Pkt-’W” Blk-”B” including water supply sanitary installation and internal development. Agmt. No. 15/DD-I/DDA/83-84 Agency: M/s. Jeet Singh Jai Mal Singh. | Sh. S.S. Jain | All the files received from WD Dandgey alongwith relevant papers regardeing proceedings of GR Hingorani has been sent to Sh. N.K. Sharma, Arbitrator through EO-1 to EM for entering Arbitration on 28.07.03 | Still awaited. |  |
| 2. | C/o 512 EWS Houses at Sector-17, Block-”A” Pkt-B, Rohini. Agmt. No. 6/DD-I/DDA/85-86 Agency: M/s. A.S. Sachdeva & Sons. | Sh. R.C. Chopra | Case is in progress P/L Sh. D.S. Mahendra | 27.09.2007 at 4:30 PM |  |
| 3. | Dev. Of land for Zone H-4-H-5 (Pt.) Pitampura. SH: Sewerage (Peripheral) Phase-I, Central Portion. Agmt. No. 9/EE/DD-VI/81-82 8/EE/HD-XXV/87-88 Agency: M/s. J.K. Gandhi | Sh. K.S. Chauhan | Case in Progress P/L Sh. Ashutosh Sharma. | 04.10.2007 at 03:00 pm |  |
| 4. | Construction of 480 SFS houses at Shalimar Bagh Block-B, Pkt-W. SH: C/o 176 SFS Cat-II & III Houses at Shalimar Bagh. Agmt.No.70/EE/HD-13/DDA/82-83 Agency: M/s. Globe Constn. Co. | Ms. Kanwal Inder | Case in Progress P/L Ms. Geeta Malhotra | yet to be decided |  |
| 5. | Dev. Of Distt. Centre Pitampura opp. Wazirpur DTC Depott. SH: C/o Road (1st Ph. Treatment). Agreement No. 40/EE/ND-5/DDA/88-89 Agency: Sh. Suraj Verma (Prop. Sh. Ajay Verma) | Sh. Pramod Kumar | -- | Still awaited. |  |
| 6. | C/o 144, MIG Houses in Pkt’J’ Wazirpur including internal development. Agmt.No. 1/DD-I/DDA/82-83 127/EE/ND-5/DDA/98-99 M/s. A.R. Khanna & Co. | Sh. V.D. Tiwari Retd. (CE) | Case in progress Sh. Bhupesh Kumar Panel Lawyer. | 10.10.2007 at 3:00 PM |  |
| 7. | C/o 512 EWS Houses in Pkt-6, Block-A, Sector-17, Rohini. Agmt. No.7/EE/DD-I/DDA/85-86 M/s. A.S. Sachdeva. | Sh. M.L. Tiku | Case in progress Sh. D.S. Mahendru Panel Lawyer. | 25.10.2007 At 4:00 PM |  |

10. 	(b)	Court Case.

Details of Court Cases pending at the end of September, 2007 – Service Matters.

| Sl. No. | File No. | Name of Employee | Name of Court/Suit No. | Name of Panel Lawyer | Nature of Case | Present Position | Next date of Hearing. | Remarks. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | F.21 (214)/97/ HC/ Legal | Smt. Brahm Wati Vs. DDA | High Court 4421/97 WR-4825/04 & court case CAS (C) 4262-2004 Smt. Barahmwati Vs/ DDA in the High Court date of Hearing was 2.11.2004 and Hon’ble Court has passed the order vide No. CAS (C) 426/04 dt. 2.11.2004 and the copy of the same has been sent to Legal Deptt. DDA as stated by Panel Lawyer. | Present Rajeev Bansal | Adminis-trative | Write appeal under letters Patent Act. Against the Judgment/ order dt. 26.4.2004 passed by Ld. Single Judge of Hon’ble Court Dismissing Writ Petition (Civil) 4825/2004 | -- | -- |

10.	(c)	Court Case

DETAILS OF COURT CASE PENDING AT THE END OF September 2007 (Works)

| S.No. | Case Title/Party Name | File No. | Suit No. / Name of Court. | Name of the Division | Name of P/L | Date of Entrustment of P/L | Last date of Hearing. | Next date of hearing | Status of the case. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Dev. Of land CGHS Pitampura (Saraswati Vihar). SH: C/o Foot path from Chander Lok Culvert to Road No. 41. M/s. Aar Bee Constn. Co. (Prop. Sh. Rakesh Kumar) | F.11(4)/TC/ 03/Legal | CS/353/ 2004 / Tis Hazari | ND-5 | Sh. P.K. Aggarwal | 11.05.2005 | 20.09.07 | 15.10.07 | Recovery suit by contractor. |
| 2. | Death of six year old child in the low lying area in Sainik Vihar. Sh. Suraj Verma | F. 9 (56)/ TC/ Legal | CS-299/ 2004 / Tis Hazari | ND-5 | Sh. Neeraj Aggarwal | 04.05.07 | 07.09.07 | 29.09.07 | Suit for Damage compen-sation. |
| 3. | C/o CSC at Pushpanjali Enclave, Block-B, Pitampura. M/s. S. Lall & Co. | F.11 (3)/ 98/TC / Legal | CS-71/ 2006 / Tis Hazari | ND-5 | Sh. R.M. Totia | 06.09.06 | 24.09.07 | 30.10.07 | Recovery suit |
| 4. | Acq. & Dev. Of land for PVC collection sorting yard light industries and Ware Houses at Tikri Kalan (Near Rohtak Road). SH: C/o RCC Storm water drain outfall drain (Box type) in Zone-E M/s. Happy Himalaya Constn. Co. | F.2 (150)/EE/ND-5/DDA/2001-01/837/TC / Legal | 103/2003 / Tis Hazari | ND-5 | Ms Renu Gupta | 19.01.04 | 05.09.07 | 19.11.07 | Recovery suit |
| 5. | Dev. Of land for Mangolpuri Indl. Area Ph.I, Storm Water Drain and Culverts. M/s. Manohar Lal Sethi | F.21 (264) 06/HC/Legal | Execution No. 172/06/ High Court | ND-5 | Sh. Bhupesh Narula | 9.11.06 | 27.08.07 | 27.08.07 | Execution for payment of diff. of decretal amount of award dat. 8.1.06 |
| 6. | D/o land for Mangolpuri Indl. Area Ph.I SH: C/o S.W. Drains and Culverts. Sh. Manohar Lal Sethi | F.21 (305) /06/ HC/ Legal F.2 (249) EE/ND-5/ DDA/ 2006 | CM-7700 & 7701/06 / FAO (05) / 356/ 06 / High Court | ND-5 | Sh. Bhupesh Narula | 28.12.06 | 16.09.07 | 15.01.08 |  |
| 7 | C/o 480 SFS Houses at Shalimar Bagh, Block-B, Pkt-W SH: C/o 208 SFS Houses. M/s. Sanyukat Nirmata | Case Club | 02/2005/ High Court | ND-5 | Sh. Bhupesh Narula | 9.11.06 | 31.07.07 | 14.12.07 | For filing of arb. Award |
| 8 | M/s. Sanyukat Nirmata |  | Execution No. 66/2006 / High Court | ND-5 | Sh. Bhupesh Narula | 11.12.06 |  |  | Execution for filling of Arb. Award. |
| 9 | M/s. Sanyukat Nirmata |  | OMP-371/2007 / High Court | ND-5 | Sh. Bhupesh Narula |  |  |  |  |
| 10. | Dev. Of land H4-H5 (Pt.) Pitampura. SH: S.W. Drain Pkt-III, Outfall. M/s. Hans Raj Constn. Co. | F.21 (180)/97/ HC/Legal | FAO (05) / 100/07 | ND-5 | Sh. D.S., Mahendroo | 15.06.07 | 20.08.07 | 15.01.08 | Petition filed by the agency before Double Bench High Court against the judgment of Single Judge vide which award published was setaside. |

11.	Details of Q.C. Lab Tests, Procedures	:	N/A

12.	Fire Fighting Equipments 	:	Office of the ND-5 / DDA

(installed with locations)

13.	List of Soil Testing Laboratories	:	N/A

14.	List of Approved Structural Consultants	:	N/A

15.	Technical Circulars	:	N/A

16.	Q.C. Circulars	:	N/A

17.	List of Contractors A,B,C,D, Categories	:	N/A

18.	RIS/EIS/EOT Cases and Completion Certificate

Details of EIS pending as on September, 2007

| S.No. | Name of work | Name of Agency | Amount (in lacs) |
| --- | --- | --- | --- |
| 1 | M/o Completed Scheme of NZ SH: C/o Sumpwell and R.C.C Bore drain MIG Houses at Jahangirpuri. | M/S K.P. Rana | Rs. 1,46,472.00 |

Details of RIS for the Quarter Ending September, 2007

| S.No. | Name of work | Name of Agency | Amount (in lacs) |
| --- | --- | --- | --- |
|  | -----------------------------------NIL ---------------------- |  |  |

Details of EOT for the Quarter Ending September, 2007

| S.No. | Name of work | Name of Agency | Amount (in lacs) |
| --- | --- | --- | --- |
|  | --------------------------NIL------------------------------ |  |  |

19.	List of approved rates of SE (P)	:	N/A

20.	Areas where services are handed over to	:

MCD, DJB and Deficiency Charges.

Monthly Progress report as on September, 2007

| S.No. | Name of Areas/Colony. | Handed over the services |  |  |  | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | MCD | Deficiency charges | DJB | Deficiency charges |  |
| 1. | Mangolpuri Industrial Area Phase-1. | -- | -- | Water Supply | Nil |  |
| 2. | C/o 80 SFS Houses Cat-II & IIIrd at Pkt L(D), Pitampura. | (i) Open Surface drain | Nil | (i) Water Supply | Nil |  |
|  |  | (ii) Road and Path | Nil | (ii) Sewerage | Nil |  |
| 3. | Peripheral Services in Sector-17, Rohini | - Road (iI) S.W. Drain | Rs. 535139.00 Rs. 778876.00 | -- -- |  |  |
| 4. | L.Sc. at Raj Sabha (CHBS) Society at Pitampura | (i) Road (ii) S.W. Drain | Deficiency estimate under Scrutiny | (i) Water Supply (ii) Sewerage | Deficiency estimate under scrutiny |  |
| 5. | LSC at Pkt C(D) Pitampura | -- | -- | Sewerage | Awaited from 7.12.02 |  |
| 6. | LSC at Pkt C(U), Pitampura | -- | -- | Sewerage | Awaited from 15.01.04 |  |

21.	List of vacant Flats/Shops / Kiosks / Commercial / Residential Plots on the date of completion / Development Ending as on July, 2007

21.	(a)	Detail of Houses as on July 2007

| Sl. No. | Name of Scheme | Year of Comp. | Divn. | Houses Constructed |  |  |  |  | Total Allotted |  |  |  |  | Total Vacant |  |  |  |  | Specified number of Vacant Houses |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | SFS | MIG | LIG | Janta | Total | SFS | MIG | LIG | Janta | Total | SFS | MIG | LIG | Janta | Total |  |
| 1 | C/o 336/224 MIG at Jahangirpuri | 1992 | ND-5 |  | 224 |  |  |  |  | 150 |  |  |  |  | 74 |  |  | 74 | 82, 84, 85, 87, 94, 101, 105, 106, 112, 114, 115, 118, 120, 121, 122, 123, 128, 162, 166, 167, 170, 174, 175, 177, 180, 181, 182, 188, 191, 197, 199, 205, 209, 210, 218, 220, 224, 229, 230, 233, 235, 240, 354, 357, 358, 363, 367, 369, 371, 377, 378, 383, 388, 389, 404, 409, 417, 419, 426, 429, 433, 434, 436, 437, 438, 442, 444, 446, 391, 393, 394, 397, 400, 403 |
| 2 | C/o 320/ 120 MIG Houses at Jahangirpuri | 1993 | ND-5 |  | 120 |  |  |  |  | 76 |  |  |  |  | 44 |  |  | 44 | 58, 59, 60, 62, 64, 65, 66, 67, 72, 73, 80, 129, 131, 137, 138, 140, 141, 143, 242, 243, 245, 289, 293, 299, 301, 306, 311, 316, 317, 318, 319, 321, 328, 329, 330, 331, 333, 336, 341, 342, 345, 346, 348, 349 |
| 3. | C/o 320 / 176 MIG Houses at Jahangirpuri | 1999 | ND-5 |  | 176 |  |  |  |  | 161 |  |  |  |  | 15 |  |  | 15 | 2A, 5A, 8, 14, 15A, 22 A, 23, 25, 33A, 46, 256A, 260, 261A, 280A, 285A |
| 4. | C/o 480 LIG Houses at Pkt P (D) at Pitampura | 1986 | ND-5 |  |  | 480 |  |  |  |  | 479 |  |  |  |  | 1 |  | 1 | 70-C SF |
| 5. | C/o 396 LIG Pkt G&J (U) at Pitampura | 1987 | ND-5 |  |  | 396 |  |  |  |  | 393 |  |  |  |  | 3 |  | 3 | 110 C SF, 39D, TF, 92D, TF. |
| 6. | C/o 376 SFS at East Mukherjee Nagar | 1994 | ND-5 | 376 305G |  |  |  |  | 375 |  |  |  |  | 1 3 (SG) |  |  |  | 1 3 (SG) | 190 Cat.III G11, 25 & 29 (S.G.) |
| 7. | 1120 EWS Pkt-A-1 to A-4, Sector-17, Rohini | 1990 | ND-5 |  |  |  | 1120 |  |  |  |  | 1115 |  |  |  |  | 5 | 5 | Pkt-A, A-1, 314 GF, Pkt-A-2, 27 and 99 (GF), Pkt-A-4, 11 GF & 182 FF. |
| 8. | 192 LIG Houses at Ashok Vihar, Phase-I, Block-J | 1990 | ND-5 |  |  | 192 |  |  |  |  | 189 |  |  |  |  | 3 |  | 3 | 54C (SF), 55C (SF) and 79C (SF). |
| 9. | 72 SFS Houses at Block-BU, Pitampura | 1993 | ND-5 | 72 |  |  |  |  | 66 |  |  |  |  | 6 |  |  |  | 6 | 15 (TF), 27 (FF), 31 (TF), 39 (TF), 48 (TF) & 72 (TF) |

21	(b)	Details of Vacant Commercial Properties as on September, 2007

| Sl. No. | Name of Scheme | LSC/ CSC | Divn | Blk/ Pkt | Year / Comp | Constructed |  |  |  |  | Vacant |  |  |  |  | Specific No. of Vacant Shops |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Shops | Stall | VPF | Office | Kiosk | Shops | Stall | VPF | Office | Kiosk |  |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 |
| 1 | Pitamprua | CSC | ND-5 | B (D) | 1994 | 16 | 14 | -- | 5 | -- | 2 | -- | -- | -- | -- | 5 No. (GF) & 32 No. (FF) |
| 2 | Pitamprua | CSC | ND-5 | B (U) | 1989 | 25 | 14 | -- | 1 | -- | -- | 1 | -- | -- | -- | 13 No. (GF) |
| 3 | Pitamprua | CSC | ND-5 | K (U) | 1989 | 9 | 10 | -- | 1 | -- | 1 | -- | -- | -- | -- | 3 No. (GF) |
| 4 | Pitamprua | CSC | ND-5 | H(U) | 1988 | 14 | 7 | -- | 1 | -- | -- | -- | -- | 1 | -- | Office 1 No. (FF) |
| 5 | Pitamprua | CSC | ND-5 | Q(U) | 1989 | 14 | 17 | -- | 1 | -- | 1 | -- | -- | -- | -- | 1 (FF) |
| 6 | Pitamprua | CSC | ND-5 | F(D) | 1990 | 16 | 9 | -- | -- | -- | 2 | -- | -- | -- | -- | 19 (FF) & 20 (FF) |
| 7 | Pitamprua | LSC | ND-5 | L(U) | 1996 | 82 | -- | -- | -- | -- | 5 | -- | -- | -- | -- | 33 (GF), 55 (FF), 56 (FF), 57 (FF) and 82 (TF) |
| 8 | Shalimar Bagh | CSC | ND-5 | B (A) | 1980-81 | 21 | 9 | -- | -- | -- | 1 | -- | -- | -- | -- | 5 No. |
| 9 | Jahangirpuri 656 MIG Houses. | CSC | ND-5 |  | 2002 | 9 | -- | 6 | -- | -- | 9 | -- | 6 | -- | -- | 1 to 9 Shops 1 to 6 Open Platform |
| 10 | LSc at JJ Colony Mangolpuri, Block-K | LSC | ND-5 | K | 1993 | 16 | -- | -- | -- | -- | 14 | -- | -- | -- | -- | 54 to 56, 58 to 68 (Disputed) |
| 11 | Pitampura Sainik Vihar | CSC | ND-5 |  | 1993 | 19 | 14 | -- | 10 | -- | 7 | 3 | -- | 6 | -- | 1, 2, 4, 8, 15, 17, 18 Stall 1, 3 & 5 (RHS) Office: 3 to 6, 9 & 10 |
| 12 | C/o CSC No.I, Blk-A, Rohini, Sector-17 | CSC | ND-5 | A | 1995 | 51 |  | -- | -- | -- | 27 | 3 | -- | -- | -- | 10, 11, 12, 14, 15, 17, 18, 20 to 23, 32 to 38, 40, 41, 42, 44, 45, 46, 48, 50 & 51 Stall 53, 55 & 57 |
| 13 | C/o 6 Nos. Kiosks at Distt. Park, Pitampura |  | ND-5 |  | 1995 | -- | -- | -- | -- | 6 | -- | -- | -- | -- | 3 | 3, 5 & 6 |
| 14 | Builtup Kiosks at CC Road No.44, Pitampura |  | ND-5 | 2003 |  | -- | -- | -- | -- | 39 | -- | -- | -- | -- | 39 | 1 to 39 Kiosks |
| 15 | Shalimar Bagh | CSC | ND-5 |  |  | 21 | 9 | - | - | - | 1 | - | -- | - | - | 5 No. |

21.	(c)	Details of Vacant Commercial Plot as on September, 2007

| S.No. | Circle | Name of Scheme / Location of Plot | Specific No. of Plot. | Plot Detail |  |  | Whether demarcated or not | Position of Service if not available | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | No. | Size of Plot | Area in Sqm. |  |  |  |
| 1(i) | CC-12 | Mangolpuri Industrial Area Ph.-I, Blk-B | Community Centre | No. not mentioned in Drawing | 127.85 x 229 (Less ESS & Petrol Pump | 29277.65 (-) 1377.65 = 28900 Sqm. | Demarcated | Service available except Water supply |  |
| (ii) | CC-12 | Mangolpuri Industrial Area Ph.-I, Blk-B | Service Centre | - do - | 154 x 99.85 | 15377 Sqm. | Demarcated | - do - |  |
| (iii) | CC-12 | Mangolpuri Industrial Area Ph.-I, Blk-B | O.C.F. | - do - | 73.5 x 73 m. | 5366.00 Sqm. | Not Demarcated | - do - |  |
| (iv) | CC-12 | Mangolpuri Industrial Area Ph.-I, Blk-B | Internal Shopping Centre. | - do - | 50 x 16 m. | 800 Sqm | Demarcated | - do - |  |
| (v) | CC-12 | Mangolpuri Industrial Area Ph.-I, Blk-B | Weight bridge | - do - | 15 x 30 m. | 450 Sqm | Not Demarcated | - do - |  |
| (vi) | CC-12 | Mangolpuri Industrial Area Ph.-I, Blk-A | Bank, Dispensary, P.O. | - do - | 60 x 62 m. | 3720 Sqm | Not Demarcated | - do - |  |
| (vii) | CC-12 | Mangolpuri Industrial Area Ph.-I, Blk-A | Informal Shopping Centre | - do - | 54 x 30 m. | 1620 Sqm | Not Demarcated | - do - |  |
| 2 (i) | CC-12 | D/o land for H-5, Pitamapura | LSC at MP Enclave | 1 No. | -- | 6070.30 Sqm. | Not Demarcated | Service Available | Specific No. & size not available in Zonal Dev. Plan |
| (ii) | CC-12 |  | LSC at Kohat Enclave | 1 No. |  | 2832.81 Sqm. | Not Demarcated | Service Available | - do - |
| (iii) | CC-12 |  | LSC at Anand Vihar | 1 No. |  | 4046.87 Sqm. | Demarcated | Service Available | Partly encroached a temple and Jhuggies (800 Sqm.) exists size not available in the drawing |
| (iv) | CC-12 |  | LSC at Harsh Vihar | 1 No. |  | 6070.30 Sqm. | Demarcated | Service Available | Partly encroached a temple (1500 Sqm.) |
| (v) | CC-12 |  | LSC at Pitamapura Village | 1 No. |  | 3000.00 Sqm. | Demarcated | Service Available | Area of encroachment 1000 Sqm. |
| (vi) | CC-12 |  | LSc at Pahari Dhiraj Society | 1 No. |  | 2832.81 Sqm. | Demarcated | Service Available | Size not available in the drawing. |
| (vii) | CC-12 |  | LSC at 80’ wide road Police colony | 1 No. |  | 4046.87 Sqm. | Demarcated | Service Available | Plot are yet to be auction |
| (viii) | CC-12 |  | LSC at Sharda Niketan | 1 No. |  | 6070.30 Sqm. | Demarcated | Service Available | Platform yet to be allotted as partly piot auctioned to builders. |
| (ix) | CC-12 |  | LSC at Pitampura Village in front of IDPL | 1 No. |  | 4046.00 Sqm. | Demarcated | Service not Available | Drawing of LSC awaited from Sr. Arch. (NZ). |
| 3 (i) | CC-12 | D/o land for H-4-5 at Pitampura | CSC at MP Enclave | 1 No. |  | 1295.00 Sqm. | Demarcated | Service Available | Size not mentioned on the plan |
| (ii) | CC-12 |  | CSC at Sharda Niketan | 1 No. |  | 1618.75 Sqm. | Demarcated | Service Available | - do - |
| (iii) | CC-12 |  | CSC at Suraksha Enclave | 1 No. |  | 809.37 Sqm. | Demarcated | Service Available | - do - |
| (iv) | CC-12 |  | CSC at Krist Jyoti Enclave | 1 No. |  | 2023.43 Sqm. | Demarcated | Service Available | - do - |
| (v) | CC-12 |  | CSC at Harsh Vihar | 1 No. |  | 1780.62 Sqm. | Demarcated | Service Available | Partly encroached (600 Sqm.) by ESS and size not mentioned in the plan. |
| (vi) | CC-12 |  | CSC at IDPL Society | 1 No. |  | 1618.75 Sqm. | Demarcated | Service Available | Size not mentioned in the Plan |
| 4.(i) | CC-12 | D/o land for H5 (Pt.) Pitamapura | CSC near QU Block, Pitampura | 1 No. |  | 150 Sqm. | Partly demarcated | Service Available | Size not mentioned in the Plan |
| (ii) | CC-12 |  | CSC near A(U) Block, Pitampura | 1 No. |  | 400 Sqm. | Demarcated | Service Available | Size not mentioned in the Plan |
| 5 (i) | CC-12 | D/o land for H-4 – H-5 Pitampura | Near Saraswati Vihar Chowk | 1 No. |  | 4046.87 Sqm. | Demarcated | Service Available | Land use not given on plan specific No. & size not given in Dev. Plan Partly allotted to Gurudwara. |
| (ii) | CC-12 |  | Near Rani Bagh Gurudwara | 1 No. |  | 6070.30 Sqm. | Demarcated | Service Available | Status with DD (LM) NZ |
| (iii) | CC-12 |  | D/o land for H-5 (Pt.) Pitampura in D (P) Block Pitampura | 1 No. |  | 323.75 Sqm. | Demarcated | Service Available | Specific no. and size not given in Dev. Plan. |
| (iv) | CC-12 |  | In H (U) Block Pitampura | 1 No. |  | 607.03 Sqm. | Demarcated | Service Available | Specific no. and size not given in Dev. Plan. |
| 6. (i) | CC-12 | D/o Community Center on Road No.44 | Vegetable Market Plot No.1 | 1 No. |  | 1600 Sqm. | Demarcated | Service Available | Specific no. and size not given in Dev. Plan. |
| (ii) | CC-12 |  | M.S. Office building Plot No. 3 | 1 No. | 64.76 x 30.50 m. | 1975.18 Sqm. | Demarcated | Service Available |  |
| (iii) | CC-12 |  | Sub Station Plot No.6. | 1 No. |  | 557.40 Sqm. | Demarcated | Service Available | Size not mentioned on Drawing |
| (iv) | CC-12 |  | Post Office Plot No. 20 | 1 No. |  | 329.28 Sqm. | Demarcated | Service Available | Size not mentioned on Drawing |
| (v) | CC-12 |  | Sub Station Plot No. 21 | 1 No. | 14.62 x 10.00 m. | 146.20 Sqm. | Demarcated | Service Available |  |
| (vi) | CC-12 |  | Electric Sub- Station Plot No. 22 | 1 No. | 18.58 x 30.00 m. | 557.40 Sqm. | Demarcated | Service Available |  |
| (vii) | CC-12 |  | Cultural Centre Plot No. 34 | 1 No. |  | 2023.00 Sqm. | Demarcated | Service Available | Size not mentioned on Drawing |
| 7 (i) | CC-12 | Facility Centre adjoining Road No. 44 CC Pitampura | Parting Plot No.1 (i) Parking Plot | 1 No. |  | 2000 Sqm. | Demarcated | Service Available | Site partly available |
|  |  |  | (ii) Parking Plot | 2 No. |  | 2000.75 Sqm. | Demarcated | Service Available | Site partly available |
| (ii) | CC-12 |  | Parking Plot No.2 | 1 No. |  | 2000.75 Sqm. | Demarcated | Service Available | Site partly available |
| 8. | CC-12 | Service Centre No.18 near Jai Shiv Society on Road No.43, Pitampura |  |  |  | 3156.56 Sqm. | Demarcated | Service Available | Size of plot not mentioned on the drawing. |
| 9 | CC-12 | D/o CC on road No.42, Plot 30 Nos. (7,8,9,10) Allotted |  |  |  | 4100 Sq.m. | Demarcated | Service Available | 6 Nos. religious structure, lev. and Sewa Bharti Kendra Area 2100 Sqm. |
| 10 | CC-12 | Near Neelamber Apartment Opp. Sainik Vihar Gate No.4 | Vacant land / plot c.s.c |  |  |  | Not Demarcated | -- | Partly encroach area 500 Sqm. |
| 11 | CC-12 | Community Hall in BU Block Pitampura | Community Hall | 1 No. | 27.50 x 62.60 m. | 1724.00 Sqm. | Demarcated | Service Available | Vacant |
| 12 | CC-12 | Vacant land near AU Block, Pitampura Pt. (H-5) |  | 1 No. |  |  | Not Demarcated | Not available | Encroachment as Jhuggi Cluster (5000 Sqm.) |
| 13 | CC-12 | CSC East of Mukerji Nagar | CSC | 1 No. |  | 2480 Sqm. | Demarcated | Service Available | One Temple constructed by RWA 376 SFS Houses at East of Mukerji Nagar. Area of encroachment 100 Sqm. |
| 14 | CC-12 | LSC at Pkt-CD, Pitampura | LSC | 1 No. | 9 x 14 m | 126.00 Sqm. | Demarcated | Service Available | Vacant |
| 15 | CC-12 | Community Hall at 656 MIG Houses Jhangirpuri | Community Hall | 1 No. | Odd Plot | 1400 Sqm. | Demarcated | Service Available | Vacant |

21.	(d)	Details of  Vacant Residential Plot as on September, 2007

| S.No. | Circle | Name of Scheme / Location of Plot | Specific No. of Plot. | Plot Detail |  |  | Whether demarcated or not | Position of Service if not available | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | No. | Size of Plot | Area in Sqm. |  |  |  |
| 1 | CC-12 | D/o 16.92 hact. land at Model Town | 34 Nos. | 63, 64 to 69 | 11X 22.50 10X 22.50 11X 22.50 | 247.50 m2 225.00 m2 247.50 m2 |  |  |  |
|  |  |  |  | 71 (ODD Plots) 327.25 m2 72 “ 282.50 m2 73 ” 267.50m2 74 “ 252.50 m2 75 “ 237.50m2 76 “ 222.50m2 77 “ 207.50m2 78 “ 213.95m2 79 “ 306.87m2 80 to 86 9 X 21.20 190.80 m2 87 and 88 11.75 X 21.20 249.10 m2 89 to 95 9 X 21.20 190.80m2 96 (odd plots) 242.21 m2 |  |  |  |  |  |
| 2 | CC-12 | Between Sainik Vihar & Defence land in Sakur Basti | Plot 1 to 3 | 3 Nos. | 25 X 12m | 300 Sqm | Demarcated | Service Available |  |
|  |  |  | Plot 4 | 1 No. | Odd Plot | 300.00 Sqm. | Demarcated | Service Available |  |
|  |  |  | Plot 5 to 8 | 4 No. | 25x11 m. | 275.00 Sqm. | Demarcated | Service Available |  |
|  |  |  | Plot No. 9 | 1 No. | Odd Plot | 425.00 Sqm. | Demarcated | Service Available |  |
|  |  |  | Plot No. 10 | 1 No. | Odd Plot | 225.00 Sqm. | Demarcated | Service Available |  |
|  |  |  | Plot No.11 | 1 No. | Odd Plot | 250.00 Sqm. | Demarcated | Service Available |  |
| 3. | CC-12 | 12 Nos. Plots near IDPL Society, Pitampura | Plot No. 1 (Corner) | 1 No. |  | 245.75 Sqm. | Not Demarcated | Service Available | Drawing are not available |
|  |  |  | Plot No. 2 | 1 No. |  | 254.74 Sqm. | Not Demarcated | Service Available | Drawing are not available |
|  |  |  | Plot No. 3 | 1 No. |  | 259.20 Sqm. | Not Demarcated | Service Available | Drawing are not available |
|  |  |  | Plot No. 4 | 1 No. |  | 263.84 Sqm. | Not Demarcated | Service Available | Drawing are not available |
|  |  |  | Plot No. 5 | 1 No. |  | 269.58 Sqm. | Not Demarcated | Service Available | Drawing are not available |
|  |  |  | Plot No. 6 | 1 No. |  | 271.79 Sqm. | Not Demarcated | Service Available | Drawing are not available |
|  |  |  | Plot No. 7 | 1 No. |  | 217.60 Sqm. | Not Demarcated | Service Available | Drawing are not available |
|  |  |  | Plot No. 8 | 1 No. |  | 201.70 Sqm. | Not Demarcated | Service Available | Drawing are not available |
|  |  |  | Plot No. 9 | 1 No. |  | 199.85 Sqm. | Not Demarcated | Service Available | Drawing are not available |
|  |  |  | Plot No. 10 | 1 No. |  | 186.50 Sqm. | Not Demarcated | Service Available | Drawing are not available |
|  |  |  | Plot No. 11 | 1 No. |  | 175.00 Sqm. | Not Demarcated | Service Available | Drawing are not available |
|  |  |  | Plot No. 12 (Corner) | 1 No. |  | 175.00 Sqm. | Not Demarcated | Service Available | Drawing are not available |

Note:	The reports of the vacant plots are as per site however the actual position may be verified from Land Department as the same are allotted by them.

22.	Jrisdiction of CE / Map. EE wise.	:	Pitamapura H-4, H-5 & H-5 (Part) Mangolpuri, 656 MIG Houses at Jahangirpuri, Model Town and Mukerji Nagar.

23.	Details of land handed over to Engineering 	:	Nil

Wing for Development.

24.	Position of Regular Staff	:

| S.No. | Designation | Sanction Strength | Men in Position | Vacant Position |
| --- | --- | --- | --- | --- |
| 1 | Executive Engineer | 1 | 1 | -- |
| 2 | Asstt. Engineer | 5 | 5 | -- |
| 3 | Junior Engineer | 14 | 14 | -- |
| 4 | Asstt. Account Officer | 1 | 1 | -- |
| 5 | Head Clerk | 1 | 1 | -- |
| 6 | Steno | 1 | 1 | -- |
| 7 | U.D.C. | 4 | 3 | 1 |
| 8 | D/Man Gr-II | 1 | 1 | -- |
| 9 | L.D.C. | 6 | 4 | 2 |
| 10 | Driver | 1 | 1 | -- |
| 11 | Peon | 4 | 4 | -- |
| 12 | Security Guard | 2 | 3 | -- |
| 13 | Daftary | -- | -- | 1 |
| 14 | Beldar | -- | 9 | -- |
| 15 | Mason | -- | 1 | -- |
| 16 | Env. Asstt. | -- | 1 | -- |
| 17 | Sanitary Mate. | -- | 1 | -- |

Sent to Director (System) through E-mail at

(1)	ddatender@dda.org.in

(2)	dirsystem@dda.org.in