LIST OF ACTIVITIES

| 1. | Details of Pending Final Bills & non-ref. of Security Deposits. |
| --- | --- |
| Name of Work | Agencies | Agmt. No. | Esst. Cost. Tender Cost | Stipulated | Remarks |
|  |  |  |  | D.O.S. D.O.C. |  |
| (i) | D/o Yamuna River Front (West Bank) along Vijay Ghat (Pushta) S.H. : C/o Water body at Yamuna Pushta | M/s Amar Constn. Co. | 76/EE/ND-I/DDA/ 04-05 | Rs.60,36,559/- Rs.16,49,051/- | 07.03.2005 06.07.2005 | Due to non submission of case by the earlier staff. |
| (ii) | --DO— S.H. : C/o root-zone channel in Phase-I at Yamuna Pushta. | M/s Birender Constn. Co. | 36/EE/ND-1/DDA/04-05 | Rs.7,68,600/- Rs.2,33,520/- | 31.10.04 30.11.04 | --do-- |
| (iii) | All due securities are being refunded on the request of respective Agencies. |  |  |  |  |  |
| 2. | Present status of works |
| S. No | Name of work | Estt. Cost Tendered Cost | D.O.S. D.O.C. | Progress up to previus month | Progress during this month | Up to date progress | Remarks |
| (i) | D/O Green belt block B to I Ashok Vihar ph-1 SH: P/L Unfiltered water supply line in front of block B to E Agency: Rajinder Singh | Rs.6,30,584/- Rs.10,60,907/- | 27.04.07 26.06.07 | 65% | 35% | 100% | Completed D.O.C. 10.07.2007 |
| (ii) | D/O Green Belt along block B to I AshokVihar, Phase- 1 SH: C/O 2Nos. pump Agency: M/S Robin Const. Co. | Rs. 1,27,471/- Rs. 1,38,885/- | 30.01.07 30.03.07 | 80% | 20% | 100% | Completed D.O.C. 30.05.2007 |
| (iii) | M/O Park/plantation of Hort. Wing under North Zone SH: Repairing of bondary wall at Khoje Wala Bagh park, Ashok vihar Ph.-1 Agency : Bajrang Engineering | Rs.2,80,,534/- Rs.3,74,122/- | 26.03.07 25.05.07 | 80% | 20% | 100% | Completed D.O.C. 12.06.2007 |
| (iv) | D/O Janak Wala Bagh at Bharat Nagar , Ashok Vihar Ph.-IV SH: C/O Parking area in Ph.-I Agency : Sh. Kundan Lal | Rs.6,91,001/- Rs.7,16,164/- | 15.07.07 14.09.07 | - | - | - | Work started on 18.07.07 |
| (v) | D/O Janak wala Bagh at Bharat Nagar Ashok Vihar Ph.-IV SH: C/O Red bajri path Agency : Sh. Yash Pal Singh | Rs.5,24,268/- Rs.33,54,574/- | 22.07.07 21.09.07 | - | - | - | Work started on 18.07.07 |
| (vi) | M/O Park/plantation of Hort. Wing under North Zone SH: Rpairing of burnt room of A/C branch & sub division office of Hort. Division –II Rama Market Pitampura Agency: R. K. Rodhiya | Rs.2,37,419.00 Rs.2,40,619.00 | 10.05.07 09.07.07 | 10% | 90% | 100% | Completed D.O.C. 02.07.07 |
| (vii) | M/O Park/plantation of Hort. Wing under North Zone SH:Improvement of existing boundary wall in Gonal Green Park, Sarswati Vihar Agency : R. K. Rodhiya | Rs. 1,90,670/- Rs.1,68,197/- | 19.07.07 18.09.07 | - | - | - | Work started on 19.07.07 |
| (viii) | M/O Park/plantation of Hort. Wing under North Zone SH: Raising of existing grill at Harsh Vihar park Pitampura Agency : R. K. Rodhiya | Rs. 1,98,745/- Rs.2,35,138/- | 19.07.07 03.09.07 | - | - | - | Work started on 19.07.07 |
| (ix) | M/O Park/plantation of Hort. Wing under North Zone SH: Repair of boundary of wall in M. D. park Lawrence Road Agency: S.V. Const. | Rs.1,35,051/- Rs.1,74,691/- | 30.03.07 29.05.07 | 30% | - | 30% |  |
| (x) | M/O Park/plantation of Hort. Wing under North Zone SH: Repair of boundary wall and scatting ring Of distt. Park Pitampura Agecy: Pankaj Chhatirya | Rs.1,62,436/- Rs.1,31.174/- | 08.05.07 07.07.07 | 85% | 15% | 100% | Completed D.O.C..06.07.07 |
| (xi) | M/O Park/plantation of Hort. Wing under North Zone SH: Repair and restoration of boundary wall in Nepal Wala Bagh. Agency: N.K. Enterprises | Rs.2,55,941/- Rs.2,28,588/- | 14.05.07 13.07.07 | 85% | 15% | 100% | Completed D.O.C..10.07.07 |
| (xii) | M/O Park/plantation of Hort. Wing under North Zone SH: Improvement of foot path in Maharishi Daya Nand park at Lawrence road Agency : N.K. Enterprices | Rs.4,10,040/- Rs.2,72,981/- | 22.07.07 21.09.07 | - | - | - | Work yet to be start |
| (xiii) | M/O Park/plantation of Hort. Wing under North Zone SH: Repair of path and water supply line of Distt. Park Pitampura Agency : N.K. Enterprices | Rs.2,70,.594/- Rs. 1,86,433/- | 22.07.07 21.09.07 | - | - | - | Work yet to be start |
| (xiv) | M/O Park/plantation of Hort. Wing under North Zone SH: Improvement of foot path in Maharishi Daya Nand park at Lawrence road Agency : N.K. Enterprices | Rs.4,10,040/- Rs.2,72,981/- | 22.07.07 21.09.07 | - | - | - | Work yet to be start |
| (xv) | M/O Park/plantation of Hort. Wing under North Zone SH: Maintaince in R/O Sweeping, Scavanging, Cleaning of 4Nos. toilet and fountain area in distt. Park Pitampura Agency: M/S Venus Associates | Rs.44,4,36/- Rs.23,7,60/- | 24.03.07 23.09.07 | 50% | 15% | 65% |  |
| (xvi) | M/O Park/plantation of Hort. Wing under North Zone SH:Repair of boundary wall in parks near road no.42,Pitampura Agency:M/S N.K. Enterprises | Rs.492532/- Rs.3.15279/- | 26.04.07 25.06.07 | 100% | - | 100% | Completed |
| (xvii) | D/O Land Biodiversity park at Jharoda Mazra &Wazirabad SH: Cleaning & Sweeping of Nature Interpellation Center, path & parking in visitors area Agency: M/S Harender singh | Rs.82,392.00 Rs.52,800.00 | 18.07.07 17.07.08 | - | - | - | Work started on 18.07.07 |
| (xviii) | D/O Land Biodiversity park at Jharoda Mazra &Wazirabad SH: Strengthening of approach road from Junction to Yamuna Biodiversity Park Agency: M/S A.S.Builder | Rs.35.04, 89/- Rs.,41,75,570/- | 07.09.06 06.01.07 | 5% | 65% | 70% |  |
| (xix) | D/O land under North Zone SH: C/O boundary wall of park between Sanik Vihar and Shakti Vihar Agency: Robin const. co. | Rs. 9,16,334/- Rs. 12,60,267/- | 26.04.07 25.06.07 | 10% | 25 | 35% |  |
| 3. | Projects held up due to Court Case -- Respective Court with Case No. -- Date of Next Hearing | Nil |
| 4. | Rain Water Harvesting -- Already Provided -- Proposed | Nil Nil |
| 5. | Water bodies -- identified, status & under encroachment. | There are three numbers developed water body identified as water body No. 41(a), 42(a) and 34(a) |
| 6. | Details of Deposit Works : (a) in hand (b) Under approval - Status | Nil |
| 7. | Details of deviation in works : (a) Undertaken (b) Proposed (In Principle Approval) |
| S.No. | Name of work | Agency | Agg. No. | Tendered Amount | Total Work Done | Deviation | Remarks |
| (i) | Park and Plantation of Horti Wing under North Zone. S.H. : R/o Burnt Room A/c Branch and Sub-Division Horticulture Division, Rama Market, Pitampura | R.K. Rodhiya | 6/EE/ND1/ 2007-2008 | 2,40,619.00 | 2,80,956.00 | 16.76% | a) Deviation already passed in form of Extra Item Statement-I by the Competent Authority. b) Nil |
| (ii) | Fencing of vacant land under North Zone. S.H. : Removal / Disposal of building rubbish from koki wala Bagh to temple at Bharat Nagar Ashok Vihar, Phase-IV. | Ramesh Chillar | 53/EE/ND1/DDA/2006-2007 | 4,96,260.00 | 5,48,462.00 | (+) 10.52% | a) Deviation already passed by the Competent Authority. b) Nil |
| (iii) | M/o parks / plantation of Hort Wing under North Zone S.H. : Repairing of foot path & disposal of malba at N.H.8, Satyawati Colony, Ashok Vihar, Phase-IV | M/s Robin Constn. Co. | 55/EE/ND-I/DDA/2006-2007 | 1,09,000/- | 1,29,164/- | (+) 18.50% | a) Deviation already passed by the Competent Authority. b) Nil |
| (iv) | Fencing of DDA Land under North Zone S.H. : Repairing of B/Wall and providing missing grills on B/Wall at picnic Hut Ashok Vihar, Ph-III | M/s Anurag Brothers | 47/EE/DN1/DDA/2006-2007 | 1,50,843/- | 1,68,685/- | (+) 11.83% | a) Deviation already passed by the Competent Authority. b) Nil |
| (v) | M/o Parks / plantation of Hort. Wing under North Zone S.H. : Repair of Distt. Part at Multan Nagar. | Sh. Ramesh Kumar Rodhiya | 59/EE/ND1/DDA/2006-2007 | 1,96,143.00 | 2,44,688.00 | 24.75% | a) Deviation already passed by the Competent Authority. b) Nil |
| (vi) | M/o Parks / Plantation of Hort Wing under North Zone. S.H. : Repair in Parks near Parmarth Hospital, Pitampura, Delhi | M/s Vats Constn. Co. | 01/EE/ND1/DDA/07-08 | 2,22,502.00 | 2,47,532.00 | 11.24% | a) Deviation already passed by the Competent Authority. b) Nil |
| 8. | Restricted Call of tenders | D/o Land for Bio-diversity park at Jharoda Mazra and Wazirabad S.H. : Arrangement of Private Security along Green House Office Building, Interpretation Center and in the area. |
| 9. | Rescinded Works. | Nil |
| 10. | Arbitration & related Court Cases |
| a) | Arbitration | Nil |
| b) | Court Cases |
| S.No | Description of Item | Agency | Name of Court Case No. | Name of P/L | Next date of Hearing |
| (i) | C/o 560 MIG DU’s at Pkt. (P) Pitampura S.H. : C/o 192 MIG DU’s at Pitampura | M/s Prakash Sharma | Supreme Court SLP (C) 2872/01 | Mrs. Kum Kum Sen. | Pending for want of irregular hearing |
| (ii) | C/o 720 LIG DU’s at Pitampura Pkt. W(P) SH. : C/o 396 LIG DU’s at Pitamprua Pkg. W(P) i/c Internal services. | M/s Sudhir Brothers | High Court OMP. 93/88 | Mrs. A. Salwan | Pending for want of hearing w.e.f. 27.07.2006 |
| (iii) | C/o 330 LIG Incremental houses i/c internal water supply sanitary installation & internal development work in sector B-IV Pkt. 6 Gr.1 at Narela. | M/s Nav Bharat Const. Co. | High Court OMP 285/06 | Sh. Bhupesh Narula | 14.08.2007 |
| (iv) | C/o 770/324 LIG DU’s at Pitampura Pkt. (W) (P) | M/s Verma Const. Co. | High Court OS-765/06 | Sh. Bhupesh Narula | 23.07.2007 |
| (v) | C/o MIG / LIG Shop & Services 256 Hact. Land at Sarai Khalil SG : C/o Road (Balance work) | M/s Ajay Verma | Tis Hazari EY/123/06 | S.L.O. (T.C.) | 07.09.2007 |
| (vi) | C/o 64 Three B/R 64 Two B/R & 96 Scooter Garage under SFS at Pitamprua | M/s Sudhir Brothers | Tis Hazari 112/03 | Mrs. Beena Sharma | 17.08.2007 |
| (vii) | M/o Parks / Plantation Hort. Wing under North Zone SH. : Sinking of tubewell & P/F unfiltered water line behind of Kirpal Bagh (Joginder Wala Bagh) Gujaran Wala Town Phase-III | Sh. S.D. Falwaria | Tis Hazari 87/2005 | Mrs. Shushma Sharma | 21.07.2007 |
| (viii) | D/o green belt in front of Bl. E to I in Ashok Vihar Phase-I SH. : C/o Cement Concrete tiles and moorum path in front of bl. E to I. | M/s Durga Const. Co. | Tis Hazari 216/04 | Sh. K.D. Sharma | 23.07.2007 |
| 11. | Details of Q.C. Lab. Tests, procedures | N.A. |
| 12. | Fire fighting Equipments : Installed (Nos.) with Location | Not installed as yet |
| 13. | List of Soil Testing Laboratories | Are issued by E.M. Office |
| 14. | List of Approved Structural Consultants | Does not pertain to this office |
| 15. | Technical Circulars | Are issued by V.C., E.M., C.E. (Q.C.) and Vigilance Department |
| 16. | Q.C. Circulars | Are issued by QAC, DDA |
| 17. | List of Contractors, A, B, C, D categories | Pertains to CRB/DDA |
| 18. | RIS/ EIS/ EOT Cases & Completion Certificate |
| S.No | Name of Work | Agency | Agreement No. | EIS | RIS | SIS | Amount | EOT |
| (i) | M/o Parks / Plantation of Hort. Wing under North Zone. S.H. : R/o Burnt room A/c branch and Sub-Div.-II Rama Market, Pitampura | R.K. Rodhiya | 6/EE/ND1/ 2007-08 | EIS No.1 | -- | -- | 40337/- | EOT not required |
| (ii) | Fencing of DDA land under North Zone S.H. : Repairing of B/wall and providing missing grills on B/Wall at Picnic Hut Ashok Vihar, Ph-III | M/s Anurag Brothers | 47/EE/ND1/ 2006-07 | EIS No.1 | -- -- | I -- | 17032/- 3145/- | Not required |
| (iii) | D/o Yamuna River Front (West Bank) along Vijay Ghat (Pushta) S.H. : C/o Water body at Yamuna Pushta | M/s Amar Constn. Co. | 76/EE/ND-I/DDA/ 04-05 | -- | -- | -- | -- | Remarks C.C. to be recorded |
| (iv) | --DO— S.H. : C/o root-zone channel in Phase-I at Yamuna Pushta. | M/s Birender Constn. Co. | 36/EE/ND-1/DDA/04-05 | -- | -- | -- | -- | Remarks C.C. sent to competent authority for counter signed |
| (v) | M/O Parks & Plantation of Hort. Wing under North Zone. S.H. : Repair of Distt. Park at Multan Nagar. | Sh. Ramesh Kumar Rodhiya | 59/EE/ND1/DDA/2006-2007 | EIS No. I | -- | -- | 4131/- | E.O.T. Not required |
| (vi) | M/o Parks Plantation of Hort Wing under North Zone S.H. : Repair in Parks near Parmarth Hospital Pitampura | M/s Vats Cons. Comp. | 1/EE/ND1/DDA/2007-2008 | EIS No.1 | -- | -- | 8462/- | --do-- |
| (vii) | M/o Parks & Planatation & Hort Wing under North Zone S.H. : Repair and Boundary Wall in Parks near Road No.42 Pitampura | M/s N.K. Enterprises | 4/EE/ND1/DDA/2007-2008 | EIS No.1 | -- | -- | 14000/- | --do-- |
| (viii) | M/o Parks and Plantation Hort Wing under North Zone. S.H. : Repair & Restoration of Boundary Wall in Nepal Wala Bagh Lawrence Road | M/s N.K. Enterprises | 4/EE/ND1/ DDA/ 2007-2008 | EIS No.1 EIS No.2 | -- -- | -- -- | 14000/- 30451/- | -do-- |
| 19. | List of approved rates of SE (P) | Are issued by Chairman Market Rate Approval Committee / Concerned SE (P) |
| 20. | Areas where services are handed over to MCD / DJB & Deficiency charges | N.A. |
| 21. | List of vacant flats / Shops / Keosk / Commercial / Residential Plots on the date of completion / development. | N.A. |
| 22. | Jurisdiction of C.E. / Map. EE wise | Asstt. Engineer-I D/o land for Bio-diversity Park at Jharoda Mazra Wazirabad Phase-I & II D/o Park between Sainik Vihar AND Shakti Vihar D/o Park at Sandesh Vihar and Shakti Vihar Ashok Vihar Phase-II Khojjay Wala Park Children Play Area 21 Bigha Park Chandi Wala Park NHP at Bada Kuan Ashok Vihar Phase-III Khimmen Singh Park Picnic Hut with Park NHP at Satyawati Colony Asstt. Engineer-II Sanjay Van Park Pitampura Distt. Park Harsh Vihar Pitampura Distt. Park Saraswati Vihar, Pitampura Lok Vihar, Pitampura Kohat Enclave, Pitampura Sanjay Park, Pitampura Western Enclave Park, Pitampura Suvidha Kunj Park, Pitampura Tarun Enclave, Pitampura Brij Vihar, Pitampura Anand Vihar, Pitampura Deepali Chowk, Pitampura Chanderlok Pitampura Orchid and Shakurpur Rajdhani Enclave Pitampura Asstt. Engineer-III Ashok Vihar Phase-I Green Belt along Block B to I Lekh Ram Park Ashok Vihar Phase-IV Ashoka Garden Zonal Green Bharat Nagar (a) Janak Wala Bagh Shastri Nagar 56 Bigha Park Shastri Nagar Park Gulabi Bagh District Park Sindhora Kalan Park Faiz Road Park Idgah Park Asstt. Engineer-IV Distt. Park Pitampura NHP at Block H(U) Pitampura Distt. Park Double Tank Pitampura NHP at Lala Wala Bagh at Pitampura ND Park Pitampura Distt. Park Multan Nagar (Sehdev Singh Park) Punjabi Bagh NHP Near Parmarth Hospital Pitampura NHP at Near NH 42 Pitampura Mazdoor Wala Park at Lawrence Road Rose Garden Park at Lawrence Road Nepal Wala Bagh at Lawrence Road Pahari Wala Bagh at Lawrence Road MD Park at Lawrence Road NHP at Block T (P) Pitampura NHP at Block T(P) & S(P) Pitampura Aziz Bux Wala Bagh at Pitampura NHP at Block R(P) Pitampura |
| 23. | Details of land handed over to Engineering Wing for development | 157 Acre for D/o Land Bio-Diversity Park at Jharoda Mazra PH-I is in progress and 300 Acre land for Bio-diversity Park at Jharoda Mazra Wazirabad Ph-II has been taken over by Engineering Wing. |
| 24. | Sanctioned Strength / In place / vacancy position of Regular Staff |
| S.No | Designation | Sanctioned Strength | Men in Position | Shortfall | Excess |
| 1. | E.E. © | 1 | 1 | -- | -- |
| 2. | A.E. © | 5 | 4 | 1 | -- |
| 3. | A.A.O. | 1 | 1 | -- | -- |
| 4. | Head Clerk | 1 | 1 | -- | -- |
| 5. | Steno | 1 | 1 | -- | -- |
| 6. | J.E. (C) | 12+1 | 13+1 | -- | 1 |
| 7. | D/Man | 1 | 1 | -- | -- |
| 8. | U.D.C. | 4 | 4 | -- | -- |
| 9. | L.D.C. | 6 | 3 | 3 | -- |
| 10. | Daftry | 1 | 1 | -- | -- |
| 11. | Peon | 4 | 4 | -- | -- |
| 12. | S.C.D. | 1 | 1 | -- | -- |

EXECUTIVE ENGINEER

ND-1, DDA