DELHI DEVELOPMENT AUTHORITY

# ELECTRICAL DIVISION – 2 / ELECTRICAL CIRCLE -I

| 1. Progress Report of works costing of more than 2 Lakhs. |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| S. No. | Name of Scheme | Estt. / Tender Cost | Agent No. | Agency | Date of Start Time of comp. (Period) | Supplementary Agent if drawn | Physical ____% of Allotment | Payment Made upto (in lacs) |
| 1. | C/o 384 SFS houses in Pkt 1& 2, Sec 3, Dwarka, Phase II |  |  |  |  |  |  |  |
| (a) | IEI of 120 SFS Cat. II + 72 SFS Cat III & 144 Scooter Garages in Gr. II | 1600316.00 1647845.00 | 83/ED-2/92-93 | S. K. Const. Pvt. Ltd. | 7.1.93 30 months | Draw in 95-96 | 90% | 16.08 |
| (b) | I.E.I. of 120 SFS Cat II + 72 SFS Cat III & 144 Scooter Garage in Gr. II | 1600316.00 1647845.00 | 84/ED-2/92-93 | S. K. Const. Pvt. Ltd. | 7.1.93 30 months | Draw in 95-96 | 85% | 16.08 |
| 2. | C/o 456 (342 MIG + 144 LIG Four storyed & 342 scooter garage. |  |  |  |  |  |  |  |
| (a) | I.E.I. 126 MIG + 42 LIG & 126 Scooter garage in Gr. I | 1013068.00 1087022.00 | 113/ED-2/92-93 | S. K. Const. Pvt. Ltd. | 1.4.93 30 months | Draw in 95-96 | 85% | 9.80 |
| (b) | IEI of 120 MIG & 42 LIG & 120 Scooter garge in Gr. II | 964739.00 1035165.00 | 114/ED-2/92-93 | S. K. Const. Pvt. Ltd. | 1.4.93 30 months | Draw in 95-96 | 88% | 9.94 |
| (c) | I.E.I. of 96 MIG & 32 LIG & 96 scooter garage in Gr. III | 771672.00 828004.00 | 115/ED-2/92-93 | S. K. Const. Pvt. Ltd. | 1.4.93 30 months | Draw in 95-96 | 88% | 8.00 |

| S. No. | Name of Scheme | Estt. / Tender Cost | Agent No. | Agency | Date of Start Time of comp. (Period) | Supplementary Agent if drawn | Physical ____% of Allotment | Payment Made upto (in lacs) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3. | 2693/2714 EWS & 358/376 LIG Dus in Pkt 3 Bindapur |  |  |  |  |  |  |  |
| (i) | 240 EWS + 40 LIG BLK D III Pkt 3, Bindapur | 518211.00 644914.00 | 131\ED-2\91-92 | M/s Metro Elect. Co. | 15.2.92 30 Months |  | 50% |  |
| (ii) | 268 EWS + 36 LIG blk B-1, Pkt 3, Bindapur | 651313.00 692334.00 | 132\ED-2\91-92 | M/s Metro Elect. Co. | 15.2.92 30 Months |  | 52% |  |
| (iii) | 278 EWS + 40 LIG blk D-1, Pkt 3, Bindapur | 583695.00 726408.00 | 133\ED-2\91-92 | M/s Metro Elect. Co. | 15.2.92 30 Months |  | 45% |  |
| (iv) | 282 EWS +23 LIG blk DII, Pkt 3, Bindapur | 629711.00 763675.00 | 134\ED-2\91-92 | M/s Metro Elect. Co. | 15.2.92 30 Months |  | 47% |  |
| (v) | 309 EWS + 32 LIG blk A Pkt 3 Bindapur | 616521.00 767260.00 | 135\ED-2\91-92 | M/s Metro Elect. Co. | 15.2.92 30 Months |  | 60% | 6.55 |
| (vi) | 284 EWS +36 LIG blk B II Pkt 3 Bindapur | 584094.00 726909.00 | 136\ED-2\91-92 | M/s Metro Elect. Co. | 15.2.92 30 Months |  | 60% | 5.97 |
| (vii) | 280 EWS + 36 LIG blk E III Pkt 3 Bindapur | 547863.00 681816.00 | 137\ED-2\91-92 | M/s Metro Elect. Co. | 15.2.92 30 Months |  | 40% | 6.27 |
| (viii) | 255 EWS + 55 LIG blk E II Pkt 3 Bindapur | 557169.00 693397.00 | 116\ED-2\91-92 | M/s H.O. Elect. | 15.2.92 30 Months |  | 45% | 6.64 |
| (ix) | 113 EWS + 20 LIG blk B III Pkt 3, Bindapur | 227362.00 282958.00 | 142\ED-2\91-92 | M/s Shaka Electric | 15.2.92 30 Months |  | 36% | 6.59 |
| (x) | 220 EWS + 20 LIG blk B III, Pkt 3, Bindapur | 430340.00 | 56\ED-2\04-05 | M/s Metro Elect. Co. | 03.04.05 12 Months |  | 50% | 1.60 |
| (xi) | 202 EWS + 24 LIG blk B III Pkt 3 , Bindapur | 400015.00 | 57\ED-2\04-05 | M/s Metro Elect. Co. | 03.04.05 12 Months |  | 40% | 1.01 |
| S. No. | Name of Scheme | Estt. / Tender Cost | Agent No. | Agency | Date of Start Time of comp. (Period) | Supplementary Agent if drawn | Physical ____% of Allotment | Payment Made upto (in lacs) |
| (xii) | C/o 224 Janta & 55 LIG Dus at Isolated Pkt 10, Naseerpur | 837922.00 862641.00 | 23\ED-2\92-93 | M/s Metro Elect. Co. | 12.06.92 30 Months | Draw in 95-96 | 77% | 7.93 |
| 4. | 470 (198 MS & 272 MIG Pkt 8, Sector 12, Dwarka |  |  |  |  |  |  |  |
| (i) | 128 MIG dus Gr. I | 1853140.00 1446045.00 | 9\ED-2\2002-3 | M/s Bharat Elect. Co. | 20/5/02 12 Months | Not | 91% | 11.06 |
| (ii) | 144 MIG Dus Gr. II | 2084981.00 1626924.00 | 10\ED-2\2002-3 | M/s Bharat Elect. Co. | 20/5/02 24 Months | Not | 92% | 12.55 |
| 5. | 264 MIG houses in Pkt 7, Sector 12, Dwk |  |  |  |  |  |  |  |
| (i) | 136 HIG houses | 1543350.00 1328288.00 | 2\ED-2\2001-2 | M/s Ajanta Electrical | 24/5/01 24 Months | Not | 90% |  |
| (ii) | 128 MIG houses | 1439151.00 1238794.00 | 3\ED-2\2002-3 | M/s Ajanta Electrical | 24/05/01 24 Months | Not | 90% |  |

2.	Rescinded works

| S. No. | Name of Scheme | Rescinded Works Tender Cost | Agent No. | Agency | Date of Start Time of comp. (Period) | Physical Progress |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | 220 EWS +20 LIG blk B III, Pkt 3, Bindapur | 430340.00 | 56/ED-2/2004-05 | M/s Metro Electrical Co. | 03/04/05 12 Months | 50% |
| 2. | 202 EWS +24 LIG blk B-II, Pkt 3, Bindapur | 400015.00 | 57/ED-2/2004-05 | M/s Metro Electrical Co. | 03/04/05 12 Months | 40% |

3.	Court Case

STATUS REPORTS OF COURT CASES

| S.No. | File No. | Case / Suit Name of Court | Name of the court | Title of case | Name of Panel | Status of case | Date of Previous hearing | Date of hearing | Date of entrusted of Panel Lawer |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | 4(56)07/DFII/legal | 519/07 | Consumer Disputes Redressed Forum II, Udog Sadan, C-22, 23 Ist ‘X’ Institutional Area Delhi –6 | Lalit Kapur V/S DDA (Party – I) | Sh. Neeraj Aggrawal | Lack intra Structures and basic amenities (Electrification at Plotted Pkt., Sec. – 13 Dwarka) | Nil | 14.06.07 (Ist hearing ) | 21.5.2007 |
| 2 | F.9(56)98/TC/Legal | ID/711/98 | Labour Court Karkarduma | Sh. Salekh Chand V/s DDA | Sh. Sanjay Sharma | Appeal against transfer to MCD | 22.5.07 | 21.8.07 | 15.12.04 |
| 3. | F.2(1048)94/HC/Legal | 294/94 | Appeal stay from High Court | DDA V/s Satbir Singh | Sh. Anil Sapra | Appeal filed in High Court against judgement of ADJ. dt. On stay of transfer to MCD | Regular Hearing |  | 16.2.05 |

4.	Fire fighting equipments – Installations

Locations -	470 (198 M.S. & 272 MIG), Pkt 8, Sector 12, Dwarka

Fire equipments 		-		1 No. Installations.

| - Pumpset i/c Diesel driven pump/set. - Wet Riser - Fire Extinguisher | - Fire Alarms - P/A systems. |
| --- | --- |