Delhi Development Authority

Northern Division No. 11

List of Various activities

1. Details of Pending final bills and non- refund of Security Deposit.

Details of Pending Final Bills for the Month Ending July, 2007

| S.No. | Name of Work | Agency | Agreement No. | Estimated Cost / Tendered Cost | Stipulated date of start / completion | Actual date of completion | Date of payment of final Bill | Reasons for delay in payment of Final bill. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | C/o 560 SFS Houses Cat – II four storeyed & 920 Scooter Garrage i/c in ternal development at Shalimar Bagh, Sh: C/o 160SFS, Houses & 120 Scooter Garrage Gr.-III at Shalimar Bagh, | M/s Aadhar Stumbh | 8/EE/ND-11 /DDA /2002-03 | Rs.4,70,207,50/- -------------------- RS.4,02,02,321/- | 9.5.2002 8.5.2004 | 31.12.04 | 30.06.05 |  |
| 2. | D/o land for community centre at Block ‘B’ Shalimar Bagh SH: Laying unfiltered water supply lime for parks & planter and filling of septic tanks. | Sh. Naresh Kr. Gupta | 33/EE/ND-11/ 2002-03 | Rs. 2,52,489/- Rs. 2,56,519/- | 09.01.03 ------------ 08.04.03 |  |  |  |
| 3. | C/o 560 SFS cat –II houses and 420 scooter Garrage i/c internal development in Ph-I, Block C & D Shalimar Bagh, SH: Transportation & filling of earth. | M/s Sai Const. Co. | 37/EE/ND-11/2003-04 | Rs. 6,02,775/- ---------------- Rs, 4,27,500/- | 01.01.04 ------------ 31.01.2004 |  |  |  |
| 4. | D/o land at block C & D Shalimar Bagh, SH: P/L peripheral sewer lime | M/s Tirupati Cement Product | 26/EE/ND-11/2004-05 | Rs.2,40,20,376/- ---------------- Rs.1,71,45,394/- | 13.11.04 ------------ 12.05.05 |  |  | Decision Pending for completion by the competent authority |
| 5. | C/o 70 Nos. two room apartment i/c internal development in Block BH (Poorvi) Shalimar Bagh | Sh. M/s Sushil Kumar & Co. | 14/EE/ ND-11 /2005-06 | Rs.1,57,08,59,815/- --------------------- RS. 1,70,59,353/- | 29.01.05 ----------- 28.01.07 | 25.01.07 | 24.07.07 |  |
| 6. | M/o completed scheme under (NZ) SH: Supply of drinking water after procuring DJB Through water tanker at the site of 648 SFS. Houses in pocket ‘A’ Block ‘D’ Shalimar Bagh | M/s Kumar Water Supply | 15/EE/ND-11/ 2005-06 | Rs. 10,25,770/- ------------------ Rs. 7,58,940/- | 20.08.05 ------------- 19.02.06 |  |  |  |
| 7. | M/o various parks (296.38 acres) under (N.Z) SH: Repair of boundary wall northern ridge Ph-II | Sh. Nanak Chand | 25/EE/ ND-11 /2006-07 | Rs. 1,67,319/- ----------------- Rs. 1,30,806/- | 14.01.07 ---------- 13.02.07 |  |  |  |
| 8. | C/o 1108 SFS House Cat- II at Shalimar Bagh, SH: C/o 144 SFS House Cat.-II at Shalimar Bagh, | M/s Grover Const. Co. | 10/EE/ND-11/ 99-2000 | Rs. 3,66,20,675/- ------------------ Rs. 3,13,54,685/- | 03.01.2000 ------------- 02.11.2001 | 16.05.2002 | 15.11.2002 |  |

Delhi Development Authority

Northern Division No. 11

List of Various activities

1. b. 	Details of non- refund of Security Deposit.

Details of Pending Final Bills for the Month Ending July, 2007

| S.No. | Name of Work | Name of Agency | Tendered Amount | Security Deposit | Remarks |
| --- | --- | --- | --- | --- | --- |
| ------ | --------------------------------------------------------------------- | Nil | -------------------- | -------------- | ------------------ |

2.	Present Status of Work

List of works costing more than Rs. 2.00  lacs as on July, 2007

| S.No. | Name of Work | Agency | Estt. Cost Tendered Amt. | Stipulated date of Start/ Completion | Physical Progress | Actual Date of Completion | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | D/o Land at Block C & D Shalimar Bagh, SH:- Raising of boundary wall at Sheesh Mahal Shalimar Bagh | Sh. Yash Pal Singh | Rs. 8,91,212/- -------------------- Rs. 6,81,845/- | 23.06.07 ---------------- 22.08.07 | Nil | ---- | Work not started by the agency |
| 2. | D/o Land of community centre Block ‘A’ Shalimar Bagh, Sh:C/o Parking with C.C. pavement. | M/s Tyagi Assoicates | RS. 8,11,749/- ---------------------- RS. 6,71,263/- | 16.1.2007 -------------- 15.07.2007 | Nil | ---- | The huge qty of earth is lying in the alignment of parking. |
| 3. | D/o Distt Centre at Block C & D Shalimar Bagh, SH:- P/L unfiltered water supply distribution line from existing tube well. | Sh. Nanak Chand | Rs. 1,98,895/- -------------------- Rs. 3,26,474/- | 29.07.2007 ------------- 28.09.2007 | Nil | ----- | Work not started by the agency |
| 4. | M/o completed scheme under north zone SH: Supply of drinking water from DJB through water tankers. | Sh. Nanak Chand | Rs. 7,82,157/- --------------- Rs. 10,78,200/- | 23.04.2007 ------------ 22.10.2007 | 70% | Work in progress | -- |

3.	Projects held up due to Court Case	:	N/A

………….. Respective Court with Case 	:	N/A

…………… Date of Next Hearing 	:	N/A

4.	Rain Water Harvesting	:	N/A

5.	Water Bodies 	:  	N/A

…………….. Identified, status and under 	:	N/A

Encroachment

6.	Details of Deposit Works;

a)	In hand	:	N/A

b)	Under approval 	:	N/A

c)	Status 	:	N/A

7.	Details deviation in works ;

a)	………… Undertaken

| S.No. | Name of work/ Agency | Tendered Cost (Rs.) | Actual Work Done (Rs.) | %age of deviation |
| --- | --- | --- | --- | --- |
| 1. | C/o 70 Nos two room apartment including internal development in Block BH (Poorvi) Shalimar Bagh Agency: M/s Sushil Kumar & Co. | Rs. 170,59,353/- | Rs. 2,03,00,503/- | 19.00% |
| 2. | Fencing of vacant land under North Zone SH: Const. & Repair of boundarywall of vacant plot at Shalimar Bagh Agency : M/s V.S. Const. Co. | Rs. 4,59,940/- | Rs. 7,31,563/- | 59.06% |
| 3. | D/o Land in Block C & D Shalimar Bagh SH: Sinking & development of tube wells for Sumken lawn, Sahipur Village at Shalimar Bagh Agency: M/s Soni Tube Wells Works. | Rs. 2,70,660/- | Rs. 3,48,260/- | 28.67% |

7. (b)	…………………. Proposed (in Principal approval)	:	N/A

8.	Restricted Call of Tender 				:	N/A

9.	Rescinded Works

Details of Rescinded Works – Status as on July, 2007

| SI No. | Name of Work | Agency | Agmt. No. | Stipulated Date of Start /Completion | Provision Extension Granted upto | Date of rescission of work | Date of Award of Balance Work | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |
| ----- | Nil | -------- | ----------- | --------- | ---------- | ----------- | --------- | -------- |

10.	Arbitration & Related Court Case

(a)	Pending Arbitration Case as on July, 2007  ………………. Nil

10.	(b)	(i) Court Case

Details of Court Cases Pending at the end of July, 2007-Service Matters

| SI. No. | File No. | Name of Employee | Name of Court / Suit No. | Name of Panel Lawyer | Nature of Case | Present Position | Next date of Hearing | Remarks. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| -------- | --------- | --------- | ---NIL--- | -------- | ------- | ----------------------- | ----------- | -- |

10.	(b)	(ii)	Court Case.

Details of Court Cases Pending at the End of July, 2007-(Works)

| S.No. | Case Title / Party Name | File No. | Suit No. / Name of Court | Name of the Division | Name of P/L | Date of Instrument of P/L | Last date of Hearing | Next dateof Hearing | Status of the case |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | C/o 96/162 MIG Houses at Shalimar Bagh, Blk-C, Pkt-A V/s M/s Suresh Kumar & Co. | F.21(88)97 /HC/ Legal/DDA | 2619/96 High Court | ND-11 | Sh. D.S. Mahendru |  | 03.08.07 | 31.08.07 |  |
| 2. | C/o 624 MIG Houses at Shalimar Bagh, Blk-C, Pkt.-C. V/s M/s Nav Bharat Const. Co. | F.2(1087)93/ HC/Legal | 2530/93 AO(CS)90/98 High Court | ND-11 | Sh. Rakesh Manjal |  |  | For regular hearing |  |
| 3. | C/o 160 SFS Houses Shalimar Bagh Blk-B, Pkt-C V/s M/s Sunder Lal Khatri & Sons | F.21(6) HC/Legal/ DDA | 240 4A/98 High Court | ND-11 | Sh. Manu Nigam |  |  | Four regular hearing |  |
| 4. | C/o CSC at Shalimar Bagh Blk-B, Pkt-F, V/s M/s Gupta Const. Co. | F.2(919)94 /HC/Legal | FAO-146/94 Tis Hazari Court | ND-11 | Sh. Parveen Nigam |  |  | 30.08.07 |  |
| 5. | C/o 288 MIG Houses Blk-C, Pkt.A at Shalimar Bagh V/s M/s V.K. Mittal | F.21(161) 2000/HC/ Legal | OMP-48/2000 High Court | ND-11 | Sh. C. Mohan Rao |  |  | 07.09.07 |  |
| 6. | C/o 560 SFS Houses Gr-II at Shalimar Bagh Blk- C & D, SH: C/o 160 SFS Houses in Gr-III (Pdg. & Installation of cast in situ under reamed pile foundation, V/s M/s Adhar Stumbh | F.11(14)05/ ND-11 / TC/Legal | 53/2005 Tis Hazari Court | ND-11 | Sh. S.D. Sharma |  |  | 07.09.07 |  |
| 7. | C/o CSC at Shalimar Bagh Blk.-B, Pkt. C v/s M/s J.S. Builders | F.11(60)05/ Arbn./Legal | 263/2005 Tis Hazari Court | ND-11 | Ms. Rajni Chauhan |  |  |  |  |
| 8. | C/o 168 LIG Houses at Shalimar bah Blk-B, Pkt-I V/s M/s Raj Singh Khatri |  | OMP-30/2005 High Court | ND-11 | Sh. Bhupesh Narula |  |  | 30.08.07 |  |
| 9. | C/o 120 LIG Houses at Shalimar Bagh Blk-A, Pkt. –N, Shalimar Bagh V/s Mohan Const. Co. | F.2(1571)89 /HC/Legal | FAO(05) 115/06 High Court | ND-11 | Sh. D.S. Mahendroo |  |  | 15.09.07 |  |
| 10. | C/o LSC at Shalimar Bagh Blk-A, Pkt-L. V/s M/s Jagan Nath Ashok Kumar | F.21(48) 06/HC /Legal | EFA(05)No.1 Of 2006 High Court | ND-11 | Mrs. Ansuya Selwan |  |  | Case admitted but to be fixed |  |
| 11. | C/o 1108 SFS Houses Cat-II at Shalimar Bagh Blk-D, Pkt-A, SH: C/o 144 SFS houses Cat-II, at Shalimar Bagh Blk-D, Pkt-A, Ph-III (Pdg. & Installation of Cast in situ under reamed pile foundation). V/s M/s Adhar Stumbh | F.11(18)05/Arbn. / HC / Legal | 42/2005 964/06 (New) Tis hazari | ND-11 | Mrs. Harjeet Khur JIO (THC) Jr. L.O. (THC) |  |  | 09.10.07 |  |
| 12. | Fencing of vacant land under North Zone. SH: C/o Boundary wall around surrendered land to DDA by a Judhiya Textile Mills at Azadpur, Delhi. V/s M/s Jai Bhagwan | F.11(89)06/ Arbn./T.C. | 1637/06 Tis Hazari | ND-11 | Mrs. Harjeet Kaur J.L.O. |  |  | 16.04.2008 |  |

11.	Detail of Q.C. Lab Tests, Procedure 	;	N/A

12.	Fire Fighting Equipments 	:	N/A

(Installed with locations)

13.	List of Soil Testing laboratories 	:	N/A

14.	List of Approved Structural Constant 	:	N/A

15.	Technical Circular 	:	Available

16.	Q.C. Circular 	:	Available

17.	List of Contractors A,B, C, D Categories 	:	N/A

18.	R/S/EIS/EOT Cases and completion certificate. 	:

18. (a)	Details of EIS Pending as on July, 2007

| S.No. | Name of Work | Name of Agency | Amount (in Lacs) | W.E.F. |
| --- | --- | --- | --- | --- |
| ------ | ------------------------------- Nil ------------------------------------------------------- | ------------------------ | ---------------------- | --------------------- |

18. (b)	Details of RIS/DIS Pending as on July, 2007

| S.No. | Name of Work | Name of Agency | W.E.F. |
| --- | --- | --- | --- |
| ------ | ------------------------------- Nil ------------------------------------------------------- | ------------------------ | --------------------- |

18. (c)	Details of EOT as on July, 2007

| S.No. | Name of Work | Name of Agency | W.E.F. |
| --- | --- | --- | --- |
| ------ | ------------------------------- Nil ------------------------------------------------------- | ------------------------ | --------------------- |

18.	(d) Completion Certificate 	:	N/A

19.	List of approved rates of SE (P)	:	Available

20	Areas where services are handed over to 	:

MCD, DJB and Deficiency Charges.

Present Status of services as on July, 2007

| S.No. | Name of Area / Colony | Services to be handed over | Remarks |
| --- | --- | --- | --- |
|  |  | MCD | Deficiency Charges | DJB | Deficiency Charges |  |
| 1. | C/o 560 SFS Houses including internal development at Shalimar Bagh Block ‘D’ Pocket ‘A’ | (i) Open surface drain (ii) Road & path | Nil Nil | (i) Water Supply (ii) Sewerage | Nil Nil | Completion plans of servicing are being submitted to MCD / DJB for further necessary action. |

21. a)	Details of Hoses as on July,  2007

| SI. No. | Name of scheme | Year of Comp. | Divn. | House Constructed | Total Allotted / Handed Over | Total Vacant | Specified Number of Vacant House |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | SFS | MIG | LIG | Janta | Total | SFS | MIG | LIG | Janta | Total | SFS | MIG | LIG | Janta | Total |  |
| 1. | 608, MIG in bock ‘B’ Pkt U & V Shalimar Bagh | 1988 | ND-11 |  | 608 |  |  | 608 |  | 606 |  |  | 606 |  | 2 |  |  | 2 | 47-C 43-D Staff Qtrs. |
| 2. | 240, LIG, Block ‘B’ Pkt-‘D’ Shalimar Bagh | 1988 | ND-11 |  |  | 240 |  | 240 |  |  | 239 |  | 239 |  |  | 1 |  | 1 | 24A (F.F.) |
| 3. | 288 MIG Blk ‘C’ Pkt-‘A’ Shalimar Bagh | 1988 | ND-11 |  | 288 |  |  | 288 |  | 287 |  |  | 287 |  | 1 |  |  | 1 | 63C(S.F.) |
| 4. | 342 LIG Blk-‘B’ Pkt-‘B’ Shalimar Bagh | 1988 | ND-11 |  |  | 342 |  | 342 |  |  | 341 |  | 341 |  |  | 1 |  | 1 | 106D-(T.F.) |
| 5. | 160 SFS Houses Cat-II Blk- C & D Shalimar Bagh | 1988 | ND-11 | 160 |  |  |  | 160 | 153 |  |  |  | 153 | 7 |  |  |  | 7 | 46952(G.F.) 542(F.F.) 415, 439, 443(SF), 536(T.F.) |
| 6. | 200 SFS Houses Cat-II Block D/A Shalimar Bagh | 2005 | ND-11 | 200 |  |  |  | 200 | 194 |  |  |  | 194 | 6 |  |  |  | 6 | 325,(G.F.) 290, 246(F.F.) 251, 295(S.F.), 540(T.F.) |
| 7. | 144 SFS Houses Cat-II Blk-D/A, Ph-III, Shalimar Bagh | 2002 | ND-11 | 144 |  |  |  | 144 | 131 |  |  |  | 131 | 13 |  |  |  | 13 | 625(G.F.) 602, 622,630,638(F.F) 451, 471, 495, 591, 595, 615(SF) and 608, 648(T.F.) |
| 8. | 200 SFS House Cat-II, Blk. ‘D’ Pkt-‘A’ Shalimar Bagh | 2002 | ND-11 | 200 |  |  |  | 200 | 193 |  |  |  | 193 | 7 |  |  |  | 7 | 49, 121, 165, 221(G.F.), 26, 154(F.F) & 71(S.F.) |

21. b)	Details of Vacant Commercial properties as on July, 2007

| SI. No. | Name of Scheme | LSC/ CSC | Divn. | Blk/ Pkt. | Year/ Comp | Constructed | Vacant | Specific No. of Vacant Shops |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Shops | Stall | VPF | Office | Kiosk | Shops | Stall | VPF | Office | Kiosk |  |
| 1. | C.S.C. at Shalimar Bagh | CSC | ND-11 | Bs | 1989 | 32 | 9 | -- | 3 | 1 | 1 | 1 | -- | -- | -- | Shop No. 24, Stall No. 25 |
| 2. | -do- | CSC | ND-11 | BH | 1990 | 33 | -- | -- | -- | -- | 6 | -- | -- | -- | -- | Shop No. 1, 8,17,22,28,29 |
| 3. | -do- | CSC | ND-11 | BT | 1992 | 19 | -- | -- | 3 | -- | 3 | -- | -- | 1 | -- | Shop No. 18,19,20 office 21No. Co-oprative Store-17 No. |
| 4. | -do- | CSC | ND-11 | AC | 1994 | 10 | 6 | -- | -- | -- | -- | -- | -- | -- | -- | Nil |
| 5. | -do- | CSC | ND-11 | BC | 1997 | 20 | -- | 17 | 4 | -- | 10 | 17 | 17 | 1 | -- | Shop No. 1.6.8.11,14,15,17,18,19 VPF 1 to 17 office 3No. |
| 6. | -do- | CSC | ND-11 | CC | 1997 | 31 | -- | 15 | 9 | -- | 3 | -- | 2 | -- | -- | Shop No. 26, 29 & 31 VPF 5 & 13 |
| 7. | -do- | CSC | ND-11 | U, V | 1989 | 27 | -- | -- | 5 | -- | 3 | -- | -- | -- | -- | Shop No. 15, 27&28 |
| 8. | LSC at Shalimar Bagh | LSC | ND-11 | AD | 1991 | 57 | -- | 7 | 9 | -- | 1 | -- | 1 | -- | --- | Shop No.11 VPF No. 3 |
| 9. | CSC at Shalimar Bagh | CSC | ND-11 | BQ | 1990 | 72 | -- | -- | 24 | 8 | 1 | -- | -- | 1 | --- | Shop No. E-5, Post Office 1 No. Dispensary 1No. |
| 10. | -do- | CSC | ND-11 | AG |  |  |  |  |  |  | 2 | -- | 1 | -- | -- | Shop No. 7 & 11, VPF. No 16 |
| 11. | LSC at Shalimar Bagh | LSC | ND-11 | BN | 2000 |  |  |  |  |  | -- | -- | -- | -- | --- | All Shops allotted plot No. 3 lying vacant. |

21. c)	 Details of Vacant Commercial plot as on July, 2007

| S.No. | Circle/ Division | Name of Scheme/ Location of Plot | Specific No. of Plot | Plot Detals | Whether Demarcated or not | Position Service if not available | Fenced/ Not Fenced | Remark |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | No. | Land Used | Area in Sq.m. |  |  |  |  |
| 1. | CC-12 ND-11 | Nursery School No. 1 in Blk-AA Shalimar Bagh | 1 | 1 |  | 511.50 | Demarcated | Available | Fenced |  |
| 2. | CC-12 ND-11 | Nursery School No. 2 in Blk-AD Shalimar Bagh | 1 | 1 |  | 0.08Hectare | Demarcated | Available | Fenced |  |
| 3. | CC-12 ND-11 | Primary School No. 3 in Blk-AD Shalimar Bagh | 1 | 1 |  | 5758.00 | Demarcated | Available | Fenced |  |
| 4. | CC-12 ND-11 | Nursery School No. 4 in Blk-AD Shalimar Bagh | 1 | 1 |  | 0.19 hectare | Demarcated | Available | Fenced |  |
| 5. | CC-12 ND-11 | Nursery School No. 5 in Blk-AE Shalimar Bagh | 1 | 1 |  | 666.00 | Demarcated | Available | Fenced |  |
| 6. | CC-12 ND-11 | Nursery School No. 6 in Blk-AD Shalimar Bagh | 1 | 1 |  | 813.00 | Demarcated | Available | Fenced |  |
| 7. | CC-12 ND-11 | Nursery School No. 7 in Blk-AD Shalimar Bagh | 1 | 1 |  |  |  |  |  | Fully encroached by Gurdwara |
| 8. | CC-12 ND-11 | Nursery School No. 8 in Blk-AG Shalimar Bagh | 1 | 1 |  | 677.00 | Demarcated | Available | Fenced |  |
| 9. | CC-12 ND-11 | Nursery School No. 9 in Blk-AG Shalimar Bagh | 1 | 1 |  | 838.00 | Demarcated | Available | Fenced |  |
| 10. | CC-12 ND-11 | Nursery School No. 13 in Blk-AD Shalimar Bagh | 1 | 1 |  | 288.00 | Demarcated | Available | Fenced |  |
| 11. | CC-12 ND-11 | Nursery School No. 14 in Blk-AN Shalimar Bagh | 1 | 1 |  | 100.00 | Demarcated | Available |  | Encroached by way of Temple |
| 12. | CC-12 ND-11 | Nursery School No. 15 in Blk-AN Shalimar Bagh | 1 | 1 |  | 792.00 | Demarcated | Available | Fenced |  |
| 13. | CC-12 ND-11 | Health Care at Blk-AL Shalimar Bagh | 1 | 1 |  | 990.00 | Demarcated | Available | Fenced |  |
| 14. | CC-12 ND-11 | Nursery School No. 1 in Blk-BT Shalimar Bagh | 1 | 1 |  | 703.00 | Demarcated | Available | Fenced |  |
| 15. | CC-12 ND-11 | Nursery School No. 2 in Blk-BT Shalimar Bagh | 1 | 1 |  | 694.00 | Demarcated | Available | Fenced |  |
| 16. | CC-12 ND-11 | Nursery School No. 4 in Blk-BN Shalimar Bagh | 1 | 1 |  | 2154.00 |  | Available |  | Being used as park. |
| 17. | CC-12 ND-11 | Nursery School No. 5 in Blk-BN Shalimar Bagh | 1 | 1 |  |  | Demarcated | Available | Fenced |  |
| 18. | CC-12 ND-11 | Nursery School No. 8 in Blk-BN Shalimar Bagh | 1 | 1 |  | 651.00 | Demarcated | Available | Fenced |  |
| 19 | CC-12 ND-11 | Nursery School No. 10 in Blk-BQ Shalimar Bagh | 1 | 1 |  | 657.00 | Demarcated | Available | Fenced |  |
| 20 | CC-12 ND-11 | Nursery School No. 12 in Blk-BP Shalimar Bagh | 1 | 1 |  | 564.00 | Demarcated | Available | Fenced |  |
| 21 | CC-12 ND-11 | Nursery School No. 12 in Blk-BK Shalimar Bagh | 1 | 1 |  | 1057.00 | Demarcated | Available | Fenced |  |
| 22 | CC-12 ND-11 | Nursery School No. 14 in Blk-BK Shalimar Bagh | 1 | 1 |  |  |  |  |  | Encroached by way of temple |
| 23 | CC-12 ND-11 | Nursery School No. 17 in Blk-BE Shalimar Bagh | 1 | 1 |  | 841.00 | Demarcated | Available | Fenced |  |
| 24 | CC-12 ND-11 | Nursery School No. 18 in Blk-BH Shalimar Bagh | 1 | 1 |  | 641.00 | Demarcated | Available | Fenced |  |
| 25. | CC-12 ND-11 | Nursery School No. 20 in Blk-BH Shalimar Bagh | 1 | 1 |  | 692.00 | Demarcated | Available | Fenced |  |
| 26. | CC-12 ND-11 | Nursery School No. 21 in Blk-BH Shalimar Bagh | 1 | 1 |  | 1319.00 | Demarcated | Available | Fenced |  |
| 27. | CC-12 ND-11 | Nursery School No. 22 in Blk-BH Shalimar Bagh | 1 | 1 |  | 808.00 | Demarcated | Available | Fenced |  |
| 28. | CC-12 ND-11 | Nursery School No. 25 in Blk-BH Shalimar Bagh | 1 | 1 |  |  | Demarcated | Available |  | Encroached by way of Arya Samaj Mandir |
| 29. | CC-12 ND-11 | Nursery School No. 30 in Blk-BH Shalimar Bagh | 1 | 1 |  | 856.00 | Demarcated | Available | Fenced |  |
| 30. | CC-12 ND-11 | HSS Between LSC Plot and Shalimar Village | 1 | 1 |  | Not available |  |  |  |  |
| 31. | CC-12 ND-11 | Primary School Between LSC and Shalimar Village | 1 | 1 |  | Not available |  |  |  |  |
| 32. | CC-12 ND-11 | Primary School in Shalimar Village. | 1 | 1 |  | Not available |  |  |  |  |

22.		:	N/A

23.	Details of land handed over  to engineering 	:	Nil

Position of Regular Staff

24.	Position of Regulars Staff 	:

| S.No. | Designation | Sanction Strength | Men in Position | Vacant Position |
| --- | --- | --- | --- | --- |
| 1. | Executive Engineer | 1 | 1 | -- |
| 2. | Asstt. Engineer | 5 | 4 | 1 |
| 3. | Junior Engineer | 13 | 11 | 2 |
| 4. | Asstt. Account Officer | 1 | 1 | -- |
| 5. | Head Clerk | 1 | -- | 1 |
| 6. | Steno | 1 | 1 | -- |
| 7. | U.D.C. | 4 | 4 | -- |
| 8. | D/ Man Gr. –II | 1 | -- | 1 |
| 9. | L.D.C. | 6 | 2 | 4 |
| 10. | Driver | 1 | 1 | -- |
| 11. | Peon | 4 | 3 | 1 |
| 12. | Security Guard | -- | 4(R)+12W.C)R. | -- |
| 13. | Daftary | 1 | -- | 1 |
| 14. | Beldar |  | 1(R) + 6(W/C)R |  |
| 15. | Mason |  | -- |  |
| 16. | Env. Asstt. |  | 3(W/C)R |  |
| 17. | Sanitary Mate |  | -- |  |
| 18. | Fitter |  | 1(R) + 1(W/C) R |  |
| 19. | Khalasi |  | 2(W/C)R |  |
| 20. | Helper |  | 1(W/C)R |  |
| 21. | Asstt. Typist |  | 1(W/C)R |  |
| 22. | Mate |  | 10(W/C)R |  |
| 23. | S/Man |  | 1(W/C)R |  |