DELHI DEVELOPMENT AUTHORITY

QUALITY ASSURANCE CELL – VI

TENTATIVE PROGRAMME OF INSPECTION                                                               DOC. NO. :  QA / F / 0102

No. F 69 ( 1 ) / Misc. / Inspn. / EE ( QAC ) – VI / DDA …………..                                                          Dated :  ……………

INSPECTION PROGRAMME FOR THE MONTH OF  NOVEMBER 2007

| Sr. No. | D. O. I. | Divn. / Circle | Name of Work / Agency | Estd. Cost / Tend. Amt. | %age of Progress | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | 27.11.07 | ED-9/CC-10 | C/o MIG/LIG , DU’s near G.T.Road at Dilshad Garden SH : C/o 96 MIG / 96 LIG DU’s at Dilshad Garden ,Gr.IV i/c internal. development ( to be constructed 100 MIG/ 100 LIG- Balance work) R/F M/s Naresh Kumar Gupta & Co. ( P ) Ltd. Agency M/s Lakshmi Const. | 6,41,91,224/- 5,32,92,949 | 48% in Sept.07 | DOS = 6.10.06 DOC = 5.1.08 Earlier Insp. = 2nd on 28.4.07 ( 18% progress ) |
| 2. | 28.11.07 | E.D.-3/CC-10 | D/o 60 Hect. of land at Bakkarwala ( Lok Nayak Puram ) SH : C/o 30m R/W road from Nangoli - Najafgarh road to Bakkarwala. M/s Walia Const. Co. | 5,10,76,466/- 372 Lakhs | 13 % in Sept.07 | DOS = 24.6.07 DOC =23.6.08 Earlier Insp. = Nil |
| 3. | 30.11.07 | E.D.-12 /CC-3 | D/o Land for IFC at Gazipur. SH: C/o 2nd phase treatement of 30m & 45m R/W & Ist Phase Treatment, Parking & Approach Road to culvert at IFC Gazipur. Agency :- Sh.. Joginder Kr. Gandhi. | 4,15,92,810/- 5,29,19,877/- | 7% in Sept.07 | DOS= 3.5.07 DOC=2.5.08 Earlier Insp. = Nil. |

Copy :-

- C.E., QAC,DDA for kind information.

- S.E.,QAC,DDA   for kind information.

- E.E.(QAC)-VI,DDA for kind information.

- A.E.(QAC)-VI,DDA for kind information.

- A.E. ( H.Q. ),QAC ,DDA for kind information.

- P.S. to S.E.(QAC) for forwarding the programme for website.

( R.K.GUPTA)

Ex.Engineer

QAC-VI,DDA