LIST OF ACTIVITIES

NORTH ZONE, DDA

Circle:-	Civil circle-7						DIVISION:- Western  Division -5

As on 31.12.2007

| 1. | Details of Pending Final Bills & non-ref, of Security Deposits. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Name of Work | Agencies | Agmt. No. | Esst. Cost. Tender Cost | Stipulated | Remarks |
|  |  |  |  |  | D.O.S D.O.C |  |
| i. | Protection of D.D.A. Land SH: C/o Randum rubble masonry on vacant land under jurisdiction of CC-5 | M/s Tara Chand Sumit Construction Co. | 13/EE/WD-5/DDA/05-06 | 893801 591219 | 28.11.05 27.05.06 | Work has been completed payment of 7th R/A held up as per instruction of higher authorities. |
| ii. | M/o of Vikas Minar SH: P/F floor tiles on 5th 6th & 7th floor at Vikas Minar | M/s S.K. Mittal & Co. | 34/EE/WD-5/DDA/05-06 | 487418 290090 | 26.03.05 25.04.05 | Concerned MB’s with vigilance brand in other case |
| iii. | All due securities are being refunded on the request of respective Agencies as & when received |  |  |  |  |  |

| 2 | Present statues of works as on 31.12.07 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| S. No. | Name of Work | Estt. Cost Tendered Cost | D.O.S D.O.C | Progress up to previous month | Progress during this month | Up to date progress | Remarks |
| i. | D/O Distt. Centre at Rajindra Place (Bal. Dev. & Constn. Work). SH: C/o parking lot ‘D’. Agency: M/s Tara Chand Sumit Const. Co. | 8342464.00 8714478.00 | 09.02.06 08.08.06 | 92% | 3% | 95% |  |
| ii. | M/o Vikas Minar SH : Replacement of basement flooring for parking at Vikas Minar. Agency : Sh. M/s Tara Chand Sumit Const. Co. | 1236568.00 1841908.00 | 14.10.06 13.04.07 | 18% | — | 18% | Show cause notice has been issued under clause 3 of the agreement. |
| iii. | M/o Vikas Minar SH: Cleaning & mopping of toilets, pantries, spittoons, dustbin, stair case, corridors, etc. of Vikas Minar Agency : M/s. Rajesh Kumar | 298862.00 474010.00 | 30.11.07 29.05.08 | 1% | 15% | 16% | Work recently awarded |
| iv. | M/o Vikas Minar SH:- Alternation of existing partition frame of CE(NZ), Director (Narela) and Director (UD). Agency : M/s Rajiv Kaushik | 467455.00 405282.00 | 23.11.07 22.12.07 | 20% | 80% | 100% |  |
| v. | M/o Vikas Minar SH: Dry cleaning of Vertical blinds visitors chairs, sofa sets. At Vikas Minar. Agency : Ms. S.V. Enterprises | 84391.00 134816.00 | 07.01.08 06.07.08 | - | - | - | Work recently awarded |
| vi. | M/o Vikas Minar SH: Providing and fixing Hortizontal and Vertical Venation blind Vikas at Minar from 1st floor to 21st floor. Agency : Ms. S.V. Enterprises | 258925.00 163992.00 | 07.01.08 06.04.08 | - | - | - | Work recently awarded |
| vii. | M/o Vikas Minar Repair of Kota/marble stone flooring and tiles work at Vikas Minar Agency : M/s. Naveen Kumar | 264192.00 183203.00 | 07.01.08 06.03.08 | - | - | - | Work recently awarded. |
| viii. | M/o Vikas Minar SH: Alternation of existing partition frame for inquiry officers and SE/CC-7/DDA at 2nd & 7th floor. Agency: M/s. Naveen Kumar | 467763.00 592324.00 | 07.01.08 21.02.08 | - | - | - | Work recently awarded. |
| ix. | M/o Vikas Minar SH: Repair of door closer and springs. Agency: M/s S.V. Enterprises | 79972.00 100334.00 | 20.10.07 19.04.08 | – | 10% | 10% |  |
| x. | M/o Vikas Minar SH: Minor repairs, oil bound distemper, painting work etc. on low and high partitions of office spaces at Vikas Minar from Basement to 21st Floor. Agency : Amit Builders. | 630086.00 414438.00 | 20.10.07 29.01.08 | 10% | 40% | 50% | Work recently awarded. |
| xi. | M/o Vikas Minar SH: Repairing and cleaning of existing, venation blinds (Horizontal & Vertical) and refixing at various floor at Vikas Minar. Agency : M/s Globe Constructions Co. | 155296.00 99397.00 | 10.12.07 09.03.08 | – | – | – | Work recently awarded |
| xii | M/o Vikas Kuteer SH : White washing, painting & miscellaneous work at Vikas Kuteer. Agency : M/s Naveen Kumar | 143144.00 104961.00 | 07.01.08 06.04.08 | - | - | - | Work recently awarded |
| xiii. | Special Repair of Vikas Minar. SH : Rehabilitation of RCC column and beams and other RCC members of Vikas Minar. Agency : M/s Cembond Constructions. | 5849019.00 6997284.00 | 15.07.07 14.04.08 | 9% | 6% | 15% |  |
| xiv. | M/o Completed scheme of N/A. II under SWZ. SH : P/F G.I. barbed wire fencing along proposed passage for local people of Dasghara Village and Const. of wicket gates. Agency : M/s P.K. Engineer | 136053.00 141210.00 | 10.07.07 09.08.07 | 60% | 40% | 100% | Show cause notice under clause 3 of the agreement has been issued |
| xv. | M/o completed scheme at Nazul A/c-II under North Zone SH: Modification of Boundary wall raising and repairing etc. along main road at Satya Park, Naraina Industrial Area Phase-II. Agency : I.D. Rehani & Co. | 565297.00 657957.00 | 08.12.07 07.03.08 | – | 15% | 15% | Work recently awarded |
| xvi. | M/o completed scheme under Nazul A/c-Ii of North Zone. SH: Construction/Repair of boundary wall, repairing of Grills etc. of green belt Todapur village. Agency: M/s. S.S. Construction Co. | 377660.00 567526.00 | 24.12.07 23.02.08 | - | - | - | Work recently awarded. |
| xvii. | Fencing of vacant land under North Zone. SH: Construction of boundary wall in and around at different locations at Anand Parabat Industrial Area. Agency : M/s. Bharat Building Construction Co. | 624600.00 824396.00 | 24.12.07 23.06.08 | - | - | - | Work recently awarded. |
| xviii. | M/o completed scheme (shops) under North Zone. SH : Cleaning and sweeping of Pizza parking open spaces at Distt. Centre Rajindra Place. Agency : M/s Madhukar Construction. | 99,638.00 1,48,180.00 | 25.10.07 14.06.08 | 15% | 15% | 30% |  |
| xix | M/o completed scheme under Nazul A/c-I of South West Zone. SH: Annual repairing and maintenance of officers flats at Bhagwan Dass Raod. Agency : M/s Aggrawal Build. &Cont. | 952343.00 1094111.00 | 23.11.07 22.02.08 | 7% | 53% | 60% | Work recently awarded. |
| xx | M/o completed scheme under Nazul A/c-I of South West Zone (M/o 7 B.D. Road Flats). SH: Renovation of flat No. 7/1 by P/L floor tiles etc. at B.D. Road Agency: Rajiv Kaushik | 503949.00 565595.00 | 08.01.08 28.01.08 | - | - | - | Work recently awarded. |
| xxi | A.R. & M/O Staff quarters at Rajinder Nagar. SH: Supply of material at Staff Quarters Rajinder Nagar. Agency : S.V. Enterprises | 150962.00 136930.00 | 25.11.07 24.12.07 | 50% | 50% | 100% |  |
| xxii | A.R. & M/O Staff quarters at Rajinder Nagar. SH: White washing, painting, distempering at DDA staff Quarters, Rajinder Nagar. Agency : AAR Constructions | 581379.00 397621.00 | 08.12.07 07.02.08 | – | 10% | 10% | Work recently awarded |
| xxiii | A.R. & M/O Staff quarters at Rajinder Nagar. SH: P/L Sewer line at Rajinder Nagar Staff Quarters. Agency: M/s Yuvraj Singh | 405307.00 587239.00 | 24.12.07 07.02.08 | - | - | - | Work recently awarded |
| 3. | Projects held up due to Court Case |  |  |  |  |  |  |
|  | -- Respective Court with Case No. -- Date of Next Hearing | Nil |  |  |  |  |  |
| 4. | Rain Water Harvesting |  |  |  |  |  |  |
|  | -- Already Provided -- Propose | Nil |  |  |  |  |  |
| 5. | Water bodies |  |  |  |  |  |  |
|  | -- identified, status & under encroachment. | Nil |  |  |  |  |  |
| 6. | Details of Deposit Works: |  |  |  |  |  |  |
|  | - in hand (b) Under approval - Status | Nil |  |  |  |  |  |

| 7. | Details of deviation in works: during October, 2007 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | (a) Undertaken. Nil (b) Proposed (In principal approval) |  |  |  |  |  |  |
| S No. | Name of work | Agency | Agg. No. | Tendered | Total Work Done | Deviation | Remarks |

| 8 | Restricted Call of tenders |
| --- | --- |

LIST OF WORK ORDER FOR THE YEAR 2007-08

| W.O. No. |  | Name of Work |  | Estt. Cost | Work order amount |  |  | Sanctioned by | Time allowed |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1/ EE/WD-5 DDA/ 0 7 -08 |  | M/O Staff Qtrs. At Rajinder Nager SH: Repair and renovation work in Bungalows and Barat Ghar at Rajinder Nagar, |  | Rs, 4,73,800/- | Rs. 5,95,583/- |  |  | CE (SWZ) DDA | 38 days |
| 2/EE/WD-5- DDA/07/08 |  | M/o Vikas Minar. SH: Providing temporary protection from falling loose concrete. |  | Rs. 1,60,459/- | Rs. 1,53,780/- |  |  | S.E./CC-5/DDA | 25 days |
| 3/ EE/ WD-5/ DDA/07-08 |  | M/o Vikas Minar. SH: Alteration of existing partition frame resistant partition of Director (IS) Alterations. |  | Rs. 5,45,683/- | Rs. 5,78,328/- |  |  | CE (SWZ) DDA | 15 days |
| 4/ EE/ WD-5/ DDA/07-08 |  | M/o Completed Scheme under N/Z A/c-1 of SWZ SH: Replacement of M.S Windows, Grills, Jallis etc. by providing Aluminium Windows Grill, Jalli etc. at Flat No. 7/1 Bhagwan Das Road |  | Rs. 2,22,165/- | Rs. 2,83,798/- |  |  | SE/CC-7/DDA | 20 days |
| 5/ EE/ WD-5/ DDA/07-08 |  | ARMO Staff Quarters at Rajindra Nagar SH: Total Station survey of Staff Quarters at Rajindra Nagar |  | Rs. 22,000/- | Rs. 29,214/- |  |  | EE/WD-5 | 7 days |
| 6/ EE/ WD-5/ DDA/07-08 |  | M/o Vikas Minar SH: Renovation of chamber at commissioner (system & planning) at 9th floor Vikas Minar |  | Rs. 83,556/- | Rs. 98,789/- |  |  | EE/WD-5 | 1 Month |
| 7/EE/WD-5/ DDA/07-08 |  | Special repair of Vikas Minar SH: Consultancy for rehabilitation of RCC column and beams and other RCC members of Vikas Minar. |  | – | Rs. 157136/- |  |  | CE/NZ/DDA | 9 months |
| 8/EE/WD-5/ DDA/07-08 |  | M/o of Vikas Minar SH: Consultancy for designing of reception area at Ground floor, Vikas Minar |  | – | Rs. 25000/- |  |  | CE/NZ/DDA |  |
| 9. |  | Rescinded Works. |  |  |  |  |  |  |  |
|  |  |  |  | Nil |  |  |  |  |  |
| 10. |  | Arbitration & related Court Cases |  |  |  |  |  |  |  |
| a) |  | Arbitration |  | Nil |  |  |  |  |  |
| b) |  | Court Cases |  | List of Court Cases are as under |  |  |  |  |  |
| S. No. | Description |  | Agency |  |  | Name of Court | Name of panel lawyer |  | Next dt. Of Hearing |
| 1 | 2 |  | 3 |  |  | 4 | 5 |  | 6 |
| i. | D/o J.J Colony kalkaji. Sh: P/L Dense carpet concrete work in J.J. Colony |  | Sh. Satya Prakash & Brothers |  |  | High Court. | Sh. D.S. Mhendroo |  | 07.03.2008 |
| ii. | C/o 504 SFS Cat. II houses at Sukhdev Vihar. Sh. C/o 192 Du’s i/c int. Development. |  | M/s. Bhartya Const Co. |  |  | High Court. 208/97 | Sh. B.B. Sharma |  | Decided |
| iii. | C/o 232/108 SFS Cat. II houses at Paschim Vihar. |  | M/s/ Hindustan Prefab Ltd. |  |  | High Court. 320/96 | Mrs. Sangeeta Chandra |  | Regular hearing |
| iv. | C/o 232/124 SFS houses at Paschim Vihar. |  | M/s/ Hindustan Prefab Ltd. |  |  | High Court. CS (OS) 1965/96 | C. Mohan Rao |  | Recovery suit filed 18.12.07 |
| v. | C/o 504 SFS Houses at SukhDev Vihar. Sh: Pile foundation. |  | M/s Ground Engineer Co. (P) Ltd. |  |  | High Court 67-A/96 Ex. 47/2002 | Mrs. A. Salwan |  | Sine dine |
| vi. | C/o M.S.O. Bldg for DDA office SH: Bldg. & basement portion |  | M/s. Layall & Co. |  |  | High Court. FAO (05) 243/92 | Mrs. A. Salwan |  | Decided |
| vii. | C/O 160 SFS at Sukhev Vihar. |  | Sh. K.K. Rathi |  |  | High Court. 179/92 | Mrs. A. Salwan |  | Decided |
| viii. | M/o Completed scheme under SWZ. Sh. Repairing of road of Janakpuri Paschim Vihar. |  | Sh. S.P. Gupta |  |  | High Court 558/2002 | K. R. Chawla |  | 08.01.08 |
| ix. | Ray Provision of passes to Village Dsagarha through ridg. |  | Residents of Village Dasgrah by DDA |  |  | High Court. | Sh. Rajeev Bansal |  | 14.08.2007 |
| x. | C/o 864 LIG Houses at Hastsal Pkt-‘B’. SH: C/o 252 LIG Houses including internal water supply installation and internal development. |  | M/s Arkey Engineers Co. |  |  | Tis Hizari Court. | Sh. Rohit Jain |  | 07.01.08 |
| xi. | Destitutinal area D- Block Janakpuri |  | Vice Chairman V/s Dir. Revenue & other |  |  | Tis Hizari Court. | Sh. H.K.L. Seghal. |  | 13.02.2008 |
| xii. | C/o 504 SFS Cat. II houses at Sukhdev Vihar. Sh. C/o 192 Du’s i/c int. Development. |  | M/s Bhartiya Const. Co. |  |  | High Court. FAO (OS) 273/97 | Sh. B.B. Shrama & Jagmohan Sabharawal. |  | decided |
| xiii | C/o 504 SFS Cat. II Houses at Sukhdev Vhiar Sh: C/o 152 MIG/ Cat. II SFS |  | Sh. S.S. Jetly |  |  | High Court 275/01 | Ms. A Salwan |  | decided |
| xiv. | C/o Shopping Center at Nehru Place on Plot No. 42 |  | C. Lal Gupta. |  |  | High Court. | Mrs. A. Salwan |  | 22.01.2008 |
| xv. | C/o 56/136 houses at Toda Pur i/c internal development |  | M/s Happy Himalya |  |  | T.C. 305/04 | Smt. Promila Kapoor |  | 23.02.08 |
| xii. | C/o 232/108 SFS Cat-II at Paschim Vihar |  | M/s Hindustan Prefab. Ltd. |  |  | FAO(OS)108/07 | Ms. Sangeeta Chandra |  | 24.01.08 |
| 11. | Details of Q.C Lab. Tests, Procedures |  | N/a |  |  |  |  |  |  |

| 12 |  | RIS/ EIS/ EOT Cases & Completion Certificate during October, 2007 |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| S. No. |  | Name of Work |  | Agency |  | Agreement | EIS | RIS | SIS | Amount | EIT |  |
| 13. |  | List of approved rates of SE(P) |  |  | Are issued by Chairman Market rate approval committee/Concerned SE (P) |  |  |  |  |  |  |  |
| 14 |  | Areas where serviced are handed over to MCD/ DJB & Deficiency charges. |  |  |  |  |  |  |  |  |  |  |
| 15. |  | List of vacant flats/ Shops/ Keosk/ Commercial/ Residential Plots on the date of completion development. |  |  | - Distt. Center Rajinder Place 2 nos shops bearing shope no. 103 & 145 - Hog market Rajindera Place 3 nos shops bearing shops no 193, 194 & 196 - Janta Flats Toda Pur 5 nos flats bearing flat nos 103, 113, 83, 86, & 94 |  |  |  |  |  |  |  |
| 16. | Jurisdiction of C.E/Map. EE wise |  | Asstt. Engineer- I - M/o Vikas Minar office building floor 11 to 21 - M/o Vikas Kuteer Barrack No. - 6 |  |  |  |  |  |  |  |  |  |

|  | Asstt. Engineer- II (i) M/o Vikas Minar office building floor basement to 10 floor |
| --- | --- |

|  | Asstt. Engineer- III - M/o of staff quarter at Rajindera Nagar, Jaidev Park, Concrete House Karol Bagh, Dev Nagar & Bagh Rao Ji - D/o Anand Parbhat area - M/o LSC 2,4 & 20 and CSC 22 at New Rajindera Nagar - M/o MOR land pocket 7,8,9 at New Rajindera Nagar - D/o of land at 8A WEA Karol Bagh |
| --- | --- |

|  | Asstt. Engineer- IV - Distt. Center of Rajindera Place - Bhooli Bhatyari Park at Ridge - “R” Block Park at New Rajindera Naga - Rock Garden at Patel Nagar - Satya Park Naraina Industrial area Phase-II - Maha Raja Aggarsen Park Inder Puri - N.H.P. Park Naraina - Janta Flats Toda Pur - Golden Park |
| --- | --- |
|  | Asstt. Engineer- V (i) M/o officers Staff Flats at Bhagwandas Road |

| 17. | Details of land handed over to Engineering Wing for development | Nil |  |  |  |
| --- | --- | --- | --- | --- | --- |
| 18. | Sanctioned Strength/In place/ vacancy position of Regular Staff |  |  |  |  |
| S. No. | Designation | Sanctioned Strength | Men in Positions | Shortfall | Excess. |
| (i) | Executive Engineer | 1 | 1 | — | — |
| (ii) | Assistant Engineer | 5 | 5 | — | –– |
| (iii) | Junior Engineer | 17 | 17 | –– | — |
| (iv) | Divisional Accountant | 1 | 1 | — | — |
| (v) | Head Clerk | 1 | 1 | — | — |
| (vi) | UDC | 5 | 5 | — | — |
| (vii) | LDC | 7 | 2 | 5 | — |
| (viii) | Assistant Cashier | 1 | 1 | — | — |
| (ix) | Steno | 1 | — | 1 | — |
| (x) | D/Man | 1 | 1 | — | — |
| (xi) | Peon | 4 | 3 | 1 | — |

EXECUTIVE ENGINEER

WD-5/DDA