DELHI DEVELOPMENT AUTHORITY

ELECTRICAL DIVISION NO. 8

LIST OF ACTIVITIES

1.	Details of Pending Final & non-refund of Security Deposits.

- Details of pending final bills for the Month ending March, 2008

| S. No. | Name of Work | Agency | Agreement No. | Stipulated date of start Completion | Actual date of completion | Date of payment of final bill | Reasons for delay in payment of final bill. |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | 2 | .3 | 4 | 5 | 6 | 7 | 8 |

.------------------------------------------------------------------------ NIL------------------------------------------------------------------------------------------------------------------

B.	Details of non-refund of Security Deposits for the Month ending March, 2008

| 0. | Name of Work | Agency | Agreement No. | Stipulated date of start Completion | Actual date of completion | Date of payment of final bill | Amount of Security Deposit deducted | Reasons for delay in refund of Security Deposit |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

.------------------------------------------------------------------------ NIL------------------------------------------------------------------------------------------------------------------

2.	Present status of work:

List of works costing more than Rs. 2.00 lacs for the month ending March, 2008

| S. No. | Name of Work | Agency | Estt. Cost Tendered amount (in lacs) | Stipulated date of start Completion | Physical progress | Actual Date | Reasons for delay in payment of final bill. |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | 2 | .3 | 4 | 5 | 6 | 7 | 8 |
| 1. | A) Construction/ Development works C/o320/258 MS Houses SFS at Motia Khan SH: IEI of 66 flats Blk.-1 Motia Khan | Goel Elect Works | 17.41 16.69 | 18.9.03 17.3.06 | 85% | Work in progress |  |
| 2. | C/o 216 MIG DU’s MS at Pitampura (near TV Tower) SH: C/o 72 MIG DUs i/c sanitary installation, water supply, sewage, drainage, roads & path and internal electrification Gr.i | Ved Prakash Mittal & Sons | 22.57 50.54 | 25.10.06 24.10.08 | 45% | Work in progress |  |
| 3. | C/o 216 MIG DU’s MS at Pitampura (near TV Tower) SH: C/o 144 MIG DUs i/c sanitary installation, water supply, sewage, drainage, roads & paths and internal electrification Gr-II & III | Winner Contst. Pvt. Ltd. | 45.18 73.01 | 14.12.06 13.12.08 | 42%. | Work in progress |  |
| 4. | S/ I of DG Set and replacement of LT Panel at Vikas Minar SH: Supplying errection, testing and commissioning of DG Set at Vikas Minar | Budhiraja Electrical | 25.09 21.52 | 22.2.07 21.5.07 | 95% | Work in progress |  |
| 5. | C/o 560 SFS houses Cat. II in Blk-D Pkt-I, Shalimar Bagh. a) IEI of 192 SFS DUs Gr.i b) IEI of 208 FS DUs Gr.ii | Goel Elect Goel Elect | 23.27 18.77 2.21 20.33 | 27.12.02 26.6.05 5.1.03 4.7.05 | 35% 49% | Work in progress Work in progress |  |
| 6. | C/o 70 LIG DUs in Blk, BH Poorvi Shalimar Bagh Sh: IEI | Cholia Elect. Work | 5.27 5.35 | 16.10.05 15.4.07 | 100% | Work in progress |  |
| 7. | M/o completed works (NZ) SH: Annual operatio of lifts & DG Set at 66 SFS MS flats Block-A-I Motia Khan | Sudhir Electricals | 5.22 5.18 | 01.07.07 30.06.2008 | 55% | Work in progress |  |
| 8. | M/o Office building at Vikas Minar SH: R/M/O lifts comprehensive maintenance | Kone Elevator India Pvt. Ltd. | 18.85 18.85 | 07.09.07 06.09.08 | 60% | Work in progress |  |

- Details of deviation in works:

Details of deviations in works for the Month ending February, 2008.

| S. No. | Name of work | Name of Agency | Agreement No. | Estimated cost Tendered Amount | Amount (in lacs) |
| --- | --- | --- | --- | --- | --- |

-------------------------------------------------------------------------- Nil -----------------------------------------------------------------------------------------------------

4.	Restricted Call of Tenders.

Details of Restricted Call  of Tenders for the Month ending March, 2008.

| S. No. | Name of work | Name of Agency | Amount (in lacs) |
| --- | --- | --- | --- |

-------------------------------------------------------------------------NIL ---------------------------------------------------------------------------------------------

5.	Rescinded Works:

Details of Rescinded Works- Status as on 31.03.08

| S. No. | Name of work | Agency | Agreement No. | Stipulated date of start Completion | Provisional extension granted upto | Date of rescission or work | Date of award of balance work | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | 2. | 3. | 4. | 5. | 6. | 7. | 8. | 9. |

------------------------------------------------------------------------------------------------------- Nil-----------------------------------------------------------------------

6	Arbitration & related Court Cases.

| S.L No. | File No | Name of Work | Name of Agency | Name of Court/ Suit No. | Name of Panel Lawyer | Nature of cases | Present position | Next | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |
| 1. | F 21 (122) 1999/ HC/Legal | C/o 448 MIG DUs at Pkt. KD Pitampura SH: IEI of 356 DUs in Gr.II | Bumbrah Elect Co V/s DDA | High Court CWO 2561/98 | Sh. D.S. Mahendru | Nil Arbrtn. Award challenged by agency in court | Argument continued | 15.5.2008 |  |
| 2. | F 12 (16) 1999/ TC/Legal | C/o 480 LIG houses at Pkt KD Pitampura SH: IEI | R.K. Angeja V/s DDA | Distt. Court 1996 A /95 | Sh. S.S. Mittal | Suit file for recovery of Rs. 97610/- levied as compensation | Argument continued | 01.08.08 |  |
| 3. | F 12 (429) 06/H C/Legal | Electrification of plot No. 4 Community Center Motia Khan | Rajesh Projects India Pvt. Ltd. V/s BSES Rajdhani Power Ltd. & others | WP (C) No. 8212/06 | Sh. Jag Mohan Sabherwal | Electrification of Community Center Motia Khan | Counter statement filed | 05.08.08 |  |
| 4. | F21(22)96/HC/Legal | D/o Land at JJR Colony Jahangirpuri SH: S/I of storm/ sewage pumps | Gita Pumps V/s DDA & MCD | OMP No. 1/96 | Sh. Bhupesh Narula | Arbitration award challenged | Argument continued | 15.07.08 |  |

7	Fire fighting Equipments (installed with locations)

| Sl. No. | Location | Electric driven pumps | Diesel driven pumps | Jocky pumps | Fire Extinguishers | Yard Hydrant | Fire Hydrant | Sprinkler |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |
| 1. | Rajendra Bhawan, Rajendera Place | 100HP-2 Nos. | 100BHP-1 No. | 20HP-I No. | 7 Nos. | 8 Nos | - | Provided in basement |
| 2. | Motia Khan (Ms housing) | 75HP- 1 No. | 100BHP-1 No. | 20HP-I No. | 5 Nos. | 12 Nos. | 20 Nos. | - |
| 3. | Jhandewallan | 75 HP-2 Nos | 75 BHP-i | 15HP-I | 2 Nos. | 7 Nos. | - | - |
| 4. | Vikas Minar | 100HP- 2 Nos. | 127 BHP-I No. | 25 HP-2 Nos. | 56 Nos. | 2 Nos. | 27 Nos. | Provided in basement & in all floors. ` |

8	EIS/EOT cases & Completion Certificate:

Details of EIS for the Month ending March, 2008

| S. No. | Name of work | Name of agency | Agreement No. | Estimated cost Tendered Amount | Stipulated Date of Start Stipulated Date of completion | Amount (in lacs) |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 |
| 1. | M/o pump sets at various colonies under north zone SH: A/R/M/O clear water pump set and D.G. set & sub p/set at 560 SFS flat category-II block C&D Shalimar bagh) | M/s Super System Engineers | 95/EE/ED-8/DDA/2006-07 | 3.31 3.25 | 26.03.07 25.03.08 | 0.07 |

Details of EOT cases for the Month ending March, 2008

| S. No. | Name of work | Agency | Agreement No. | Estt.Cost Ten. Amt. | EOT granted without levy of compensation | EOT granted with levy of compensation | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |
| 1. | M/o Office building at Vikas Minar (SH: Annual comprehensive & overhauling of CC TV system) | M/s G.S. comprehensive | 77/EE/ED-8/DDA/2006-07 | 0.65 0.63 | 10.2.08 to 7.3.08 | - | - |
| 2. | M/o Office building as Vikas Minar (SH : Annual operation & maintenance of wet riser sprinkler system) | M/s Fire Cool Engineers | 79/EE/ED-8/DDA/2006-07 | 2.87 2.88 | 16.2.08 to 26.3.08 | - | - |
| 3. | M/o Pump set at various colonies under North Zone. (SH: Running, operation & maintenance of clear water pump set at Mangolpuri Industrial Area, Block-B | M/s Saztkar Electricals | 81/EE/-ED-8/DDA 2006-07 | 1.65 0.75 | 13.2.08 to 20.3.08 | - | - |

9	Sanctioned Strength/In place/ vacancy

Position of Regular Staff

| S. No. | Designation | Sanction strength | Present strength | Shortfall |
| --- | --- | --- | --- | --- |
| 1. | Executive Engineer | 1 | 1 | Nil |
| 2. | Asst. Engineer | 5 | 5 | Nil |
| 3. | Junior Engineer | 17 | 16 | 1 |
| 4. | D/man Gr.II | 1 | 1 | Nil |
| 5. | AAO | 1 | 1 | Nil |
| 6. | Head Clerk/ Asst. | 1 | 1 | Nil |
| 7. | U.D.C. | 2 | 1 | 1 |
| 8. | I.D.C. | 2 | 1 | 1 |
| 9. | Steno | 1 | 1 | Nil |
| 10. | S.C. Driver | 2 | 2 | Nil |
| 11. | S/ Guard | 2 | 2 | Nil |
| 12. | Peon | 2 | 1 | 1 |

Sent to Director (System) through E-mail at

- ddatender@dda.org.in