LIST OF ACTIVITIES

NORTH ZONE DDA

# CIRCLE :- CIVIL CIRCLE –7								DIVISION : NORTHERN DIVISION  - 1

| 1. | Details of Pending Final Bills & non-ref. of Security Deposits. |
| --- | --- |
| Name of Work | Agencies | Agmt. No. | Esst. Cost. Tender Cost | Stipulated | Remarks |
|  |  |  |  | D.O.S. D.O.C. |  |
| (i) | D/o Yamuna River Front (West Bank) along Vijay Ghat (Pushta) S.H. : C/o Water body at Yamuna Pushta | M/s Amar Constn. Co. | 76/EE/ND-I/DDA/ 04-05 | Rs.60,36,559/- Rs.16,49,051/- | 07.03.2005 06.07.2005 | Due to non submission of case by the earlier staff. |
| (ii) | --DO— S.H. : C/o root-zone channel in Phase-I at Yamuna Pushta. | M/s Birender Constn. Co. | 36/EE/ND-1/DDA/04-05 | Rs.7,68,600/- Rs.2,33,520/- | 31.10.04 30.11.04 | --do-- |
| (iii) | All due securities are being refunded on the request of respective Agencies. |  |  |  |  |  |
| 2. | Present status of works |
| S. No | Name of work | Estt. Cost Tendered Cost | D.O.S. D.O.C. | Progress up to previus month | Progress during this month | Up to date progress | Remarks |
| (i) | D/O Land Biodiversity park at Jharoda Mazra &Wazirabad SH: Cleaning & Sweeping of Nature Interpellation Center, path & parking in visitors area Agency: M/S Harender singh | Rs.82,392.00 Rs.52,800.00 | 18.07.07 17.07.08 | 25% | 15% | 40% | Work started on 18.07.07 |
| (ii) | D/O land under North Zone SH: C/O boundary wall of park between Sanik Vihar and Shakti Vihar Agency: Robin const. Co. | Rs. 9,16,334/- Rs. 12,60,267/- | 26.04.07 25.06.07 | 80% | 20% | 100% |  |
| (iii) | D/o Land Bio-Diversity Park at Jharoda Majra and Wazirabad SH : Providing sitting arrangement by constructing RR Masonry wall at Amphi Theatro M/s Bajrang Engineering | Rs.2,05,796/- Rs.1,54,237/- | 29.07.07 11.09.07 | 20% | 60% | 80% |  |
| (iv) | D/o Land Bio-Diversity Park at Jharoda Majra and Wazirabad SH : C/o RCC Pipe drain M/s Bajrang Engineering | Rs. 1,75,738/- Rs. 1,63,034/- | 07.08.07 06.10.07 | - | 20% | 20% |  |
| (v) | D/o Park between Sainik Vihar & Shakti Vihar, Pitam Pura SH : C/o Footpath M/s B.S.Builder | Rs.16,99,040/- Rs. 11,06,324/- | 01.09.07 31.10.07 | - | - | - | Transfer to ND-11 |
| (vi) | D/o Park between Sainik Vihar & Shakti Vihar, Pitam Pura SH : C/o Soft Parking Sh. Yash Pal Singh | Rs.11,74,777/- Rs.11,20,494/- | 04.09.07 03.12.07 | - | - | - | Transfer to ND-11 |
| (vii) | M/o park / plantation of Hort. Wing under North Zone SH : Repair of Boundary Wall and painting of MS Grill in park Block S(P) and T(P) Pitam Pura Sh. R.K.Rodiya | Rs.1,66,358/- Rs.1,44,942/- | 25.09.07 08.11.07 | 20% | 80% | 100% | Completed 26-10-07 |
| (viii) | M/o park / plantation of Hort. Wing under North Zone SH : Improvement of Baradari and fountain pond at Picnic Hut Park (Ashok Vihar Ph.III) Sh. R.K.Rodiya | Rs. 1,72,474/- Rs.1,54,429/- | 28.09.07 27.11.07 | - | - | - | Transfer to ND-11 |
| (ix) | D/o District Park at Sandesh Vihar Pitam Pura, SH : Sinking of Tube-Well (5 Nos.) M/s Soni Tube-Well Works | Rs.6,18,919/- Rs. 9,04,710/- | 28.09.07 27.11.07 | - | - | - | Completed 22-10-07 |
| (x) | M/o park / plantation of Hort. Wing under North Zone SH : Repair of Footpath and Boundary Wall of District Park Double Tank Pitam Pura Sh. R.K.Rodiya | Rs.3,49,893/- Rs.3,41,984/- | 01.10.07 30.11.07 | 20%` | 80% | 100% | Completed 26-10-07 |
| (xi) | C/o 336 Multi Storeyed HIG Houses at Mukherjee Nagar, SH : C/o 96 Multistoreyed HIG houses i/c pile foundation and internal electrification All complete Group II M/s Winner Construction Co. | Rs.8,77,43,884/- Rs.13,59,71,180/- | 31.08.07 30.08.09 | - | - | - | Design mix approved by CE (NZ). Test piles being cast. |
| (xii) | D/o Land Bio-Diversity Park at Jharoda Majra and Wazirabad SH : Raising of Stone Masonary B/Wall with random rubber at top fixed with concertina coil in corridor of Ph-I and II M/S A.G. Constructions Co. | Rs.4,64,489/- Rs.4,29,927/- | 16.10.05 15.11.07 | - | 20% | 20% |  |
| (xiii) | D/o Land Bio-Diversity Park at Jharoda Majra and Wazirabad SH : R/O damaged & Sunk grass Pavement / Path on main trail near R.C.C. bridge. M/S Sharma Constructions Co. | Rs.6,36,446/- Rs.4,95,085/- | 05.11.07 18.01.08 | - | - | - | Work yet to be start |
| 3. | Projects held up due to Court Case -- Respective Court with Case No. -- Date of Next Hearing | Nil |
| 4. | Rain Water Harvesting -- Already Provided -- Proposed | Nil Nil |
| 5. | Water bodies -- identified, status & under encroachment. | There are three numbers developed water body identified as water body No. 41(a), 42(a) and 34(a) |
| 6. | Details of Deposit Works : (a) in hand (b) Under approval - Status | Nil |
| 7. | Details of deviation in works : (a) Undertaken (b) Proposed (In Principle Approval) Nil |
| S.No. | Name of work | Agency | Agg. No. | Tendered Amount | Total Work Done | Deviation | Remarks |
| 8. | Restricted Call of tenders | S.H.: Improvement of park by providing Tubewell in Mazdoor wala park at Lawrence Rd. |
| 9. | Rescinded Works. | Nil |
| 10. | Arbitration & related Court Cases |
| a) | Arbitration | Nil |
| b) | Court Cases |
| S.No | Description of Item | Agency | Name of Court Case No. | Name of P/L | Next date of Hearing |
| (i) | C/o 560 MIG DU’s at Pkt. (P) Pitampura S.H. : C/o 192 MIG DU’s at Pitampura | M/s Prakash Sharma | Supreme Court SLP (C) 2872/01 | Mrs. Kum Kum Sen. | Pending for want of irregular hearing |
| (ii) | C/o 720 LIG DU’s at Pitampura Pkt. W(P) SH. : C/o 396 LIG DU’s at Pitamprua Pkg. W(P) i/c Internal services. | M/s Sudhir Brothers | High Court OMP. 93/88 | Mrs. A. Salwan | Pending for want of hearing w.e.f. 27.07.2006 |
| (iii) | C/o 330 LIG Incremental houses i/c internal water supply sanitary installation & internal development work in sector B-IV Pkt. 6 Gr.1 at Narela. | M/s Nav Bharat Const. Co. | High Court OMP 285/06 | Sh. Bhupesh Narula | 15.02.2008 |
| (iv) | C/o 770/324 LIG DU’s at Pitampura Pkt. (W) (P) | M/s Verma Const. Co. | High Court OS-765/06 | Sh. Bhupesh Narula | 15.11..2007 |
| (v) | C/o MIG / LIG Shop & Services 256 Hact. Land at Sarai Khalil SG : C/o Road (Balance work) | M/s Ajay Verma | Tis Hazari EY/123/06 | S.L.O. (T.C.) | 02.11..2007 |
| (vi) | C/o 64 Three B/R 64 Two B/R & 96 Scooter Garage under SFS at Pitamprua | M/s Sudhir Brothers | Tis Hazari 112/03 | Mrs. Beena Sharma | 20.11.2007 |
| (vii) | M/o Parks / Plantation Hort. Wing under North Zone SH. : Sinking of tubewell & P/F unfiltered water line behind of Kirpal Bagh (Joginder Wala Bagh) Gujaran Wala Town Phase-III | Sh. S.D. Falwaria | Tis Hazari 87/2005 | Mrs. Shushma Sharma | 14.01.2008 |
| (viii) | D/o green belt in front of Bl. E to I in Ashok Vihar Phase-I SH. : C/o Cement Concrete tiles and moorum path in front of bl. E to I. | M/s Durga Const. Co. | Tis Hazari 216/04 | Sh. K.D. Sharma | 22.11.2008 |
| 11. | Details of Q.C. Lab. Tests, procedures | N.A. |
| 12. | Fire fighting Equipments : Installed (Nos.) with Location | Not installed as yet |
| 13. | List of Soil Testing Laboratories | Are issued by E.M. Office |
| 14. | List of Approved Structural Consultants | Does not pertain to this office |
| 15. | Technical Circulars | Are issued by V.C., E.M., C.E. (Q.C.) and Vigilance Department |
| 16. | Q.C. Circulars | Are issued by QAC, DDA |
| 17. | List of Contractors, A, B, C, D categories | Pertains to CRB/DDA |
| 18. | RIS/ EIS/ EOT Cases & Completion Certificate |
| S.No | Name of Work | Agency | Agreement No. | EIS | RIS | SIS | Amount | EOT |
| (i) | D/o Yamuna River Front (West Bank) along Vijay Ghat (Pushta) S.H. : C/o Water body at Yamuna Pushta | M/s Amar Constn. Co. | 76/EE/ND-I/DDA/ 04-05 | -- | -- | -- | -- | Remarks C.C. to be recorded |
| (ii) | --DO— S.H. : C/o root-zone channel in Phase-I at Yamuna Pushta. | M/s Birender Constn. Co. | 36/EE/ND-1/DDA/04-05 | -- | -- | -- | -- | Remarks C.C. sent to competent authority for counter signed |
| (iii) | M/o Park/Plantation of Horticulture Wing under North Zone SH : Repair of Boundary Wall in M.D. Park (District Park) Lawrence Road | M/s S.V Construction Co. | 58/EE/ ND-1 DDA/ 06-07 | EIS No.I |  |  | Rs. 5412/- | EOT approved |
| (iv) | D/o Green belt along Block B to I Ashok Vihar Phase-I SH : P/L unfiltered water supply line in front of Block B to E | Sh. Rajinder Singh | 5/EE/ ND-1 DDA/ 07-08 | EIS No. I & II III IV V | - | - | Rs. 19,904/- Rs.40,630/- Rs.8205/- Rs.5494/- | EOT approved |
| (v) | D/o Yamuna river front (West bank along Vijay Ghat Pushta SH: Root Zone Channel (Water bodies) in Ph-I Yamuna Pushta | M/s Birender Construction Co. | 36/EE/ND-I/ DDA/04-05 | Revised EIS-I |  |  | Rs.1,48,462/- |  |
| (vi) | D/o Yamuna river front (West bank along Vijay Ghat Pushta SH : P/F Fabricated Huts (3 Nos) Pota Cabin at Yamuna Pushta | M/s Home Decorators |  | EIS-I |  |  | Rs.73,146/- | EOT Yet to be approved |
| (vii) | M/o Park/Plantation of Horticulture Wing under North Zone SH : Repair of Boundary Wall at Khojewala Park, Ashok Vihar, Phase-II. | M/S Bajrang Engg. |  | EIS I & II |  |  | 53,474/- | EOT yet to be approved |
| (viii) | M/o Park/Plantation of Horticulture Wing under North Zone SH : Repair of path and water supply line in Distt. Park at Pritam Pura. | M/S N.K. Enterprises |  | EIS I & II |  |  | 11,657/- |  |
| (ix) | D/o Janak wala Bagh at Bharat Nagar, Ashok Vihar, Phase-iv SH : C/O Red Bajri Path | Sh. Yashpal Singh |  | EIS-I |  |  | 13,443/- | EOT approved |
| 19. | List of approved rates of SE (P) | Are issued by Chairman Market Rate Approval Committee / Concerned SE (P) |
| 20. | Areas where services are handed over to MCD / DJB & Deficiency charges | N.A. |
| 21. | List of vacant flats / Shops / Keosk / Commercial / Residential Plots on the date of completion / development. | N.A. |
| 22. | Jurisdiction of C.E. / Map. EE wise | Asstt. Engineer-I D/o land for Bio-diversity Park at Jharoda Mazra Wazirabad Phase-I & II Asstt. Engineer-II D/o Park at Sandesh Vihar C/o 336 Multistoreyed HIG Houses at Mukherjee Nagar SH : 96 Multi Storeyed HIG Houses i/c Pile Foundation and Internal Electrification. All complete Gr- II Asstt. Engineer-III Shastri Nagar 56 Bigha Park Shastri Nagar Park Gulabi Bagh District Park Sindhora Kalan Park Faiz Road Park Idgah Park Asstt. Engineer-IV Mazdoor Wala Park at Lawrence Road Rose Garden Park at Lawrence Road Nepal Wala Bagh at Lawrence Road Pahari Wala Bagh at Lawrence Road MD Park at Lawrence Road |
| 23. | Details of land handed over to Engineering Wing for development | 157 Acre for D/o Land Bio-Diversity Park at Jharoda Mazra PH-I is in progress and 300 Acre land for Bio-diversity Park at Jharoda Mazra Wazirabad Ph-II has been taken over by Engineering Wing. |
| 24. | Sanctioned Strength / In place / vacancy position of Regular Staff |
| S.No | Designation | Sanctioned Strength | Men in Position | Shortfall | Excess |
| 1. | E.E. © | 1 | 1 | -- | -- |
| 2. | A.E. © | 5 | 4 | 1 | -- |
| 3. | A.A.O. | 1 | 1 | -- | -- |
| 4. | Head Clerk | 1 | 1 | -- | -- |
| 5. | Steno | 1 | 1 | -- | -- |
| 6. | J.E. (C) | 12+1 | 13+1 | -- | 1 |
| 7. | D/Man | 1 | 1 | -- | -- |
| 8. | U.D.C. | 4 | 3 | 1 | -- |
| 9. | L.D.C. | 6 | 4 | 2 | -- |
| 10. | Daftry | 1 | 1 | -- | -- |
| 11. | Peon | 4 | 4 | -- | -- |
| 12. | S.C.D. | 1 | 1 | -- | -- |

EXECUTIVE ENGINEER

ND-1, DDA