LIST OF ACTIVITIES

NORTH ZONE, DDA

Circle:-	Civil circle-7						DIVISION:-	Northern Division WD-5

As on 30.09.2007

| 1. | Details of Pending Final Bills & non-ref, of Security Deposits. |
| --- | --- |
|  | Name of Work | Agencies | Agmt. No. | Esst. Cost. Tender Cost | Stipulated | Remarks |
|  |  |  |  |  | D.O.S D.O.C |  |
| i. | Protection of D.D.A. Land SH: C/o Randum rubble masonry on vacant land under jurisdiction of CC-5 | M/s Tara Chand Sumit Construction Co. | 13/EE/WD-5/DDA/05-06 | 893801 591219 | 28.11.05 27.05.06 | Work has been completed payment of 7th R/A held up as per instruction of higher authorities. |
| ii. | M/o of Vikas Minar SH: P/F floor tiles on 5th 6th & 7th floor at Vikas Minar | M/s S.K. Mittal & Co. | 34/EE/WD-5/DDA/05-06 | 487418 290090 | 26.03.05 25.04.05 | Concerned MB’s with vigilance brand in other case |
| iii. | All due securities are being refunded on the request of respective Agencies as & when received |

| 2 | Present statues of works as on 30.09.07 |
| --- | --- |
| S. No. | Name of Work | Estt. Cost Tendered Cost | D.O.S D.O.C | Progress up to previous month | Progress during this month | Up to date progress | Remarks |
| i. | D/O Distt. Centre at Rajindra Place (Bal. Dev. & Constn. Work). SH: C/o parking lot ‘D’. Agency: M/s Tara Chand Sumit Const. Co. | 8342464.00 8714478.00 | 09.02.06 08.08.06 | 82% | — | 82% | Likely deviation yet to be approved |
| ii. | M/o Vikas Minar SH : Replacement of basement flooring for parking at Vikas Minar. Agency : Sh. M/s Tara Chand Sumit Const. Co. | 1236568.00 1841908.00 | 14.10.06 13.04.07 | 18% | — | 18% | Show cause notice has been issued under clause 3 of the agreement. |
| iii. | M/o Vikas Minar SH: Cleaning & mopping of toilets, pantries, spittoons, dustbin, stair case, corridors, etc. of Vikas Minar Agency : M/s. Globe Construction Co. | 298862.00 183888.00 | 27.09.07 31.03.08 | — | — | — | Work recently awarded |
| iv. | M/o Vikas Minar SH:- Supply of material for day to day maintenance of Vikas Minar for repair of wooden partition/ glasses in aluminum and wooden partition and their accessories | 193250.00 273965.00 | 28.09.07 27.10.07 | — | — | — | Work recently awarded |
| v. | M/o Vikas Kuteer SH : Scavenging and cleaning of office building, open area and toilets at Vikas Kuteer Agency : M/s S. V. Enterprises | 40077.00 56400.00 | 01.06.07 31.12.07 | 40% | 5% | 45% | Work in progress |
| vi. | M/o Completed scheme of N/A. II under SWZ. SH : P/F G.I. barbed wire fencing along proposed passage for local people of Dasghara Village and Const. of wicket gates. Agency : M/s P.K. Engineer | 136053.00 141210.00 | 10.07.07 09.08.07 | — | 20% | 20% | Show cause notice under clause 3 of the agreement has been issued |
| vii | Special Repair of Vikas Minar. SH : Rehabilitation of RCC column and beams and other RCC members of Vikas Minar. Agency : M/s Cembond Constructions. | 5849019.00 6997284.00 | 18.01.07 14.04.08 | 2% | — | 2% | Scaffolding work in progress |
| viii | M/o completed scheme of Nazul A/c-II under SWZ. SH : Repair of broken boundary wall and closing of missing link at R Block Park, New Rajindera Nagar. Agency : M/s Amit Builders | 237630.00 219873.00 | 15.07.07. 14.09.07 | — | 100% | 100% | Work completed |
| ix. | M/o completed scheme (shops) under N/Z. SH: disinfection & chemical treatment of 3 nos. UGR at distt. Centre Rajindera Place Agency: M/s SV Enterprises | 37562.00 44880.00 | 28.09.07 12.10.07 | — | — | — | Work recently awarded |
| 3. | Projects held up due to Court Case |
|  | -- Respective Court with Case No. -- Date of Next Hearing | Nil |
| 4. | Rain Water Harvesting |
|  | -- Already Provided -- Propose | Nil |
| 5. | Water bodies |
|  | -- identified, status & under encroachment. | Nil |
| 6. | Details of Deposit Works: |
|  | in hand (b) Under approval - Status | Nil |

| 7. | Details of deviation in works: during September, 2007 |
| --- | --- |
|  | (a) Undertaken. Nil (b) Proposed (In principal approval) |
| S No. | Name of work | Agency | Agg. No. | Tendered | Total Work Done | Deviation | Remarks |

| 8 | Restricted Call of tenders |
| --- | --- |

LIST OF WORK ORDER FOR THE YEAR 2007-08

| W.O. No. | Name of Work | Estt. Cost | Work order amount | Sanctioned by | Time allowed |
| --- | --- | --- | --- | --- | --- |
| 1/ EE/WD-5 DDA/ 0 7 -08 | M/O Staff Qtrs. At Rajinder Nager SH: Repair and renovation work in Bungalows and Barat Ghar at Rajinder Nagar, | Rs, 4,73,800/- | Rs. 5,95,583/- | CE (SWZ) DDA | 38 days |
| 2/EE/WD-5- DDA/07/08 | M/o Vikas Minar. SH: Providing temporary protection from falling loose concrete. | Rs. 1,60,459/- | Rs. 1,53,780/- | S.E./CC-5/DDA | 25 days |
| 3/ EE/ WD-5/ DDA/07-08 | M/o Vikas Minar. SH: Alteration of existing partition frame resistant partition of Director (IS) Alterations. | Rs. 5,45,683/- | Rs. 5,78,328/- | CE (SWZ) DDA | 15 days |
| 4/ EE/ WD-5/ DDA/07-08 | M/o Completed Scheme under N/Z A/c-1 of SWZ SH: Replacement of M.S Windows, Grills, Jallis etc. by providing Aluminium Windows Grill, Jalli etc. at Flat No. 7/1 Bhagwan Das Road | Rs. 2,22,165/- | Rs. 2,83,798/- | SE/CC-7/DDA | 20 days |
| 5/ EE/ WD-5/ DDA/07-08 | ARMO Staff Quarters at Rajindra Nagar SH: Total Station survey of Staff Quarters at Rajindra Nagar | Rs. 22,000/- | Rs. 29,214/- | EE/WD-5 | 7 days |
| 6/ EE/ WD-5/ DDA/07-08 | M/o Vikas Minar SH: Renovation of chamber at commissioner (system & planning) at 9th floor Vikas Minar | Rs. 83,556/- | Rs. 98,789/- | EE/WD-5 | 1 Month |
| 9. | Rescinded Works. |
|  |  | Nil |
| 10. | Arbitration & related Court Cases |
| a) | Arbitration | Nil |
| b) | Court Cases | List of Court Cases are as under |
| S. No. | Description | Agency | Name of Court | Name of panel lawyer | Next dt. Of Hearing |
| 1 | 2 | 3 | 4 | 5 | 6 |
| i. | D/o J.J Colony kalkaji. Sh: P/L Dense carpet concrete work in J.J. Colony | Sh. Satya Prakash & Brothers | High Court. | Sh. D.S. Mhendroo | 07.03.2008 |
| ii. | C/o 504 SFS Cat. II houses at Sukhdev Vihar. Sh. C/o 192 Du’s i/c int. Development. | M/s. Bhartya Const Co. | High Court. 208/97 | Sh. B.B. Sharma | Order Reserved |
| iii. | C/o 232/108 SFS Cat. II houses at Paschim Vihar. | M/s/ Hindustan Prefab Ltd. | High Court. 320/96 | Mrs. Sangeeta Chandra | Regular hearing |
| iv. | C/o 232/124 SFS houses at Paschim Vihar. | M/s/ Hindustan Prefab Ltd. | High Court. CS (OS) 1965/96 | C. Mohan Rao | Recovery suit filed 18.12.07 |
| v. | C/o 504 SFS Houses at SukhDev Vihar. Sh: Pile foundation. | M/s Ground Engineer Co. (P) Ltd. | High Court 67-A/96 Ex. 47/2002 | Mrs. A. Salwan | Regular Hearing |
| vi. | C/o M.S.O. Bldg for DDA office SH: Bldg. & basement portion | M/s. Layall & Co. | High Court. FAO (05) 243/92 | Mrs. A. Salwan | Regular Hearing |
| vii. | C/O 160 SFS at Sukhev Vihar. | Sh. K.K. Rathi | High Court. 179/92 | Mrs. A. Salwan | Case decided and copy of judgment awaited |
| viii. | M/o Completed scheme under SWZ. Sh. Repairing of road of Janakpuri Paschim Vihar. | Sh. S.P. Gupta | High Court 558/2002 | K. R. Chawla | 09.10.2007. |
| ix. | Ray Provision of passes to Village Dsagarha through ridg. | Residents of Village Dasgrah by DDA | High Court. | Sh. Rajeev Bansal | 14.08.2007 |
| x. | C/o 864 LIG Houses at Hastsal Pkt-‘B’. SH: C/o 252 LIG Houses including internal water supply installation and internal development. | M/s Arkey Engineers Co. | Tis Hizari Court. | Sh. Rohit Jain | 18.10.2007 |
| xi. | Destitutinal area D- Block Janakpuri | Vice Chairman V/s Dir. Revenue & other | Tis Hizari Court. | Sh. H.K.L. Seghal. | 13.02.2008 |
| xii. | C/o 504 SFS Cat. II houses at Sukhdev Vihar. Sh. C/o 192 Du’s i/c int. Development. | M/s Bhartiya Const. Co. | High Court. FAO (OS) 273/97 | Sh. B.B. Shrama & Jagmohan Sabharawal. | 30.10.2007 |
| xiii | C/o 504 SFS Cat. II Houses at Sukhdev Vhiar Sh: C/o 152 MIG/ Cat. II SFS | Sh. S.S. Jetly | High Court 275/01 | Ms. A Salwan | 20.11.2007 |
| xiv. | C/o Shopping Center at Nehru Place on Plot No. 42 | C. Lal Gupta. | High Court. | Mrs. A. Salwan | 05.11.2007 |
| xv. | C/o 56/136 houses at Toda Pur i/c internal development | M/s Happy Himalya | T.C. 305/04 | Smt. Promila Kapoor | 12.11.07 |
| 11. | Details of Q.C Lab. Tests, Procedures | N/a |
| 12. | Fire fighting Equipments: Installed (Nos) with Location | N/a |
| 13. | List of Soil Testing Laboratories | N/a |
| 14. | List of Approved Structural Consultants | N/a |
| 15. | Technical Circulars | N/a |
| 16. | Q.C. Circulars | N/a |
| 17. | List of Contractors, A, B, C, D categories | N/a |

| 18 | RIS/ EIS/ EOT Cases & Completion Certificate during September, 2007 |
| --- | --- |
| S. No. | Name of Work | Agency | Agreement | EIS | RIS | SIS | Amount | EIT |
| 19. | List of approved rates of SE(P) | Are issued by Chairman Market rate approval committee/Concerned SE (P) |
| 20 | Areas where serviced are handed over to MCD/ DJB & Deficiency charges. |  |
| 21 | List of vacant flats/ Shops/ Keosk/ Commercial/ Residential Plots on the date of completion development. | Distt. Center Rajinder Place 2 nos shops bearing shope no. 103 & 145 Hog market Rajindera Place 3 nos shops bearing shops no 193, 194 & 196 Janta Flats Toda Pur 5 nos flats bearing flat nos 103, 113, 83, 86, & 94 |
| 22. | Jurisdiction of C.E/Map. EE wise | Asstt. Engineer- I M/o Vikas Minar office building floor 11 to 21 M/o Vikas Kuteer Barrack No. - 6 |

|  | Asstt. Engineer- II (i) M/o Vikas Minar office building floor basement to 10 floor |
| --- | --- |

|  | Asstt. Engineer- III M/o of staff quarter at Rajindera Nagar, Jaidev Park, Concrete House Karol Bagh, Dev Nagar & Bagh Rao Ji D/o Anand Parbhat area M/o LSC 2,4 & 20 and CSC 22 at New Rajindera Nagar M/o MOR land pocket 7,8,9 at New Rajindera Nagar D/o of land at 8A WEA Karol Bagh |
| --- | --- |

|  | Asstt. Engineer- IV Distt. Center of Rajindera Place Bhooli Bhatyari Park at Ridge “R” Block Park at New Rajindera Naga Rock Garden at Patel Nagar Satya Park Naraina Industrial area Phase-II Maha Raja Aggarsen Park Inder Puri N.H.P. Park Naraina Janta Flats Toda Pur Golden Park |
| --- | --- |
|  | Asstt. Engineer- V (i) M/o officers Staff Flats at Bhagwandas Road |

| 23. | Details of land handed over to Engineering Wing for development | Nil |
| --- | --- | --- |
| 24. | Sanctioned Strength/In place/ vacancy position of Regular Staff |
| S. No. | Designation | Sanctioned Strength | Men in Positions | Shortfall | Excess. |
| (i) | Executive Engineer | 1 | 1 | — | — |
| (ii) | Assistant Engineer | 5 | 6 | — | 1 |
| (iii) | Junior Engineer | 17 | 10 | 7 | — |
| (iv) | Divisional Accountant | 1 | 1 | — | — |
| (v) | Head Clerk | 1 | 1 | — | — |
| (vi) | UDC | 5 | 5 | — | — |
| (vii) | LDC | 7 | 2 | 5 | — |
| (viii) | Assistant Cashier | 1 | 1 | — | — |
| (ix) | Steno | 1 | — | 1 | — |
| (x) | D/Man | 1 | 1 | — | — |
| (xi) | Peon | 4 | 3 | 1 | — |

EXECUTIVE ENGINEER

WD-5/DDA