DELHI DEVELOPMENT AUTHORITY

ELECTRICAL DIVISION NO. 8

LIST OF ACTIVITIES

1. Details of Pending Final Bills & non-refund of Security Deposits.

A.	Details of pending final bills for the Month ending November, 2007

| Sl. No. | Name of Work | Agency | Agreement No. | Stipulated date of start Completion | Actual date of completion | Date of payment of final bill | Reasons for delay in payment of final bill |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | 2. | 3. | 4. | 5. | 6. | 7. | 8. |

-------------------------------------------------------------------------NIL------------------------------------------------------------------------------------

.B	Details of non-refund of Security Deposits for the Month ending November. 2007

| Sl. No. | Name of Work | Agency | Agreement No. | Stipulated date of start Completion | Actual date of completion | Date of payment of final bill | Amount of Security Deposit deducted | Reasons for delay in refund of Security Deposit |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | 2. | 3. | 4. | 5. | 6. | 7. | 8. | 9. |

-------------------------------------------------------------------------NIL------------------------------------------------------------------------------------

2. Present status of works.

List of works costing more than Rs. 2.00 lacs for the month ending Nov., 2007

| Sl. No. | Name of Work | Agency | Estt. Cost Tendered amount(in lacs) | Stipulated date of start Completion | Physical progress | Actual Date of completion | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | 2. | 3. | 4. | 5. | 6. | 7. | 8. |
| 1. | A) Construction/Development Works C/o 320/258 MS houses SFS at Motia Khan SH: IEI of 66 flats Blk-1 Motia Khan | Goel Elect. Works | 17.41 16.69 | 18.9.03 17.3.06 | 70% | Work in progress |  |
| 2. | C/o 216 MIG DU’s MS at Pitampura (near TV Tower) SH: C/o 72 MIG DUs i/c sanitary installation, water supply, sewage, drainage, roads & paths and internal electrification Gr.I | Ved Prakash Mittal & Sons | 22.57 50.54 | 25.10.06 24.10.08 | 30% | Work in progress |  |
| 3. | C/o 216 MIG DU’s MS at Pitampura (near TV Tower) SH: C/o 144 MIG DUs i/c sanitary installation, water supply, sewage, drainage, roads & paths and internal electrification Gr.II & III | Winner Constn. Pvt. Ltd. | 45.18 73.01 | 14.12.06 13.12.08 | 28% | Work in progress |  |
| 4. | S/I of DG Set and replacement of LT Panel at Vikas Minar SH: Supplying, errection, testing and commissioning of DG Set at Vikas Minar | Budhiraja Electricals | 25.09 21.52 | 22.2.07 21.5.07 | 80% | Work in progress |  |
| 5. | C/o 560 SFS houses Cat.II in Blk-D Pkt-1, Shalimar Bagh a)IEI of 192 SFS DUs Gr.I b)IEI of 208 FS DUs Gr.II | Goel Elect. Goel Elect. | 23.27 18.77 22.21 20.33 | 27.12.02 26.6.05 5.1.03 4.7.05 | 75% 75% | Work in progress Work in progress |  |
| 6. | C/o 70 LIG DUs in Blk.BH Poorvi Shalimar Bagh SH:IEI | Cholia Elect. Works | 5.27 5.35 | 16.10.05 15.4.07 | 60% | Work in progress |  |

3. Details of deviation in works:

Details of deviations in works for the Month ending Nov., 2007.

| Sl. No. | Name of work | Name of Agency | Agreement No. | Estimated Cost. Tendered Amount | Amount (in lacs) |
| --- | --- | --- | --- | --- | --- |
| 1. | M/o pumps set at various colonies under North Zone (SH: Annual operation and maintenances of mono block pump sets for clear water supply at Community Centre Block-K (P), Pitampura | M/s Satkar Electricals | 35/EE/ED-8/ DDA/ 2006-07 | 1.61 1.58 | 0.15 |
| 2. | M/o Completed schemes of North Zone under NA-II (SH: Annual operation and maintenance of musical fountain at Saraswati Vihar | M/s Pumps Engineering & Associates | 33/EE/ED-8/ DDA/ 2006-07 | 1.71 1.70 | 0.13 |

4. Restricted Call of Tenders.

Details of Restricted Call of Tenders for the Month ending Nov., 2007.

| Sl. No. | Name of work | Name of Agency | Amount (in lacs) |
| --- | --- | --- | --- |

---------------------------------------------------------NIL-------------------------------------------------------------------

5. Rescinded Works:

Details of Rescinded Works – Status as on 30.11.07

| Sl. No. | Name of Work | Agency | Agreement No. | Stipulated date of start Completion | Provisional extension granted upto | Date of rescission of work | Date of award of balance work | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | 2. | 3. | 4. | 5. | 6. | 7. | 8. | 9. |

-------------------------------------------------------------------------NIL------------------------------------------------------------------------------------

6. Arbitration & related Court Cases.

A.	Details of Court Cases pending at the end of Nov., 2007 – Services matters

| Sl. No. | File No. | Name of employee | Name of Court/Suit No. | Name of Panel Lawyer | Nature of case | Present position | Next date of hearing | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | 2. | 3. | 4. | 5. | 6. | 7. | 8. | 9. |
| 1. | F.1(476)95/IC/Legal | Sh. Om Prkash, Wireman W/C ® V/s DDA | Distt. Court RCA 11/2000 | Sh. Ashish Sharma | Transfer of W/C Staff to MCD | Arguments continued | 04.01.08 | - |

B.	Details of Court Cases pending at the end of  Nov., 2007 – (Works)

| Sl. No. | File No. | Name of Work | Name of Agency | Name of Court/Suit No. | Name of Panel Lawyer | Nature of case | Present position | Next date of hearing | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | 2. | 3. | 4. | 5. | 6. | 7. | 8. | 9 | 10. |
| 1. | F21(122)1999/HC/Legal | C/o 448 MIG DUs at Pkt. KD Pitampura SH: IEI of 356 DUs in Gr. II | Bumbrah Elect. Co. V/s DDA | High Court CWO 2561/98 | Sh. D.S. Mahendru | Nil Arbtrn. Award challenged by agency in Court. | Argument continued | 21.01.08 |  |
| 2. | F12(16)1999/TC/Legal | C/o 480 LIG houses at Pkt. KD Pitampura SH: IEI | R.K.Aneja V/s DDA | Distt. Court 1996 A/95 | Sh. S.S. Mittal | Suit file for recovery of Rs. 97610/- levied as compensation under Clause 2 of the Agreement | Argument continued | 11.12.07 |  |
| 3. | F12(429)06/HC/Legal | Electrification of plot No. 4 Community Centre Motia Khan | Rajesh Projects India Pvt. Ltd. V/s BSES Rajdhani Power Ltd. & others | WP©No. 8212/06 | Sh. Jag Mohan Sabherwal | Electrification of Community Centre Motia Khan | Counter statement filed | 18.03.08 |  |
| 4. | F21(221)96/HC/Legal | D/o land at JJR Colony Jahangirpuri SH: S/I of storm/sewage pumps | Gita Pumps V/s DDA & MCD | OMP No. 1/96 | Sh. Bhupesh Narula | Arbitration award challenged | Argument continued | 23.01.08 |  |

7. Fire fighting Equipments (installed with locations):

| Sl. No. | Location | Electric driven pumps | Diesel driven pumps | Jocky pumps | Fire extinguishers | Yard Hydrant | Fire Hydrant | Sprinkler System |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | 2. | 3. | 4. | 5. | 6. | 7 | 8 | 9 |
| 1. | Rajendra Bhawan, Rajendra Place | 100 HP – 2 Nos. | 100 BHP – 1 No. | 20 HP – 1 No. | 7 Nos. | 8 Nos. | - | Provided in basement |
| 2. | Motia Khan (MS housing) | 75 HP – 1 No. | 100 BHP – 1 No. | 20 HP – 1 No. | 5 Nos. | 12 Nos. | 20 Nos. | - |
| 3. | Jhandewallan | 75 HP – 2 Nos. | 75 BHP – 1 No. | 15 HP – 1 No. | 2 Nos. | 7 Nos. | - | - |
| 4. | Vikas Minar | 100 HP – 2 Nos. | 127 BHP – 1No. | 25 HP – 2 Nos. | 56 Nos. | 2 Nos. | 27 Nos. | Provided in basement & in all floors. |

8. EIS/EOT cases & Completion Certificate:

Details of EIS for the Month ending Nov., 2007

| Sl. No. | Name of Work | Name of agency | Agreement No. | Estimated Cost Tendered Amount | Stipulated Date of Start Stipulated Date of Completion | Amount (in lacs) |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | 2. | 3. | 4 | 5 | 6 | 7 |
| 1. | M/o Pump sets at various colonies under North Zone (SH: Annual operation & maintenance of clear water pump set at 656 MIG Houses at Jahangirpuri | M/s Shiv Electric | 38/EE/ED-8/ DDA/ 2006-07 | 1.62 1.58 | 08.10.06 07.10.07 | 0.08 |
| 2. | M/o Pump sets at various colonies under North Zone (SH: Annual maintenance & operation of clear water pump set, D.G. set and sub-pump sets at 560 SFS Flats Cat.-II Block-C&D, Shalimar Bagh. | M/s Super System Engineers | 95/EE/ED-8/ DDA/ 2006-07 | 3.31 3.25 | 26.03.07 25.03.08 | 0.08 |
| 3. | M/o completed schemes of North Zone under NA-II (SH: Operation & maintenance of clear water pump set at Cascade Shopping Centre at Neta Ji Subhash Place, Pitampura | M/s Kuka Enterprises | 36/EE/ED-8/ DDA/ 2006-07 | 1.88 1.79 | 25.09.06 24.09.07 | 0.05 |

Details of EOT cases for the Month ending Nov. 2007

| Sl. No. | Name of Work | Agency | Agreement No. | Estt. Cost Ten.Amt. | EOT granted without levy of compen- sation | EOT granted with levy of compensa- tion | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | 2. | 3. | 4. | 5. | 6. | 7. | 8. |
| 1. | M/o completed schemes of North Zone under NA-II (SH: Annual operation and maintenance of musical fountain at Saraswati Vihar. | M/s Pumps Engineering & Associates | 33/EE/ED-8/DDA/06-07 | 1.71 1.70 | 21.09.07 to 02.10.07 | - | - |
| 2. | M/o completed schemes of North Zone under NA-II (SH: Comprehensive maintenance of programmable computerized musical fountain at Distt. Park, Pitampura . | M/s S.K. Enterprises | 87/EE/ED-8/DDA/05-06 | 1.30 1.27 | 09.02.07 to 08.06.07 | - | - |

9.Sanctioned Strength/In place/vacancy

Position of Regular Staff

| S.No. | Designation | Sanction strength | Present strength | Shortfall |
| --- | --- | --- | --- | --- |
| 1. | Executive Engineer | 1 | 1 | Nil |
| 2. | Asstt. Engineer | 5 | 5 | Nil |
| 3. | Junior Engineer | 17 | 16 | 1 |
| 4. | D/ man Gr. II | 1 | 1 | Nil |
| 5. | AAO | 1 | 1 | Nil |
| 6. | Head Clerk/ Asstt. | 1 | 1 | Ni. |
| 7. | U.D.C. | 2 | 1 | 1 |
| 8 | I..D.C. | 7 | 4 | 3 |
| 9. | Steno | 1 | 1 | Nil |
| 10 | S.C. Driver | 1 | 1 | Nil |
| 11. | S/ Guard | 2 | 2 | Nil |
| 12. | Peon | 2 | 1 | 1 |

Sent to Director (System) through E-mail at

- dda.tender@dda.org.in 2) dirsystem@.dda.org.in