DELHI DEVELOPMENT AUTHORITY

ELECTRICAL DIVISION – 5 / ELECTRICAL CIRCLE -I

List of Activities:-

1.	Detail of pending final bills & non refund of security deposits :-

(i)	Detail of pending final bill :-

| S. No. | Name of Scheme | Estt. Cost Tendered Cost | Agreement No. Agency | D.O. Start Period of Completion |
| --- | --- | --- | --- | --- |
| 1. | C/o 212 SFS Houses at Sect. 6, Pkt I, Dwarka, Phase I SH: Running & operation of 20 KVA DG set Sub P/set & 10 HP Booster pump set | Rs. 88548.00 Rs. 84000.00 | 4/EE/ED-5/99-200 M/s Hindustan Enterprises | 20.5.99 12 Months |
| 2. | M/o Various colonies under Dwarka Zone. SH : Running, Maintenance and operation of 20 KVA DG set sub P/set and 10 HP booster P/set at Sector 6, Dwarka, Phase I | Rs. 102732.00 Rs. 98400.00 | 19/EE/ED-5/2000-01 M/s Hindustan Enterprises | 20.7.2000 12 Months |
| 3. | M/o various colonies under Dwarka Zone (SH : r/m/ operation of 10 HP booster pump set, 5 HP Sub P/set & 20 KVA DG set at C/o 212 SFS in Pkt – I, Sector 6, Dwarka, Phase I ) | Rs. 112800.00 Rs. 108000.00 | 6/EE/ED-5/DDA/2001-02 M/s Hindustan Enterprises | 20.8.2001 12 Months |

| 2. Progress Report of works costing of more than 2 Lakhs. |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| S. No. |  | Name of Scheme |  | Estt. / Tender Cost | Agent No. |  | Agency | Date of Start Time of comp. (Period) |  | Supplementary Agmt. if drawn | Physical Progress % of Allotment | Payment Made upto date (in lacs) |
| 1. |  | C/o 568 (520 Cat. III & 48 Cat II) Multistoreyed houses HIG DU’s in Sec – 18-B, at DWK. Ph. II. SH: IEI of 266 DU’s (236 Cat III& 30 cat II) in Gr. I. |  | 6325785.00 4891948.00 | 21/EE/EI.D.5/DDA/02-03 |  | M/s Shiv Electric | 01-09-02 36 Months |  | No | 75% | 24.10 |
| 2. |  | C/o 568 (520 Cat III & 48 Cat II) Multistoreyed DU’s in Sect. 18-B at Dwarka Ph. II. SH: IEI OF 302 DU’s (284 cat III & 18 cat II) in Gr. II. |  | 7232514.00 5588641.00 | 24/EE/EI.D.5/DDA/02-03 |  | M/s Shiv Electric | 06-09-02 36 Months |  | No | 75% | 23.96 |
| 3. | C/o 440 HIG (cat – III) Multistoreyed houses in Sect. 19-B, Dwarka, Ph. II SH: IEI of 368 DU’s cat III & 72 DU’s cat II. |  | 10499348.00 8128975.00 |  |  | 23/EE/EI.D.5/DDA/02-03 | M/s Shiv Electric |  | 06-09-02 36 Months | No | 75% | 32.57 |

| S. No. | Name of Scheme | Estt. / Tender Cost | Agent No. | Agency | Date of Start Time of comp. (Period) | Supplementary Agmt. if drawn | Physical Progress % of Allotment | Payment Made upto date (in lacs) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 4. | C/o 440 HIG (Cat III) Multistoreyed houses in Sect. 19-B, Dwarka, Ph. II. SH : Providing & Installation of Fire Fighting sytem. | 5021892.00 5498356.00 | 25/EE/EI.D.5/DDA/02-03 | M/s Hooxon Trading Corpn. | 21-12-02 36 Months | No | 95% | 37.45 |
| 5. | C/o 528 LIG houses in Pkt. 3-C, Sect. 16-B, Dwarka, Ph II, SH : IEI of 256 LIG houses in Pkt. 3-C, Sect. 16-B, DWK. Ph. II, Gr. II | 2138838.00 1881180.00 | 03/EE/EI.D.5/DDA/2000-2001 | M/s Bharat Electric Co. | 20-04-02 24 Months | Yes | 80% | 16.38 |
| 6. | C/o 528 LIG houses in Pkt. 3-C, Sect. 16-B, DWK. Ph II. SH : IEI of 256 LIG houses in Pkt. 3-C, Sect. 16-B, Gr. I | 2013300.00 1770745.00 | 04/EE/EI.D.5/DDA/2000-2001 | M/s Bharat Electric Co. | 20-04-2000 24 Months | Yes | 80% | 15.41 |
| 7. | C/o 1760 Janta houses at Pkt. B, Sect. 16-B, DWK, Ph. II, SH : IEI of 352 Janta Houses at Sect. 16-B, DWK. Ph. II, Gr. I. | 1822304.00 1695199.00 | 09/EE/EI.D.5/DDA/2000-2001 | M/s Bharat Electric Co. | 08-06-2000 24 Months | Yes | 80% | 15.24 |

| S. No. | Name of Scheme | Estt. / Tender Cost | Agent No. | Agency | Date of Start Time of comp. (Period) | Supplementary Agmt. if drawn | Physical Progress % of Allotment | Payment Made upto date (in lacs) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 8. | C/o 1760 Janta Houses (Four storeyed) at Pkt B., Sect. 16-B, DWK. Ph. II. SH : IEI of 448 Janta houses at Sec. 16-B, DWK. Ph. II, Gr. II | 2327628.00 2076766.00 | 55/EE/EI.D.5/DDA/99-2000 | M/s Goel Electric Works | 28-02-2000 24 Months | No | 70% | 11.58 |
| 9. | C/o 1760 Janta Houses (For storeyed) at Sect. 16-B, Pkt B, Sect. 16-B, DWK. Ph. II SH: IEI of 352 Janta Houses at Sector 16-B, DWK, Ph. II, Gr. II | 2489165.00 1960724.00 | 02/EE/EI.D.5/DDA/2002-2003 | M/s Bharat Electric Co. | 23-05-02 24 Months | Yes | 80% | 9.57 |
| 10. | C/o 1760 Janta houses (Four storeyed) at Sect. 16-B, Pkt. B, DWK. Ph. II. SH : IEI of 480 Janta Houses at Sec. 16-B, Pkt. B, DWK. Ph.II i/c Int. Dev. In Gr. IV. | 2489165.00 2069419.00 | 26/EE/EI.D.5/DDA/01-02 | M/s Rajdhani Associates | 09-01-02 24 Months | No | 70% | 9.00 |

| S. No. | Name of Scheme | Estt. / Tender Cost | Agent No. | Agency | Date of Start Time of comp. (Period) | Supplementary Agmt. if drawn | Physical Progress % of Allotment | Payment Made upto date (in lacs) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 11. | C/o 620 LIG houses (Five storeyed) i/c Int. Dev. i.e. water supply, Sewerage, roads & SW Drains in MLU Pkt. 4, Sec. 11, DWK, Ph. I. SH : S/I of clear water P/sets & DG set. | 1239022.00 1158846.00 | 21/EE/EI.D.5/DDA/06-07 | M/s K.R. Pumps & Engg. (P) Ltd. | 29-09-06 4 Months | No | 90% | 6.94 |
| 12. | C/o 4100 SRT in Pkt. I & II Sect. 16-B, Dwarka (SH: IEI of 448 SRT in Pkt. I, Sect. 16-B, DWK. Ph. II Gr.I | 2375464.00 2185090.00 | 32/EE/EI.D.5/DDA/99-2000 | M/s Metro Elect. Co. | 22-11-99 30 Months | Yes | 50% | 18.40 |
| 13. | C/o 4100 SRT in Pkt. I & II Sect. 16-B, DWK. (SH: IEI of 400 SRT in Pkt. I, Sect. 16-B, DWK. Ph. II, Gr. I ) | 2375464.00 2185090.00 | 33/EE/EI.D.5/DDA/99-2000 | M/s Metro Elect. Co. | 22-11-99 30 Months | Yes | 80% | 18.09 |
| 14. | C/o 4100 SRT in Pkt. I & II Sect. 16-B, DWK. (SH: IEI of 400 SRT in Pkt. I, Sect. 16-B, DWK. Ph. II, Gr. III. | 2120950.00 1950973.00 | 34/EE/EI.D.5/DDA/99-2000 | M/s Metro Elect. Co. | 22-11-99 30 Months | Yes | 95% | 16.41 |

| S. No. | Name of Scheme | Estt. / Tender Cost | Agent No. | Agency | Date of Start Time of comp. (Period) | Supplementary Agmt. if drawn | Physical Progress % of Allotment | Payment Made upto date (in lacs) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 15. | C/o 4100 SRT in Pkt. I & II Sect. 16-B, Dwarka (SH: IEI of 320 SRT in Pkt. I, Sect. 16-B, DWK. PH. I Gr. IV. | 1696760.00 1560779.00 | 35/EE/EI.D.5/DDA/99-2000 | M/s Metro Elect. Co. | 22-11-99 30 Months | Yes | 70% | 13.46 |
| 16. | C/o 4100 SRT in Pkt. I & II Sect. 16-B, DWK. (SH: IEI of 320 SRT in Pkt. I, Sect. 16-B, DWK. Ph. I Gr. IV) | 2375464.00 2184232.00 | 37/EE/EI.D.5/DDA/99-2000 | M/s Bharat Electric Co. | 22-11-99 30 Months | Yes | 80% | 18.51 |
| 17 | C/o 4100 SRT in Pkt. I & II Sect. 16-B, DWK (SH: IEI of 288 SRT in Pkt. II Sect. 16-B, DWK. PH I, Gr. VIII) | 2545140.00 2340249.00 | 39/EE/EI.D.5/DDA/99-2000 | M/s Bharat Electric Co. | 22-11-99 30 Months | Yes | 80% | 19.93 |
| 18 | C/o 4100 SRT in Pkt. I & II Sect. 16-B, Dwarka (SH : IEI of 288 SRT in Pkt. II Sect. 16-B, DWK.Ph.II Gr. IX) | 1527084.00 1406685.00 | 40/EE/EI.D.5/DDA/99-2000 | M/s Prominent Electric Works | 22-11-99 24Months | Yes | 80% | 11.31 |

| S. No. | Name of Scheme | Estt. / Tender Cost | Agent No. | Agency | Date of Start Time of comp. (Period) | Supplementary Agmt. if drawn | Physical Progress % of Allotment | Payment Made upto date (in lacs) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 19 | D/o 1769.88 Hact. Of land at Pappan Kalan Dwarka Project Ph. I i/c alternative plots around village Amberhai Bagdola & Manglapuri. (SH:S/E/T/C of Sub. Stn. Equipments at CT-1, Sect. 7, Dwarka, Ph.I) | 9848520.00 9548811.00 | 30/EE/EI.D.5/DDA/02-03 | M/s Shiv Electric | 13-10-02 9 Months | No | 95% | 85.00 |
| 20 | C/o 304 MIG houses Sect. 17, Pkt. E, DWK. Ph. II SH: IEI of 152 MIG houses in Gr. I | 1650591.00 1294129.00 | 25/EE/EI.D.5/DDA/06-07 | M/s Bharat Electric Co. | 16-8-98 30 Months | Yes | 85% | 10.51 |
| 21 | C/o 304 MIG Houses Sect. 17, Pkt. E, DWK. Ph. II SH: IEI of 152 MIG houses in Gr. I | 1650591.00 1317332.00 | 33/EE/EI.D.5/DDA/06-07 | M/s Bharat Electric Co. | 28-12-97 30 Months | Yes | 85% | 10.65 |
| 22 | C/o 792 MIG houses in Sect. 17, Pkt. A DWK. Ph. II (SH: IEI of 96 MIG houses in Gr. I) | 1093890.00 857747.00 | 35/EE/EI.D.5/DDA/06-07 | M/s Bharat Electric Co. | 15-03-99 30 Months | Yes | 85% | 7.50 |

| S. No. | Name of Scheme | Estt. / Tender Cost | Agent No. | Agency | Date of Start Time of comp. (Period) | Supplementary Agmt. if drawn | Physical Progress % of Allotment | Payment Made upto date (in lacs) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 23 | C/o 792 MIG houses in Sect. 17 Pkt. A DWK. Ph II (SH: IEI of 224 MIG houses in Gr. II). | 2543301.00 1993548.00 | 27/EE/EI.D.5/DDA/06-07 | M/s Bharat Electric Co. | 26-01-98 30 Months | Yes | 80% | 16.56 |
| 24 | C/o 792 MIG houses in Sect. 17, Pkt. A DWK. PH. III (SH: IEI of 216 MIG houses in Gr. III). | 2459894.00 1928634.00 | 29/EE/EI.D.5/DDA/06-07 | M/s Bharat Electric Co. | 26-08-98 30 Months | Yes | 90% | 16.58 |
| 25 | C/o 792 MIG houses in Sect. 17, Pkt. A DWK. Ph. II (SH: IEI of 256 MIG houses in Gr. IV). | 2914114.00 2284187.00 | 31/EE/EI.D.5/DDA/06-07 | M/s Bharat Electric Co. | 26-01-98 30 Months | Yes | 80% | 18.83 |

3.	Fire Fighting equipments

Locations 		1)	440 HIG (368 Cat-III & 72 Cat-II)

Multistoreyed houses in Sector 19-B, Dwarka

Equipments:-		(a)	Fire Pumping set and Diesel driven fire pump set.

- Wet Risers

- Fire-extinguishers

- Fire Alarm

- PA system

- 568 HIG (520 Cat - III & 48 Cat – II)

Multistoreyed houses DU’s at Sector 18-B, Dwarka.

Equipments :-		(a)	Fire Pumping sets and  Diesel driven fire pump set

- Wet-Risers

- Fire-extinguishers

- Fire Alarm

(e)	P.A. System