DELHI DEVELOPMENT AUTHORITY

PROGRESS REPORT OF WORKS IN VARIOUS DIVISIONS UNDER NORTH ZONE (WD-5)

As on : 30.11.2007

| S.No. | Name of Scheme | Status of A/A & E/S (Fig. in Lacs of Rupees) | E.C. T.C. | D.O.S. D.O.S. | Budget (in Lacs) | Expdr. Upto 31.07.07 (In Lacs) | Physical progress %age upto prev. month | Progress %age during current month | Total progress %age | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 |
| 1 | D/o Distt. Centre at Rajindra Place (Balance dev. & constn. Work) SH:- C/o Parking lot ‘D’) | Accorded for 464.23 Lacs | 83.42 87.14 | 09.02.06 08.08.06 | 150.00 Lacs | 94.13 | 90% | 2% | 92% |  |
| 2 | M/o completed schemes of Nazul A/c-II under SWZ. | A/R & M/O | — | — | 150.00 |  |  |  |  |  |
| (i) | SH: P/F G.l. barbed wire fencing along proposed passage for local people of Dasghara Village & Constn. Of wicket gates. | — | 1.36 1.41 | 10.07.07 09.08.07 | — | — | 60% | – | 60% | Show came notice under clause 3 issued |
| (ii) | SH: Modification of boundary wall raising and repairing etc. along main road at Satya Park, Naraina Industrial Agrea Phase-II. | – | 5.65 6.57 | 08.12.07 07.03.08 | – | – | – | – | – | Work recently awarded |

| S.No. | Name of Scheme | Status of A/A & E/S (Fig. in Lacs of Rupees) | E.C. T.C. | D.O.S. D.O.S. | Budget (in Lacs) | Expdr. Upto 31.07.07 (In Lacs) | Physical progress %age upto prev. month | Progress %age during current month | Total progress %age | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 |
| 3. | M/o Vikas Minar | A/R & M/O | — | — | 300.00 Lacs | 110.05 |  |  |  |  |
| i. | SH: Cleaning & mopping of toilets, pantries, spittoons, dustbin, stair case, corridors, etc. of Vikas Minar | — | 2.99 4.74 | 30.11.07 29.05.08 | — |  | – | 1% | 1% | Work recently awarded |
| ii. | SH:- Replacement of basement flooring for parking at Vikas Minar. | — | 12.36 18.41 | 14.10.06 13.04.07 | — | — | 18% | 0% | 18% | Notice under Clause 3 has been issued. |
| iii. | SH:- Alternation of existing partition frame of CE(NZ), Director (Narela) and Director (UD). | — | 4.67 4.05 | 23.11.07 22.12.07 | — | — | — | 20% | 20% | Work recently awarded |
| Iv. | M/o Vikas MInar SH: Repair of door closer and springs | – | 0.79 1.00 | 20.10.07 19.04.08 | – | – | – | – | – |  |
| v. | M/o Vikas Minar SH: Minor repairs, oil bound distemper, painting work etc. on low and high partitions of office spaces at Vikas Minar from basement to 21st floor. | – | 6.30 4.14 | 20.10.07 29.01.08 | – | – | – | 10% | – | Work recently awarded |
| vi. | SH: Repairing and cleaning of existing, venation blinds (Horizontal & Vertical) and refixing at various floor at Vikas Minar. |  | 1.55/ 0.99 | 10.12.07 09.03.08 | – | – | – | – | – | Work recently awarded |
| 4. | Special repairs at Vikas Minar | Accorded for Rs. 102.43 lacs | — | — | 100.00 lacs |  |  |  |  |  |
| (i) | SH: Rehabilitation of RCC columns & beams & other RCC members of Vikas Minar | — | 58.49 69.97 | 15.07.07 14.04.08 | — | — | 4% | 5% | 9% |  |
| 5. (i) | M/o Vikas Kuteer SH:- Scavenging & cleaning of office bldg., open area & toilets at Vikas Kuteer. | A/R & M/O — | 0.40 0.56 | 01.06.07 30.11.07 | 10.00 Lacs — | — | 60% | 40% | 100% |  |
| 6. (i) | M/o completed scheme (shops) under North Zone. SH: Cleaning and sweeping of Pizza parking open spaces at Distt. Centre Rajindra Place. | A/R & M/O | 0.99 1.48 | 25.10.07 14.06.08 | -do- | – | – | 15% | 15% |  |
| 7. | M/o completed scheme Nazul A/c-I of SWZ. | -do- |  |  |  |  |  |  |  |  |
| (i) | SH: Annual repairing and maintenance of officers flats at Bhagwan Dass Road. | -do- | 9.52 10.94 | 23.11.07 22.02.08 | - | - | - | 7% | 7% |  |
| 8. | A.R. & M/O Staff quarters at Rajinder Nagar. |  |  |  |  |  |  |  |  |  |
| (i) | SH:Supply of materials at Staff Quarters Rajinder Nagar. | -do- | 1.50 1.36 | 25.11.07 24.12.07 | - | - | - | 50% | 50% |  |
| (ii) | SH : White washing, painting, distempering at DDA staff quarters, Rajinder Nagar | -do- | 5.81 3.97 | 8.12.07 07.02.07 |  |  |  |  |  |  |

Executive Engineer

WD-5/DDA