(SOUTH WEST ZONE)

# MAJOR  PROJECTS   HELD   UP   DUE   TO   COURT   CASE   UPTO   JULY-2007

| S.No. | Name of Work | Court Case No. | Respective Court | Date of next hearing | Remarks |
| --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 |
| 1 | D/O Therapy Park near Safdarjung Hospital ## SWD-1 |  | Supreme Court |  | Project already placed in EAC meeting on approved in 72 meeting out of 31 Acres of land, 2 Acres is under stay & 29 Acres cases in Court. |

(SOUTH WEST ZONE)

# PRESENT   STATUS   OF   WORK   UPTO   JULY-2007

| S.No. | Name of Work | A/A & E/S | Present Progress | Remarks |
| --- | --- | --- | --- | --- |
| 1 | C/o Mega Housing Project (2304/2252 HIG/MIG/LIG) at Vasant Kunj, Sec.D,Pkt.6 i)Group-I(252 HIG +104 MIG+120 LIG ## SWD-1 | Rs. 2208.07 lacs | 16.5% | Tenders have been received in being sent to WAB for award. |
|  | ii) Group-II(252 HIG +104 MIG +120 LIG ## SWD-4 |  | 13% | Tenders have been received in being sent to WAB for award. |
|  | iii) Group-III(252 HIG +104 MIG +120 LIG ## SWD-2 |  | 10% | Tenders have been received in being sent to WAB for award. |
|  | iv) Group-IV(252 HIG +104 MIG +120 LIG ## SWD-2 |  | 11% | Tenders have been received in being sent to WAB for award. |

( SOUTH WEST ZONE)

PRESENT   STATUS   OF   WORK  UPTO   JULY-2007

| S.No. | Name of Work | A/A & E/S | Present Progress | Remarks |
| --- | --- | --- | --- | --- |
| 2 | ### MEGA HOUSING C/o 436 MIG/LIG houses at Vasant Kunj at Mehrauli Mahipalpur Road near Spinal Injury Hospital. a)311 MIG, 125 LIG ## SWD-1 | Rs. 7724 lacs Rs. 4731.00 lacs | 3% | Tenders have been received in being sent to WAB for award. |
|  | ### b)C/o 416 HIG multi four storeyed houses Vasant Kunj at Mehrauli Road near Sultangarhi Tomb ## SWD-4 |  | 2% | Tenders have been received in being sent to WAB for award. |
| 3 | C/o 850 Mass Housing (170 HIG, 340 MIG & 340 LIG) at Vasant Kunj near Sultan- garhi on Turnkey basis (actual no. of houses to be const -ructed 795 No. (140 HIG,350 MIG & 305 LIG SWD-2 |  | 80% | Work held up on a/c of external electrification. |
| 4 | C/O 160 HIG at Vasant Kunj Sec.B, Pkt.2 - 72 HIG,Gr-I b) 64 HIG,Gr.II (SWD-4) | Rs. 807 lacs |  | Work just started |

( SOUTH WEST ZONE )

# PRESENT   STATUS   OF   WORK  UPTO  JULY-2007

| S.No. | Name of Work | A/A & E/S | Present Progress | Remarks 5 |
| --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 |  |
| 5 | C/o 860/830 two room houses with Lounge on the East side of Pkt. D-6 at Vasant Kunj i/c internal dev. (Civil & Elect.) 290 DU’s Gr.I 270 DU’s Gr.II 270 DU’s Gr.III ## SWD-4 | Rs. 2848 lacs | 39.05% 41% 27% | #### Work in Progress upto July-2007 |
| 6 | D/O land in West of JNU, Vasant Kunj Phase-II ii) C/o 12 lacs capacity of UGR & pump house (Balance Work) ## SWD-4 | Rs. 8376.62 lacs | 95% | Work in Progress upto July-2007 |

( SOUTH WEST ZONE)

# PRESENT   STATUS   OF   WORK  UPTO   JULY-2007

| S.No. | Name of Work | A/A & E/S | Present Progress | Remarks 5 |
| --- | --- | --- | --- | --- |
| 7 | C/o 362 (268 MIG + 94 LIG) houses at Vasant Kunj near Sultangarhi Eight Storeyed ## SWD-1 | Rs.29,90,36/- lacs |  | Tenders have been called. |
| 8 | LSC at Sector-A, Pkt. B & C, Vasant Kunj |  |  | The drawing has been received and all the services in the said area are available |
| 9 | LSC at Sector-D, Pkt. 2, Vasant Kunj |  |  | The scheme has been approved by the Screening Committee as per inquiries from (LM). |
| 10 | LSC in Sector D-6 Vasant Kunj |  |  | Revised drawing has been issued by ACA-II has been prepared by this office and sent to EM office and Director (Finance) on 24.1.2007. |

( SOUTH WEST ZONE )

# DETAILS   OF   PENDING    FINAL   BILLS   UPTO   JULY-2007

| S. N | Name of Work/Agreement No. (SWD-2) | Name of Agency | Estimated Cost/ Tendered Cost | Actual date of Completion | Due Date of Final Bill | Target date for finalizing pending bills/Reasons |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 |
| 1 | C/o 1008 DUs under SFS houses in Sec.C, Pkt.IV, Vasant Kunj. SH: C/o 88 Cat.III, 66 Cat.II & 110 S/Grgs., Gr.V at Vasant Kunj (Alt. Site Sec.C, Pkt.1). Agmt. No.15/EE/HD.X/84-85 | M/s. S.P. Dhawan & Assoc. (P) Ltd. | ##### Rs.120,76,036/- Rs.181,74,434/- | 19.1.90 | 19.7.90 | Bill finalized in March-2007. |
| 2 | C/o 340 DUs under SFS in Sec.C, Pkt.IV, Vasant Kunj. SH: C/o 102 Cat.III, 68 Cat.II & 102 S/Grgs. at Gr.I Agmt.No.38/EE/HD.XXI/84-85 | M/s. Globe Construction Co. | ##### Rs.133,00,973/- Rs.200,31,265/- | 30.9.89 | 30.3.90 | QC paras pending and EIS yet to be approved from Competent Authority |
| 3 | D/o land in West of JNU at Vasant Kunj Phase-II. SH: C/o peripheral SW drain in constraint area part-I. Agmt.No.75/EE/SWD-2/0102 | M/s. Tomar Construction Co. | ##### Rs. 498,00,330/- Rs. 509,42,365/- | 5.2.2007 | 5.8.2007 | QC/CTE paras pending & BOT case to be decided by the Competent Authority. |

( SOUTH WEST ZONE )

# DETAILS   OF   PENDING    FINAL   BILLS   UPTO   JULY-2007

| S. N | Name of Work/Agreement No. | Name of Agency | Estimated Cost/ Tendered Cost | Actual date of Completion | Due Date of Final Bill | Target date for finalizing pending bills/Reasons |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 |
| 1 | (SWD-1) C/o 152 SFS Cat.II houses in Sect.D, Pkt.6, Vasant Kunj in Gr.I Agmt. No.7/EE/SWD-1/DDA/ 97-98 | M/s. Naresh Kapoor | ##### Rs. 353,02,575/- Rs. 3,51,96,220/- | 30.6.2001 | 30.7.2005 | 31.8.2007 Due to non finalization of deviation statement by the competent authority |
| 2 | (SWD-1) C/o 152 SFS Cat.II houses in Sect.D, Pkt.6, Vasant Kunj in Gr.II Agmt. No.6/EE/SWD-1/DDA/ 97-98 | M/s. Naresh Kapoor | ##### Rs. 3,51,00,117/- Rs. 3,51,67,768/- | 30.6.2001 | 30.7.2005 | 31.8.2007 Due to non finalisation of deviation statement by the Competent Authority |

###### REGARDING LIST OF COURT CASE IN SOUTH WEST ZONE

| S. N | Case Title/Party Name | File No. | Suit No. | Name of division | Name of Court | Name of P/L | Last date of hearing | Next date of hearing | Status of the Case |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |
| 1 | C/o SFS houses at Sheikh Sarai Pkt.C, SH: C/o 84 Cat.II & 42 Cat.II, B-Type houses i/c Internal Development M/s. Bhai Sardar Singh & Sons | F21(219)01/HC/ Legal | 1945-A/2000 | SWD-1 | High Court | Bhupesh Narula | 8.5.2007 | 30.7.2007 | Demanding more interest award |
| 2 | C/o SFS houses at Sheikh Sarai Pkt.C, SH: C/o 84 Cat.II & 42 Cat.II, B-Type houses i/c Internal Development M/s. Bhai Sardar Singh & Sons | F21(219)01/HC/ Legal | Recovery Suit | SWD-1 | High Court | Rajeev Bansal 9110114141 | 15.6.2007 | September-2007 | ---do--- |
| 3 | C/o 630 SFS houses in Sec.B, Pkt.5 & 6, Vasant Kunj SH: 50 houses & 30 Cat.III, 20 Cat.II) & 30 S/Grgs in Gr.V M/s. S.S. Jetly. | F11(86)04/Arbn./ Legal F61(133)/SWD-1/ 89-90/Arbn. | 419/04 | SWD-1 | High Court | Since Shri Arvind Nayyar | 22.5.2007 | 13.7.2007 | ---do--- |
| 4 | C/o 55 houses in (33 Cat.III, 22 Cat.II) & 33 S/Gs in Gr.IV M/s. S.S. Jetly | F11(85)/04/Arbn./ Legal | 347/04 | SWD-1 | High Court | Sh. Gaurav Sareen | 22.5.2007 | 13.7.2007 | ---do--- |

###### REGARDING LIST OF COURT CASE IN SOUTH WEST ZONE

| S. N | Case Title/Party Name | File No. | Suit No. | Name of division | Name of Court | Name of P/L | Last date of hearing | Next date of hearing | Status of the Case |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |
| 5 | D/o land at Vasant Kunj Sec.B. SH: Raising of 30 m road between Pkt.IV, Sec.B, Vasant Kunj | F21(219)01/HC/ Legal | 1945-A/2000 | SWD-1 | High Court | Bhupesh Narula |  |  | As per Penal Lawyer dated 10.10.2002 suit was disposed off. |
| 6 | C/o SFS houses at Sheikh Sarai –II, Pkt. B& C SH: M.S. Grill to window, MS park railing RCA drain etc. | F60(8)99/00/ SWD-1/DDA | OMP No.99/3 | SWD-1 | High Court | Pawan Mathur | 18.5.2007 | 29.7.2007 | ---do--- |
| 7 | C/o 852 HIG/MIG/LIG houses at Vasant Kunj at Mehrauli Mahipalpur road Sultangarhi Tomb.. M/s. EPI | F21(37)/05/HC/ Legal | IA No.486/05 in CS(OS)75/ 05 | SWD-1 | High Court | Gaurav Sareen | 22.5.2007 | 20.11.2007 | ---do--- |
| 8 | C/o 160 & 120 DUs under SFS at Vasant Kunj, Sec.D, Pkt.3, Gr.I & IV. SH: Dry brick as flooring on road berms & parks M/s. Kripal Singh Ahluwalia | F21(126)/01/HC/ Legal | 1779/2000 | SWD-1 | High Court | Pavan Malhotra | 6.8.2007 | Case admitted | ---do--- |
| 9 | C/o Mega Houses Projects (2304 HIG/MIG/LIG houses behind Pkt.D-6, Vasant Kunj. SH: C/o 240 HIG, 104 MIG, 120 LIG multistoreyed houses in Gr.I Agmt. No.17/EE/WD-1/DDA/ 01-02 M/s. Ahluwalia Contracts (India) Ltd. | F21(18)/05/HC/ Legal | CS(OS)/109/ 2005 | SWD-1 | High Court | Vibhu Shanker | 10.1.2007 | 31.8.2007 | Demanding more interest on award. |

###### REGARDING LIST OF COURT CASE IN SOUTH WEST ZONE

| S. N | Case Title/Party Name | File No. | Suit No. | Name of division | Name of Court | Name of P/L | Last date of hearing | Next date of hearing | Status of the Case |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |
| 10 | C/o Mega Houses Projects (2304 HIG/MIG/LIG houses behind Pkt.D-6, Vasant Kunj. SH: C/o 240 HIG, 104 MIG, 120 LIG multistoreyed houses in Gr.III Agmt. No.19/EE/WD-5/DDA/ 01-02 M/s. Ahluwalia Contracts (India) Ltd. | F21(22)/05/HC/ Legal/Pt.I | 1371/2005 | SWD-1 | High Court | Jagmohan Sabharwal with CM Rao & B.D. Sharma | 10.1.2007 | 25.9.2007 | Demanding more interest on award. |
| 11 | C/o 96 SFS houses Cat.II, & Cat.III at Kishangarh, Pkt.B comprising 48 cat.II, 48 cat.III & 72 S/gs i/c Internal Development M/s. Shilpa Engg. Services | F11(73)04/Arbn./ TC/Legal | 565/04 | SWD-1 | Tis Hazari | Sh. Sanjay Sharma 9833203330 | 23.7.2007 | 5.9.2007 | ---do--- |
| 12 | C/o 1 No. Underground water tank of 1 MG capacity in Sector-B, Vasant Kunj M/s Raj Bros. | F2(349)/95/PC/ Legal | 1070/95 | SWD-1 | Patiyala House | Smt. Promila Kapoor | 2.8.2007 | 13.11.2007 | ---do--- |
| 13 | D/o land at Vasant Kunj, Sec.A. SH: Road cutting of road & drain M/s. Brij Lal & Sons | F10(124)/00/TC/ Legal | 73/03 | SWD-1 | Tis Hazari | S.D. Sharma | 9.3.2007 | Under regular hearing | ---do--- |
| 14 | D/o land at Vasant Kunj, Sec.A. SH: Road cutting of road & drain M/s. Brij Lal & Sons | F10(124)/00/TC/ Legal | 1002/2006 | SWD-1 | Tis Hazari | K.D. Sharma | 19.7.2007 | Final argument | ---do--- |

###### REGARDING LIST OF COURT CASE IN SOUTH WEST ZONE

| S. N | Case Title/Party Name | File No. | Suit No. | Name of division | Name of Court | Name of P/L | Last date of hearing | Next date of hearing | Status of the Case |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |
| 14 | C/o 400 houses Pkt.C at Kishangarh. SH: C/o 144 houses Cat.III, Pkt.-C, Kishangarh,72 Cat.III & 72 Cat.II. M/s. P.C. Sharma & Co. | F11(85)04/Arbn./ Legal | 524/04 | SWD-1 | Tis Hazari | Smt. Promila Kapoor | 2.5.2007 | 22.8.2007 | Demanding more interest on award. |
| 15 | C/o 630 SFS houses Sec.B, Pkt.5 & 6, Vasant Kunj. SH: C/o 50 houses (30 Cat.III, 20 Cat.II) & 30 S/Gs. in Gr.X in Pkt. B & C, Vasant Kunj M/s. K.R. Builders Pvt. Ltd. | F11(76)04/TC/ Legal | 1351/06 | SWD-1 | Tis Hazari | Sh. Bhupesh | 3.7.2007 | 20.3.2008 | ---do--- |
| 16 | C/o 944 SFS houses at Kishangarh, Sec.A, Pkt.C. SH: C/o 192 SFS (96 Cat.III, 96 Cat.II & 144 S/Grgs. Gr.II M/s. Uppal Engg. Constn. Co. | F2(1253)91/HC/ Legal | 2831/91 | SWD-2 | High Court | M/s. A Salwan | --- | 22.8.2007 | Reply filed, hearing in progress |
| 17 | C/o 228 SFS at Hauz Khas Mehrali Road, New Delhi SH: C/o 126 3 bed, 84 2 bed, 84 Servant Qtrs., 52 Car Garrages & 98 S/Grs. Gr.I M/s. Republic Construction Co | F2(110)95/HC/ Legal F2(102)05/HC/ Legal | 158/95 154/94 | SWD-2 | High Court | Sh. Anil Sapra | --- | 26.11.2007 | Reply filed, hearing in progress |
| 18 | C/o 64 Cat.III, 48 Cat.II flats & 80 S/Grgs. at Sec.B, Pkt.1, Vasant Kunj, Gr.IV M/s. S. Bedi Constn. Co. | F2(923)91/HC/ Legal F2(602)97/HC/ Legal | LPA/2006 X N0.23/06 | SWD-2 | High Court | Execution Case | --- | Main case disposed off on 12.9.06 fresh appeal file N.D.H. 10.7.2007 | Reply filed, hearing in progress |

###### REGARDING LIST OF COURT CASE IN SOUTH WEST ZONE

| S. N | Case Title/Party Name | File No. | Suit No. | Name of division | Name of Court | Name of P/L | Last date of hearing | Next date of hearing | Status of the Case |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |
| 19 | C/o 228 SFS houses at Hauz Khas Gr.II Agmt. No.7/HD-VIII/81-82 M.s S.K. Aggarwal | F2(923)/91/HC/ Legal/ F2(207)/97/HC/ Legal/ | 1320A/91 Ex 170/97 | SWD-2 | High Court | A. Salwan | --- | 26.9.2007 | Reply filed, hearing in progress. |
| 20 | C/o 850 Mass Housing (170 HIG, 340 MIG, 340 LIG) at Vasant Kunj, Near Sultangarhi on Turnkey Basis Agmt. No.18/EE/SWD-2/DDA /01-02 M/s. Ahluwalia Constn. Co | F21(90)06/HC/ Legal | 5653/2006 | SWD-2 | High court | A. Salwan | --- | Case has been reserved for judgement on 7.12.2006 | Reply yet to be filed |
| 21 | C/o 12 Cat.III, 9 Cat.II SFS houses in Sec.C, Pkt.3, Vasant Kunj. Agmt.No.67/SWD-8/A/91-92 M/s. Manoj Builders | F11(10)04/Arbn/ TC/Legal | 48/2004 | SWD-2 | Tis Hazari | Ms. Promila Kapoor | --- | 15.11.2007 | Reply filed, hearing in progress |
| 22 | C/o SFS houses in Sec.B, Pkt.10, Vasant Kunj SH: C/o 24 Cat.III, 24 Cat.II & 26 s/Grs. I/c W/S, S/I & Int. dev. of Sec.B, Pkt.6&7, Vasant Kunj (Earlier Pkt.10) Agmt.No.29/EE/SWD-2/92-93 Sh. Naresh Kapoor | F9(110)04/TC/ Legal | CM(M)No. 2552/05 | SWD-2 | Tis Hazari | H.K.L. Sehgal | --- | 18.9.2007 | Reply filed, hearing in progress |

###### REGARDING LIST OF COURT CASE IN SOUTH WEST ZONE

| S. N | Case Title/Party Name | File No. | Suit No. | Name of division | Name of Court | Name of P/L | Last date of hearing | Next date of hearing | Status of the Case |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |
| 23 | C/o 680 SFS at Vasant Kunj, Sec.B, Pkt.10. SH: C/o 90 Cat.III, 90 Cat.II flats & 135 S/grs. Vasant Kunj, Gr.II Agmt. No.43/HD-8/79-80 M/s. S & S Builders (P) Ltd. | F21(58)/98/HC/ Legal/ | 2198A/97 | SWD-2 | High Court | A. Salwan | --- | 18.9.2007 | Reply filed, hearing in progress. |
| 24 | C/o LSC at Wazir Pur, Ph.I Block-F Agmt No.266/HD.VIII/76-77 M/s. A.R. Khanna & Sons | F2(1228)93/HC/ Legal | 1781/94 | SWD-2 | High Court | A. Salwan | --- | As per decision of Arbitration scrutiny before case is under process. | Case disposed off on 24.1.2006 |
| 25 | C/o 96 Cat.III, 64 Cat.II & 96 S/Grs. Sec.B, Pkt.1 Gr.V, Vasant Kunj. Agmt.No.15/HD-XXI/A/84-85 M/s. S. Bedi Constn. Co. | F2(21)02/HC/ Legal | 2898A/96 | SWD-2 | High Court | A. Salwan | --- | Reply filed, hearing in progress. | Appeal admitted in 24/2002 but further date not yet fixed as intimated by P/L |
| 26 | P/L Rising Main from Vasant Kunj Ph.II to Ghitorni STP SH: Rising main from RD-0 to 3400 from SPS to T-Junction at Mehrauli Mahipalpur Road Gr.I Agmt.No.3/SWD-2/99-2000 M/s. Y.D. Builders & Hotel (P) Ltd. | F21(183)02/HC/ Legal | 1450/2002 | SWD-2 | High Court | Sh. Gaurav Sareen | --- | 17.8.2007 | Reply filed, hearing in progress. |

###### REGARDING LIST OF COURT CASE IN SOUTH WEST ZONE

| S. N | Case Title/Party Name | File No. | Suit No. | Name of division | Name of Court | Name of P/L | Last date of hearing | Next date of hearing | Status of the Case |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |
| 27 | P/L Rising Main from Vasant Kunj Ph.II to Ghitorni STP SH: P/L Rising Main from RD-3400 to 7300 from T-Junction at Mehrauli Mahipalpur Road to STP Ghitorni Gr.II. Agmt.No.43/SWD-2/99-2000 M/s. Y.D. Builders & Hotel (P) Ltd. | F21(183)02/HC/ Legal | 48/2004 | SWD-2 | High Court | Sh. Gaurav Sareen | --- | 17.8.2007 | Reply filed, hearing in progress |
| 28 | C/o 120 DUs SFS & 90 S/Grs. in Sec.D, Pkt.3, Gr.III,V. Kunj. Agmt. No.10/30/HD.16/84-85 M/s. K.R. Builders (P) Ltd. | F21(107)03/TC/ Legal | EX.28/2003 | SWD-2 | Tis Hazari | Ms. Geeta Mehrotra | --- | 27.9.2007 | ---do--- |
| 29 | C/o 160 DUs SFS & 120 S/Grs. Sec.D, Pkt.III, Gr.II, Vasant Kunj Agmt.No.9/29/HD.16/84-85 M/s. K.R. Builders (P) Ltd. | F21(127)03/HC/ Legal | Ex.123/2002 | SWD-2 | High Court | Ms. Geeta Mehrotra | --- | 27.9.2007 | ---do--- |
| 30 | C/o 630 SFS houses & 378 S/Grs. at Sec.B, Pkt. 5 & 6, Vasant Kunj. SH: C/o 60 houses & 36 S/Grs. at Sec.B, Pkt. 5 & 6, Gr. IX, V. Kunj. Agmt. No.31/SWD03/88-89 M/s. K.R. Builders (P) Ltd. | F21(266)06/HC/ Legal | EX 9/2004 | SWD-2 | High Court | Sh. Arvind Nayyar | --- | Case disposed of on 30.3.2000. Now under process of decision of security. | ---do--- |

###### REGARDING LIST OF COURT CASE IN SOUTH WEST ZONE

| S. N | Case Title/Party Name | File No. | Suit No. | Name of division | Name of Court | Name of P/L | Last date of hearing | Next date of hearing | Status of the Case |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |
| 31 | C/o 78 Cat.III, 78 Cat.II flats & 170 S/Grs. etc. under SFS at V.Kinj, Sec.B, Pkt.9, Gr. II Agt.No.41/EE/HD-VIII/84-85 M/s. Saraswati Constn. Co. | F21(266)06/HC/ Legal | EA-2/05 in Ex.144/03 | SWD-2 | High Court | Sh. Pawan Mathur |  | 06.07.2007 | Reply filed, hearing in progress |
| 32 | C/o SFS houses at Basant Vllage. SH: C/o 4 3bed room, 44 Car/Grs., 88 Servant Qtrs.i/c int. W/Supply, Drainage Instts. Ag.No.88/EE/SWD-7/89-90/A M/s. M.N. Arora | F21(56)06/HC/ Legal | OMP 69/2006 | SWD-2 | High Court | Sh Bhupesh Narula |  | Case reserved for judgement on 7.2.2007 | Reply yet to be filed, hearing in progress. |
| 33 | C/o 288 Janta houses for landless & Harizans at Basant Village i/c int. development. Ag.No.88/EE/SWD-7/89-90/A M/s. Pt. Munshi Ram & Associates (P) Ltd. | F21(142)/05/HC/ Legal | OMP 273/2005 | SWD-2 | High Court | Sh. D.S. Mahendroo | --- | 6.9.2007 | Reply filed, hearing in progress |

###### REGARDING LIST OF COURT CASE IN SOUTH WEST ZONE

| S. N | Case Title/Party Name | File No. | Suit No. | Name of division | Name of Court | Name of P/L | Last date of hearing | Next date of hearing | Status of the Case |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |
| 35 | ### SWD-4 C/o 416 houses at Alakhnanda opp. Tara Apartment. SH: C/o 193 houses Cat.II M/s. Jagat Ram Trehan & Sons | F21(119)97/HC/ Legal | 498/A/97 AAO No. 463/2006 | SWD-4 | High Court | Sh. Ashutosh Sharma | --- | 9.10.2007 | In progress |
| 36 | ### C/o 944 houses under SFS at Kishangarh Pkt.C. SH: C/0 192 houses (96 cat.III & 96 Cat.II & 144 S/Gs Gr.IV 13/HD-XXI/82-83 |  | PAO No. 78/2006 | SWD-4 | High Court | Sh. A. Salwan | --- | 26.9.2007 | In progress |
| 36 | ### C/o 944 houses under SFS at Kishangarh Pkt.C. SH: C/0 192 houses (96 cat.III & 96 Cat.II & 144 S/Gs Gr.V 13/HD-XXI/82-83 |  | Ex.No. 188/2006 | SWD-4 | High Court | Sh. Gaurang Kant | --- | 3.11.2007 | In progress |
| 37 | ### C/o 840 DUs under SFS in Pkt.B, 104 Cat.III, 78 Cat.II & 128 S/Gs. i/c internal dev.Gr.I 35/HD-21 | F21(18)98/HC/ Legal | FAO (05)/ 595/2006 | SWD-4 | High Court | Geeta Malhotra | --- | 24.10.2007 | In progress |
| 38 | ### C/o 840 DUs under SFS in Pkt.B, 104 Cat.III, 78 Cat.II & 128 S/Gs. i/c internal dev.Gr.II 35/HD-21 | F21(18)98/HC/ Legal | Ex. 563/2006 | SWD-4 | High Court | D.S. Mahendru | --- | 26.11.2006 | In progress |

###### REGARDING LIST OF COURT CASE IN SOUTH WEST ZONE

| S. N | Case Title/Party Name | File No. | Suit No. | Name of division | Name of Court | Name of P/L | Last date of hearing | Next date of hearing | Status of the Case |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |
| 39 | C/o 852 HIG/MIG/LIG houses at Vasant Kunj Mehrauli/ Mahipalpur Road Sultangarhi Tomb | F21(106)04/HC/ Legal | 957/2004 | SWD-4 | High Court | Rajeev Bansal | --- | 20.9.2007 | In progress |
| 40 | C/o 403 houses under SFS (155 Cat.III, 243 Cat.II & 310 S/Gs. i/c D/o land in Pkt.2 & 3, Sec.B, Vasant Kunj. Agmt.No.74/EE/SWD-4/89-90 |  | OMP No. 287/2004 | SWD-4 | High Court | D.S. Mahendru | --- | --- | Matter listed in the list of final cases to be heard on its turn last date of hearing 22.8.05 |
| 41 | C/o 1140 DUs & comprising of 684 cat.III, 456 cat.II flats & 84 S/Gs. under SFS at V. Kunj Sec.B, Pkt.1 i/c D/o land. SH: C/o 108 Cat.III, 72 Cat.II flats and 10 Nos. S/Gs. Gr.VII |  | 3020/A/1996 | SWD-4 | High court | A. Salwan | --- | 8.5.2007 | Matter listed in the list of final cases to be heard on its turn last date of hearing 22.8.05 |
| 42 | C/o 180 houses MIG Pkt.A & B Kalkaji Extn. I/c D/o land. Agmt. No. HD-XXI/81-82 | F21(27)06/HC/ Legal | FAO(05)/143/06 | SWD-4 | High Court | A. Salwan | --- | 6.8.2007 | In Progress |
| 43 | C/o 180 houses MIG Pkt.A & B Kalkaji Extn. I/c D/o land. Agmt. No. HD-XXI/81-82 | F21(27)06/HC/ Legal | Ex 22/06 | SWD-4 | High Court | A. Salwan | --- | 6.8.2007 | In Progress |
| 44 | C/o 168 SFS houses at Kalkaji near Community Centre at Gr.I Agmt.No.16/HD-XXI/DDA/ 80-81 | F2(95)92/EA to EM duplicate file) | FAO/205/96 | SWD-4 | High Court | D.S. Mahendru | --- | 4.12.2007 | In Progress |

###### REGARDING LIST OF COURT CASE IN SOUTH WEST ZONE

| S. N | Case Title/Party Name | File No. | Suit No. | Name of division | Name of Court | Name of P/L | Last date of hearing | Next date of hearing | Status of the Case |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |
| 45 | C/o 12.00 lac gallons capacity underground tank & pump houses at Sec.B, Pkt.5 & 6 Vasant Kunj, New Delhi regarding deduction of cases | F21(109)/06/HC/ Legal | WP(S)6813/ 2006 | SWD-4 | High Court | Anil Sapra | --- | Reserved the orders on 7.12.06 | In progress |
| 46 | C/o 240 HIG/104 MIG/120 LIG multistoreyed houses behind Pkt.D-6, Vasant Kunj, Gr.II, New Delhi | F21(08)/05/HC/ Legal | CS(05)86/ 2005 | SWD-4 | High Court | Geeta Mehrotra | --- | --- | In Progress |
| 47 | C/o 72 SFS (96 Cat.III & 36 S/Gs. at Vasant Kunj, Sec.C, Pkt.9 | F11(43)05/HC/ Legal | 258/2005 | SWD-4 | Tis Hazari | Sh. S.N. Zulfikar | --- | 30.3.2007 | In Progress |
| 48 | D/o land at West of JNU Vasant Kunj, Ph.II SH:C/o 12 lacs gallons capacity underground pump house | F11(41)05/TC/ Legal | 257/05 | SWD-4 | Tis Hazari | Rajender Mal Tatia | --- | 28.5.2007 | In Progress |

###### SOUTH  WEST  ZONE

###### DETAILS      OF      DAEVIATION      IN      WORKS      IN     CIVIL      CIRCLE-1

| S.No. | Name of work | Agency | Reference vide which statement received from E.E. | ## Remarks |
| --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 |
| 1 | C/o 152 SFS Cat.II houses in Sec.D, Pkt.6, Gr.I & II ## SWD-1 | M/s. Naresh Kapoor | DB(3)/AE(P)/SWD-1/886-887 Dated 25.7.2007 | SE-1/3(1)/07/CC.1/1775 dated 7.8.2007 |
| 2 | M/o completed scheme under SWZ Nazul A/c-II (Hort. Work) | M/s. S.K. Associates | F4(111)/AE(P)/Hor./06-07/23 dated 1.3.2007 | SE.I/18(186)2007/EOT/1794 dated 8.8.2007 SE.I/18(186)2007/EOT/1890 dated 17.8.2007 |

### List  of   Extra/Substitute   Statement   under   Process    in   Civil   Circle-I

| S.No. | Name of Work | Agency | Amount of Statement | Reference vide which statement received | ## Remarks |
| --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 |
| 1 | D/o land in West of JNU at Vasant Kunj, Phase-II SH: C/o Peripheral SW drain in constraint area (Part-I) ## SWD-2 | M/s. Tomar Construction Co. | E.I.S.-I Rs. 1.96 lacs E.I.S.-III Rs.10.97 lacs | F4(120)/AE(P)/SWD-2/ DDA/06/1356 dt.13.10.06 | SE.I/18(71)2002/DDA/Item/4185 dated 1.12.2006 SE.I/18(71)2002/DDA/Item/1738 dated 30.7.2006 |
| 2 | M/o Completed Scheme un SWZ Nazul A/C-II SH: Cleaning & desilting of pucca sedimentation at Masood Pur Dairy | Sh. Sudhir Kumar | EIS-II Rs. 0.89 lacs | F4(111)/AE(P)/SWD-2/ DDA/882 dt.23.7.07 | SE.I/18(191)2007/DDA/1751 dated 1.8.2007 |
| 3 | D/o land in West of JNU at Vasant Kunj, Ph.II SH: C/o 12.00 lacs gallons capacity of UG Tank & pump house (balance work) at risk & cost of M/s. V.K. Goel | M/s. Rajender Pd. Gupta | EIS-III – Rs. 12.36 lacs EIS-IV – Rs. 14.54 lacs | F1 (157)/AE(P)/SWD-4/ DDA/763 dt.12.6.07 F1(157)/AE(P)/SWD-4/ DDA/764 dt.12.6.07 | Sent to CE(SWZ)’s office. |

( SOUTH WEST ZONE )

### List  of   R.I.S./D.I.S.    Statement   under   Process    in   Civil   Circle-I

| S.No. | Name of Work | Agency | Amount of Statement | Reference vide which statement received | Remarks |
| --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 |
| 1 | D/o land in West of JNU at Vasant Kunj, Phase-II SH: C/o Peripheral SW drain in constraint area (Part-I) ## SWD-2 | M/s. Tomar Construction Co. | Rs. 1796/- | F4(120)/AE(P)/SWD-2/ DDA/07/391 dt.9.3.07 | SE.I/18(71)2007/RIS.I/1666 dated 25.7.2007 |

( SOUTH WEST ZONE )

### List  of   E.O.T.    Cases   under   Process    in   Civil   Circle-I

| S.No. | Name of work/Agency | Date of Start | Date of Completion | Extra as required upto | Remarks |
| --- | --- | --- | --- | --- | --- |
| -----------------------------------------------------------NIL---------------------------------------------------------- |  |  |  |  |  |