## Sheet1
STATUS OF LAND HANDED OVER/YET TO BE HANDED OVER TO ENGINEERING WING
ZONE : SOUTH WEST
S.NO. | CIRCLE/ | DETAILS OF SCHEME/ | AREA OF LAND | AREA OF LAND | AVAILIBILITY | STATUS | REMARKS
| DIVISION | PROJECT | HANDED OVER | YET TO BE | OF DEV.PLANS | DEVELOPMENT
HANDED OVER
1 | CC-5/WD-1 | Utilisation of Vacant land at | 57427 Sqm | -- | Available | 50% area developed
|  | Kirti Nagar. |  |  |  | & 50% to be
developed
2 | CC-5/WD-1 | D/o land for alternative plots | 5812 Sqm | -- | Not Available | N.A. | Revised layout plan
|  | for shops of the effectees of |  |  |  |  | to be issued by area
|  | Naraina Ring Road widening |  |  |  |  | Planning Wing on
the intervention on
Hon'ble Court.
3 | CC-5/WD-1 | D/o land sanitary fill Site No.2 | 27500 Sqm | -- | Available | -- | B/Wall existing,
|  | at Hastsal. |  |  |  |  | P.E.under finalisation
4 | CC-1/SWD-1 | C/o 362 houses in Sultangarhi | -- | 2 Hact. | Drg.Available | Detail Estimate
|  | Mehrauli Mahipalpur Road. |  |  |  | under prepn.
5 | CC-1/SWD-2 | 102 Bigha land at Mahipalpur | -- | 8.59 Acre | N.A. | B/Wall constructed,
|  | Near Shamshan Bhomi. |  |  |  | Survey conducted
Dev Plan Available
6 | CC-1/SWD-2 | Vacant land at Village | -- | 12.57 Hact. | N.A. | Development Plan
|  | Mahipalpur near CISF Camp |  |  |  | yet to be approved
(Under Process)
7 | CC-1/SWD-4 | Land occupied by CRPF to be | 3.00 Hact. | -- | Not Available | Area yet to be fenced. | (Under CRPF)
constructed for given as
open ground.
8 | CC-1/SWD-4 | D-7/8 near ESS and Shanti | 0.08 Hact. | -- | Available | Yet to be auctioned | Nursery School
Sport Complex at V.Kunj.
9 | CC-1/SWD-4 | D-4 Vasant Kunj,SFS houses | 0.08 Hact. | -- | Available | Yet to be auctioned | Nursery School
STATUS OF LAND HANDED OVER/YET TO BE HANDED OVER TO ENGINEERING WING
S.NO. | CIRCLE/ | DETAILS OF SCHEME/ | AREA OF LAND | AREA OF LAND | AVAILIBILITY | STATUS | REMARKS
| DIVISION | PROJECT | HANDED OVER | YET TO BE | OF DEV.PLANS | DEVELOPMENT
HANDED OVER
10 | CC-1/SWD-4 | D-4 on Mahipalpur Mehrauli | 2.50 Hact. | -- | Available | Partly fenced with | Work could not be
|  | road 100 SFS houses |  |  |  | RBI fencing | takenup due to alignm-
ent of road and encroa-
chment.
11 | CC-1/SWD-4 | Sec. D-5 near Petrol Pump | 16.00 Hact. | -- | Not Available | Not fenced | Estimate for fencing
|  | along Mahipalpur Road. |  |  |  |  | submitted to CC-I
Partly area under
encroachment
12 | CC-1/SWD-4 | C/o 416 SFS houses MIG flats | 5.89 Hact. | -- | Available | Work heldup due to | Area fenced.
|  | near M.M.road (L&T) |  |  |  | High Court Order
13 | CC-1/SWD-4 | Land at Village Adhchini along | 0.045 Hact. | -- | Not Available | Full fenced levelled
|  | Aurbindo Marg Kh.No.25 & 26 |  |  |  | & dressed.