## Sheet1
OFFICE OF THE EXECUTIVE ENGINEER
ELECTRICAL DIVISION NO.7
KESHAV PURAM , DELHI
DEVIATION STATEMENT 2-7-07 onwards
ending July 2007
S.No. | NAME OF WORK | AGENCY | AGGREMENT | ESTIMATED | TENDERED | AMOUNT OF DEVIATION |  | REFERENCE OF
|  |  | NO | COST | AMOUNT | APPROVED/ PROPOSED |  | PRINCIPAL
APPROVED ACCORDED
1 | M/O Pump set at various places | M/s parkash | 16/EE/ED-7/ | Rs. 1,59,912/- | Rs.1,47,420/- | Rs.13870/- @ | Rs.13923/- | BY THE COMPETENT
| under N/zone SH : A /R/M/O booster pump sets, | Electric | D.D.A/06-07 |  |  | 9.40 % Above |  | AUTHORITY
| submersible pump set and D.G SET at | Corporaton
768 Janta Houses in sector B-4, Pocket-3 Narela.
2 | M/o Pork, plantation, trucks & other equipment in | M/s H.S. Engg. | 91/EE/ED-7/ | Rs.3,89,302/- | Rs.38129/- | Rs.68015/- @ | Rs.68045/- | -
| Hort. Wing under N.A/C II SH. Annul repair & | Works | D.D.A/06-07 |  |  | 17.83%above
maintenance of submersible pump set,
monoblock p/set & Pannel boord/ Feeder Pillor,
D.G. set & other E&M installation in park/ green
under Hort. Din No.II
3 | D/o Golf course at Bhalaswa SH. Lifting & | M/s Pumps | 26/EE/ | Rs.83,870/- | Rs.83203/- | Rs.2313/- @ | Rs.2313/- | -
| lowering of Submersible pamp sets/mono block | Engg. & | ED-/06-07 |  |  | 2.77%above
| sub. Pump sets and supplying and fixing | Associates
other accessonies.
4 | D/o Land at Narela Township SH-Prdg.Street | M/s Goel | 55/EE/ED-7/ | Rs.809929/- | Rs.895313/- | Rs.170897/-@ | Rs.170897/- | Principal approval from EE(E)
| Lighting on 40 mtr. 20 mtr 20 mtrs road at | Electric | DDA/06-07 |  |  | 19.05% |  | ED -7
| Narela sector A-6 to crossing at 80 mtr road | Works |  |  |  | above
at Narela
5 | D/o land for Yamuna Bio-diversity park at | M/s Pumps | 14/EE/ | Rs.122679/- | Rs.118590/- | Rs.16761@ | Rs.16761/- | -
| Jharoda Mazra, Wazirabad.(Sh. A/R/M and | Engg. & | ED-7/06-07 |  |  | 14.13%
| operation of 10 KVA D.G. set and lighting | Associates |  |  |  | above
arrangement of internal and external eletrification.
6 | D/o Golt course at Bhalaswa SH. A/R/M/O of 5 | Do | 20/EE/ | Rs.309256/- | Rs.284160/- | Rs.39649@ | Rs.39649/- | -
| 5 No. Sub. pump set 3 nos. Mono |  | ED-7/06-07 |  |  | 13.95%
| submersible pump set at Golt course Bhalsawa |  |  |  |  | above
and 7.5 HP Nos treated water pump sets at
Burari
7 | M/o Pumps set at various places under North zone | M/s Satish | 34/EE/ED-7 | Rs.158916/- | Rs.154080/- | Rs.9112/-@ | Rs. 9112/- | -
| Sh. A/R/M/O of sub. P/sets in tubewell nos 1+2 | Electricals | DDA/06-07 |  |  | 5.91%above
clear water booster pump set and D.G set at
sector A-9, Narela
8 | M/o Pump set, at various places under north zone
| SH. A/R/M/O of sub. P/Set temporary service | Do | 37/EE/ED-7 | Rs.146748/- | Rs.142320/- | Rs.5739/-@ | Rs.5739/- | -
| line for tube well nos 2 & 3 at transit camp near |  | DDA/06-07 |  |  | 4.03%above
Gautam colony Narela
9 | M/o Completed scheme under north zone. | M/s Parkash | 137/EE(E)/ED-7 | Rs.183131/- | Rs.167721/- | Rs.39917/-@ | Rs.39640/- | -
| (SH. Annual running, operation & Maintenance | Electrical | DDA/05-06 |  |  | 23.79%
| of electric installation at katha kunj and parking | corparation |  |  |  | above
around Hanuman Mandir, Bela Road

## deviation
OFFICE OF THE EXECUTIVE ENGINEER
ELECTRICAL DIVISION NO.7
KESHAV PURAM , DELHI
DEVIATION STATEMENT 2-7-07 onwards
ending July 2007
S.No. | NAME OF WORK | AGENCY | AGGREMENT | ESTIMATED | TENDERED | AMOUNT OF DEVIATION |  | REFERENCE OF
|  |  | NO | COST | AMOUNT | APPROVED/ PROPOSED |  | PRINCIPAL
APPROVED ACCORDED
1 | M/O Pump set at various places | M/s parkash | 16/EE/ED-7/ | Rs. 1,59,912/- | Rs.1,47,420/- | Rs.13870/- @ | Rs.13923/- | BY THE COMPETENT
| under N/zone SH : A /R/M/O booster pump sets, | Electric | D.D.A/06-07 |  |  | 9.40 % Above |  | AUTHORITY
| submersible pump set and D.G SET at | Corporaton
768 Janta Houses in sector B-4, Pocket-3 Narela.
2 | M/o Pork, plantation, trucks & other equipment in | M/s H.S. Engg. | 91/EE/ED-7/ | Rs.3,89,302/- | Rs.38129/- | Rs.68015/- @ | Rs.68045/- | -
| Hort. Wing under N.A/C II SH. Annul repair & | Works | D.D.A/06-07 |  |  | 17.83%above
maintenance of submersible pump set,
monoblock p/set & Pannel boord/ Feeder Pillor,
D.G. set & other E&M installation in park/ green
under Hort. Din No.II
3 | D/o Golf course at Bhalaswa SH. Lifting & | M/s Pumps | 26/EE/ | Rs.83,870/- | Rs.83203/- | Rs.2313/- @ | Rs.2313/- | -
| lowering of Submersible pamp sets/mono block | Engg. & | ED-/06-07 |  |  | 2.77%above
| sub. Pump sets and supplying and fixing | Associates
other accessonies.
4 | D/o Land at Narela Township SH-Prdg.Street | M/s Goel | 55/EE/ED-7/ | Rs.809929/- | Rs.895313/- | Rs.170897/-@ | Rs.170897/- | Principal approval from EE(E)
| Lighting on 40 mtr. 20 mtr 20 mtrs road at | Electric | DDA/06-07 |  |  | 19.05% |  | ED -7
| Narela sector A-6 to crossing at 80 mtr road | Works |  |  |  | above
at Narela
5 | D/o land for Yamuna Bio-diversity park at | M/s Pumps | 14/EE/ | Rs.122679/- | Rs.118590/- | Rs.16761@ | Rs.16761/- | -
| Jharoda Mazra, Wazirabad.(Sh. A/R/M and | Engg. & | ED-7/06-07 |  |  | 14.13%
| operation of 10 KVA D.G. set and lighting | Associates |  |  |  | above
arrangement of internal and external eletrification.
6 | D/o Golt course at Bhalaswa SH. A/R/M/O of 5 | Do | 20/EE/ | Rs.309256/- | Rs.284160/- | Rs.39649@ | Rs.39649/- | -
| 5 No. Sub. pump set 3 nos. Mono |  | ED-7/06-07 |  |  | 13.95%
| submersible pump set at Golt course Bhalsawa |  |  |  |  | above
and 7.5 HP Nos treated water pump sets at
Burari
7 | M/o Pumps set at various places under North zone | M/s Satish | 34/EE/ED-7 | Rs.158916/- | Rs.154080/- | Rs.9112/-@ | Rs. 9112/- | -
| Sh. A/R/M/O of sub. P/sets in tubewell nos 1+2 | Electricals | DDA/06-07 |  |  | 5.91%above
clear water booster pump set and D.G set at
sector A-9, Narela
8 | M/o Pump set, at various places under north zone
| SH. A/R/M/O of sub. P/Set temporary service | Do | 37/EE/ED-7 | Rs.146748/- | Rs.142320/- | Rs.5739/-@ | Rs.5739/- | -
| line for tube well nos 2 & 3 at transit camp near |  | DDA/06-07 |  |  | 4.03%above
Gautam colony Narela
9 | M/o Completed scheme under north zone. | M/s Parkash | 137/EE(E)/ED-7 | Rs.183131/- | Rs.167721/- | Rs.39917/-@ | Rs.39640/- | -
| (SH. Annual running, operation & Maintenance | Electrical | DDA/05-06 |  |  | 23.79%
| of electric installation at katha kunj and parking | corparation |  |  |  | above
around Hanuman Mandir, Bela Road