## Sheet1
REDUCED ITEM STATEMENT, EXTRA ITEM STATEMENT , SUBSTITUTE ITEM STATEMENT & E.O. TIME
2-7-07 onwards
ending July 2007
S.NO. | NAME OF WORK | AGENCY | AGREEMENT | Estt.Cost/ | AMOUNT OF |  | DETAIL OF E.O.T
|  |  |  | Tender Cost | R.I.S | E.I.S | Without levy | with | REMARK
[7 empty] | of compensation | levy of
1 | M/O pump set at various places | M/S N.K Engg. Works | 36/EE/FD 7DDA/ | Rs.147,408/- | Nil | Nil | From 24/6/07 to | compensation | Approved by
| under north Zone CSH A/R/M/O |  | 2006-07 | Rs142,980/- |  |  | 28/6/07 |  | EE(E)/ED-7
| of clear booster P/Set 30 KVA | [5 empty] | i.e five days
for 660 L.I.G incr. houses in sector
A-6, Pocket -I Narela
2 | M/o Pump sets at various places | M/S Parkash Electric | 16/EE/ED7/DDA/ | Rs. 159912/- | Nil | Nil | From 14.5.2007 to | - | Do
| under North zone SH : A/R/M/O | corporation | 2006-07 |  |  |  | 12.6.2007
| booster pump sets, submersible | [5 empty] | in 30 days
P/set and D.G. set at 768 Janta
Houses in sector B-4 Pocket -3
Narela
3 | M/O Park, Plantation truckes & | M/S Pumps Engg. & | 122/EE/ED-7/DDDA | Rs. 403991/- | - | - | From 11-04-2007 | - | Approved by
| other equipment in Hart. Wing | Associatiats | 2006-07 | Rs.449954/- |  |  | to 14-05-2007 |  | SE(E) -2/El Circle 2
| under N.A II SH pdg. And | [5 empty] | i.e. one month 4 days
installation of park / Path light in
| Park/green at Parmeshwari wala | [5 empty] | to 14-05-2007
Bagh
4 | D/o land for Yamuna Bio-diversity | M/S Pumps Engg. & | 14/EE/ED-7/2006-07 | Rs. 122679/- | - | -
| Pocket at Jhorada Majra, Wazirabad | Associatiats |  | Rs.118500/- |  |  | From 14-05-07 |  | Approved by
| SH : A/R/M/O of 10 KVA DG set and | [5 empty] | to 12-06-2007 |  | EE(E) /ED-7/DDA
| Lighting arrangement of Internal & external | [5 empty] | i.e. 30 days
electrification
5 | D/o Golt course at Bhalaswa SH : | M/S Pumps Engg. & | 124 EE/E/ED-7 /DDA | Rs. 73844/- | - | Rs 12627/- | - | - | Approved by
| Supplying and fixing of decorative | Associatiats | 2006-07 | Rs81,1801/- |  |  |  |  | EE (ED-7)
| luminaire at Gate for Golt Course at | [5 empty] | -
Bhalaswa
6 | D/o Golf course at Bhalaswa SH : A/R/M/O | do | 20 EE/E/FD-7 /DDA | Rs. 308256/- | - | - | from 21-5-2007 | - | Approved by
| of 5 Nos submesible pump sets 3 Nos Mono |  | 2006-07 | Rs284160/- |  |  | to 28-06-2007 |  | EE / ED-7
| Block submersible pumps at Golf Course | [5 empty] | i.e. one month
| Bhalwasa and 7.5 H.P 2 Nos treated water | [5 empty] | and eight days
pumps at Burari
7 | D/O Golf Course at Bhalswa | do | 124 EE/E/FD-7 /DDA | Rs 73844/- | - | Rs 21045/- | - | -
| SH : SUPPLYING & FIXING OF decorative |  | 2006-07 | Rs81180/- |  | substituted |  |  | Approved by
| lumanaries at Gate for Golf Course |  |  |  |  | item |  |  | SE (Elec - 2 /
Circle 2
8 | M/O pump set at varios places under North Zone | M/s Satish Electricals | 37 EE/E/FD-7 /DDA | Rs 146748/- | - | - | From 1-7-2007 | -
| SH : a/r/m/o of submersible Pump sets, |  | 2006-07 | Rs 142390/- |  |  | to 6-7-2007 |  | Approved by
| service line for tube well no 1& 2 at Transit Camp | [5 empty] | i.e. six days |  | EE (ED-7)
Gautam Colony, Narela
9 | DO SH : A/R/M/O of submersible | DO | 34 EE/E/FD-7 /DDA | Rs 1,58916/- | - | -
| pump set , tube well No. 1 & 3 clear water pump |  | 2006-07 | Rs 154080/- |  |  | From 24-6-07 | - | Approved by
| boster pump set & DG Set, Sector A9, Narela | [5 empty] | to 6-7-07 |  | EE (ED-7)
i.e. 13 days