DELHI DEVELOPMENT AUTHORITY

WESTERN DIVISION NO. 5, VIKAS MINAR

NEW DELHI – 110001

QUOTATION NOTICE

Name of Work	: -	Special repair of Vikas Minar.

SH	: -	Rehabilitation of R.C.C. columns and beams and other R.C.C. members of Vikas Minar.

Sealed quotation are invited on lump sum basis for the following work by the Executive Engineer, Western Div. No. 5, Vikas MInar, Delhi – 110002 upto 3.00 P.M. on 04.08.007 Behalf of DDA, for the Consultancy for Structural Design, from specialized firm who meet the following conditions, which shall be opened on the same say at 3.30 P.M. in the office of Executive Engineer, W.D-5/D.D.A IN the presence of intending Consultants/their representatives.

The quotationers are advised to inspect the site & access the scope of work before quoting their rates. The rates should be quoted in figures as well as in words.

The acceptance of quotation will rest with the DDA who does not bind himself to accept the lowest quotation and reserves to himself the right to reject or liable to be rejected,

Project Cost:- Rs. 6997284/-

SCOPE OF WORK:

The consultant shall inspect work and conduct in-situ & laboratory tests necessary to establish the cause – effect relation. The consultant shall be responsible for quality assurance procedure, inspection of work during the execution of work and final inspection of work after completion. The consultant will study the existing specifications, nomenclature of items of works, analysis of rates and standards applicable shall given their view. The consultant may add/deduct some item as per site requirement. The salient features shall be brought out in the presentation and supporting literature shall be made available.

(A)    Consultant shall prepare & submit a detailed rehabilitation plan, which    shall include the following:

1.	Details regarding selection of materials, equipment and methods of

Rehabilitation. If any new materials/ techniques are proposed, they shall be supported with necessary technical/ documentation/ data.

2.	Detailed nomenclature of items to be executed (Including added new items).

3.	Detailed specifications including acceptance criteria/ standards for

work to be executed & materials used.

4.	Step procedure of execution of work at different locations/ for

different elements including surface preparation, method

construction & techniques to be adopted.

5.	All drawings for execution shall be submitted in minimum of two

sets along with a set in a reproducible format.

6.	Safety plan before and during repair/ rehabilitation including details of shuttering, centering & scaffolding required for repairs at different locations, keeping in view intricacies involved like large spans, extra heights, etc. Details for planned demolition of structurally sensitive   portions shall also be prepared.

7.	Methods of fixing fixtures/ fittings etc for the reinstallation/ installation of services, false ceiling, interior decoration, etc shall also be detailed out.

8.	Detailed Quality Assurance System during execution.

9.	Acceptance criteria of materials and the items of work to be

executed.

The proposal will be examined and approved by the Employer. If modification same the proposal is required, the consultant shall carry out the same.

(B)    The consultant shall assist in supervision and quality assurance of work during execution, conducting corrective supervision, acceptance or work executed and issuing stability and rehabilitation certificate. The consultant shall prepare guidelines for further maintenance and post repair periodic inspection and details should provide for:-

1.	The consultant will be closely associated in the supervision of execution consultant or the Employer at the time of execution in order to ensure that the same is being carried out as per their concept and approval. While routine supervision will be carried out by the Engineer-in-charge, the consultant will render advice at different stages of execution. The consultant shall send his representative having   relevant experience for supervision as and when required by the Employer.

2.	It will also include revision of designs and drawings,   due   to shortcomings, if any, which might surface at the time of execution. Consultant shall    claim   nothing    extra in this regard.

3.	Carrying out quality assurance tests during progress of work. During the actual testing the consultant shall be actively involved with the testing.

4.	A detailed plan for maintenance manual.

5.	Issue completion certificate base on acceptance tests carried out on

rehabilitated structure.

- Preparation of documentation using photographs.

- Time Allowed:-   9 Months

(A) 	 36 weeks from start of work.

i. 	The work shall commence for 10th day after the date of written orders to commence the work.

ii.	The Progress of the work shall be reviewed in weekly meetings between representative of consultantand Engineer,

Employer and the contractor, if any. The record of such meeting shall be ma in tainted.

iii.	In case consultant  is  unavoidably hindered in carrying out the investigation, design/ drawings on account  of delayed decisions or  approval by the Employer,  which a re  necessary to carry  out  further  work,  he shall apply for be  allowed suitable extension of time to the on occurrence of such hindrance. The decision of the Employer shall be final and bindings on the consultant.

iv.	In case of delays attributable to the Employer after   the start of work, the Employer shall be made liable to pay compensation to the consultant at a rate as may be   specified in the agreement towards the fixed charges of establishment including the remuneration of    the key personnel, only if   exclusively employed for the work in question.

v.	For the delays attributable to the consultant, the consultant shall be made liable to pay compensation to the Employer at a rate as may be specified   in the agreement.

Visit Charges:- 	There shall be  not any visit charges till completion  of work

Condition/Requirement:- The intending Consultant/ structural Designed should   have satisfactorily   completed three works (at least on of them in Central Govt./ Central automus body/ Central /PSU) of the similar nature  of work during last five  years. A certificate of the same issued by the Organization under whom the works have been executed be enclosed at   the time of submission of quotation.

No: F.5(97)WD-5/DDA/2007-08/1763					Dated 27.07.07

EXECUTIVE ENGINEER

WD-5/ DDA