## Sheet1
Pre-bid clarification
Sno | Description | Tender Clause | Tender Stipulation | Acil's query | Reply
1 | Joint venture modality |  |  | 1. Joint venture is requested to be allowed whether we purchase the document in our name and submit JV formalities before due date of tender. We are in process of importing technology/ partner. | As per NIT provisions.
|  |  |  | 2. We have sufficient experience in contruction industry, we may please be considered lead partner irrespective of technical experience of our joint venture partner. | As per NIT provisions.
2 | Certificates and list of documents to be submitted by bidders | Method of tender submission page no 6 & 7 | Mentioned on page no 6 & 7 | Are these documents to be submitted with bid ? | As per NIT provisions.
3 | Maintenance/ defect liability peroid | Scope of work page16 clause no19 | Three years | This should be 12 months as a general industry practice | As per NIT provisions.
3 | Time for completion | Front page of NIT | 36 months. | As contractor has to obtain opprovals from several Govt. departments on which we have no control. The completion period of 36 months will star after getting such appprovals. | As per NIT provisions.
4 | Suggestive Architectural finishes | Page 21 |  | Upto what extent these specifications can be followed as we may consider prefinished wall and conrete panels and may go away with plastering etc. | As per NIT provisions.
5 | Design requirement of structural components | Page 26 |  | Structural design shall be carried out with latest modelling softwares and necessary connection as per pre-fabrication techniqes between pre-cast members shall be provided and this may differ Indian pre-cast codes. | As per NIT provisions.
6 | Condition of Reinforcement steel | Clause 2.0 page no 73 | TMT bars of main producers i.e SAIL, TATA ,IISCO & RINL | We envisage the use of smaller dia of reinforcement steel in pre-fab units i.e 3.6mm & 6mm and wire mesh also which main producers do not manufecture. We should be alowed to use the steel from secondary producers. Manufecturer's test certificate will be submitted and no separate testing will be carried out at site/external laboratory. | As per NIT provisions.
7 | Material advance | Escalation | Not applicabe | To be applicable for such long duration project. | As per NIT provisions.
8 | Time for submission |  |  | The time for submission may be extended upto 25/03/2012 to complete all formalities
| Eligibility requirements |  |  | The criteria kept for eligibility is too stringent considering that pre-cast technologies are in beginning stage in India. We suggest that cap of number of stories or height from precast construction work expeirence at page no 42 at clause (iii) may be reomoved as it can be accepted that adding height to pre-cast building is a small fraction of overall industry. | As per NIT provisions.
Note on F3: Admin: