Details of Contractor Concluded During the Month of June, 2009

Division  No. SED-11/DDA

| 1. | 2. | 3. | 4. | 5. | 6. | 7. | 8. | 9. | 10. | 11. | 12. | 13. | 14. | 15. | 16. | 17. | 18. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Tender No. | Item nature of work | Made of tender Enquiry | Dt. Of public action of NIT | Type of Bidding (Single/ -two Bid System) | Last Dt. Of receipt of tender | Nos. of tenders recd | Nos. & name of parties not qualified after technical evaluation | Whether contractor awarded to lowest tender evaluated LI | Contract No. & Date | Name of Contract | Name of Contractor | Value of contract | Schedule dt. Of completion of supplies contract | Actual dt. Of start of work | Actual dt. Of completion | Reasons for delay if any | Remarks |
| 83/SED-11/08-09 | Maint work | Item rate | 24.11.08 | Single | 02.12.08 | 2 Nos | N.A | Yes | Agmt. 75 SED-11/ 08-09 | Day to day M/o Cricket Practice pitches at Lala Lajpat Rai M.Park Lajpat Nagar | M/S Om Parkash Contractor | 2,25,000,/- | 21.06.09 | 13.12.08 | 19.06.09 | -- | -- |
| 96/SED-11/08-09 | Maint work | Item rate | 18.12.08 | Single | 30.12.08 | 4 Nos | N.A | Yes | Agmt. 107 SED-11/ 08-09 | Rubbing, Grinding & Polishing of Kota Stone flooring in D- Block Vikas Sadan | M/S Kirishna Constn. Co. | 1,41,125,/- | 12.04.09 | 12.03.09 | 10.04.09 | -- | -- |
| 36/SED-11/08-09 | Maint work | Item rate | 26.09.08 | Single | 03.10.08 | 2 Nos | N.A | Yes | Agmt. 57 SED-11/ 08-09 | Maint. & upkeep of A-Block cleaning & mopping at all floors Vikas Sadan | M/S Prime Services | 5,46,000,/- | 22.04.09 | 18.10.08 | 05.06.09 | -- | EOT granted without levy of compensation |
| 38/SED-11/08-09 | Maint work | Item rate | 26.09.08 | Single | 03.10.08 | 2 Nos | N.A | Yes | Agmt. 58 SED-11/ 08-09 | Cleaning of toilets, office at all floors and shaft in C-Block Vikas Sadan | M/S Prime Services. | 9,01,524,/- | 22.04.09 | 16.10.08 | 02.06.09 | -- | -DO- |
| 99/SED-11/08-09 | Maint work | Item rate | 14.01.09 | Single | 21.01.09 | 4 Nos | N.A | Yes | Agmt. 103 SED-11/ 08-09 | Repair of water case code in Millennium Park at Sarai Kale Khan. | M/S Indian Enterprises | 4,21,808,/- | 05.05.09 | 06.03.09 | 05.05.09 | -- | -- |
| 98/SED-11/08-09 | Maint work | Item rate | 14.01.09 | Single | 21.01.09 | 3 Nos | N.A | Yes | Agmt. 111 SED-11/ 08-09 | Repair of Grit wash and water proofing of walls and roof etc. in staff flats at AGVC | M/S Civil Constn. Co | 3,41,347,/- | 02.06.09 | 03.04.09 | 01.06.09 | -- | -- |
| 100/SED-11 /08-09 | Maint work | Item rate | 14.01.09 | Single | 21.01.09 | 5 Nos | N.A | Yes | Agmt.112 SED-11/ 08-09 | Filling sand in sand pits and removing and laying C.C. Paver in Millennium Park at Sarai Kale Khan | Srhi Sumit Kumar Saroha | 1,76,293,/- | 02.06.09 | 03.04.09 | 02.06.09 | -- | -- |
| 78/SED-11 /08-09 | Maint work | Item rate | 12.12.08 | Single | 20.12.08 | 2 Nos | N.A | Yes | Agmt.91 SED-11/ 08-09 | Pdg. & fixing false celining in Lift Lobby B-Block Vikas Sadan | M/S Varshnay Constn. Co. | 7,60,530,/- | 28.02.09 | 30.01.09 | 29.05.09 | -- | EOT granted without levy of compensation |
| 04/SED-11 /09-10 | Maint work | Item rate | 02.04.09 | Single | 15.04.09 | 2 Nos | N.A | Yes | Agmt.17 SED-11/ 09-10 | Disinfection & Rodent Control Masures at Vikas Sadan | M/S Pest Control Services of India. | 1,24,780,/- | 15.01.2010 | 16.07.09 | Work in progress | -- | -- |
| 16/SED-11 /09-10 | Maint work | Item rate | 15.05.09 | Single | 23.05.09 | 6 Nos | N.A | Yes | Agmt.18 SED-11/ 09-10 | C/O of pump House and drainages water treatment system for raw water from Nallah. at SFSC | Shri Mahender Kumar | 14,89,710,/- | 17.11.09 | 18.07.09 | Work in progress | -- | -- |
| 18/SED-11 /09-10 | Maint work | Item rate | 22.05.09 | Single | 30.05.09 | 4 Nos | N.A | Yes | Agmt.19 SED-11/ 09-10 | Repair and jointing of water line with internal & STP point at Lala Lajpat Rai M. Park Lajpat Nagar | M/S Arch Constn. | 2,17,958/- | 02.09.09 | 20.07.09 | Work in progress | -- | -- |
| 05/SED-11 /09-10 | Maint work | Item rate | 02.04.09 | Single | 11.04.09 | 3 Nos | N.A | Yes | Agmt.20 SED-11/ 09-10 | Dry of cleaning of sofa set. At Vikas Sadan. | M/S Super Care | 74,000,/- | 23.01.2010 | 24.07.09 | Work in progress | -- | -- |
| 12/SED-11 /09-10 | Maint work | Item rate | 15.05.09 | Single | 26.05.09 | 4 Nos | N.A | Yes | Agmt.21 SED-11/ 09-10 | Up keep of office furniture at Vikas Sadan | Shri Amit Kumar Sharma | 3,72,675,/- | 24.01.2010 | 25.07.09 | Work in progress | -- | -- |
| 13/SED-11 /09-10 | Maint work | Item rate | 15.05.09 | Single | 30.05.09 | 5 Nos | N.A | Yes | Agmt.22 SED-11/ 09-10 | Renovation of toilets of C-1 Block at Vikas Sadan | Shri Rajeev Sehgal | 10,33,898/- | 26.09.09 | 27.07.09 | Work in progress | -- | -- |
| 17/SED-11 /09-10 | Maint work | Item rate | 30.05.09 | Single | 12.06.09 | 11 Nos | N.A | Yes | Agmt.23 SED-11/ 09-10 | Levlling and dressing of Green area at Madan Gir. | M/s S.K. Associate | 1,26,722/- | 31.08.09 | 01.08.09 | Work in progress | -- | -- |
| 28/SED-11 /09-10 | Maint work | Item rate | 03.07.09 | Single | 15.07.09 | 7 Nos | N.A | Yes | Agmt.24 SED-11/ 09-10 | C/o Gate and repair of site office near Virat Cinema. | M/o Consolidation Construction Co. | 60,000/- | 09.09.09 | 10.08.09 | Work in progress | -- | -- |
| 29/SED-11 /09-10 | Maint work | Item rate | 03.07.09 | Single | 15.07.09 | 7 Nos | N.A | Yes | Agmt.25 SED-11/ 09-10 | Repair of damaged Boundary wall i.c painting of area near Virat Cinema | M/s Arch Contraction | 90,204/- | 29.08.09 | 10.08.09 | Work in progress | -- | -- |
| 110/SED-11 /08-09 | Maint work | Item rate | 11.06.09 | Single | 20.06.09 | 3 Nos | N.A | Yes | Agmt.26 SED-11/ 09-10 | Restoration of damaged Road damaged by BSES for laying electric cable in F/o M/S select infrastructure (P) Ltd. Plot No. A-3 Distt. Center Saket. | Shri Ankur | 4,49,976/- | 09.09.09 | 10.08.09 | Work in progress | -- | -- |