DELHI DEVELOPMENT AUTHORITY

ELECTRICAL DIVISION NO. 8

LIST OF ACTIVITIES

1.	Details of Pending Final & non-refund of Security Deposits.

- Details of pending final bills for the Month ending July, 2008

| S. No. | Name of Work | Agency | Agreement No. | Stipulated date of start Completion | Actual date of completion | Date of payment of final bill | Reasons for delay in payment of final bill. |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | 2 | .3 | 4 | 5 | 6 | 7 | 8 |

.------------------------------------------------------------------------ NIL------------------------------------------------------------------------------------------------------------------

B.	Details of non-refund of Security Deposits for the Month ending July, 2008

| 0. | Name of Work | Agency | Agreement No. | Stipulated date of start Completion | Actual date of completion | Date of payment of final bill | Amount of Security Deposit deducted | Reasons for delay in refund of Security Deposit |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

.------------------------------------------------------------------------ NIL------------------------------------------------------------------------------------------------------------------

2.	Present status of work:

List of works costing more than Rs. 5.00 lacs for the month ending July, 2008

| S. No. | Name of Work | Agency | Estt. Cost Tendered amount (in lacs) | Stipulated date of start Completion | Physical progress | Actual Date | Physical progress (in %age) | Reasons for delay in payment of final bill. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |
| 1. | C/o 320/258 MS flats (SFS) at Motia Khan)` | M/s Goel Elect at work | 17.41 16.69 | 18.9.03 17.3.06 | 18.9.03 | 17.3.6 | 85% | I st inspection on 15.04.05 & file enclosed. |
| 2. | C/o 560 SFS houses Cat.II in Blk, D Pkt. I, Shalimar Bagh IEI of 192 SFS DU’s Gr.I | M/w Goel Electrical | 7.06 15.48 | 10.1.08 9.1.09 | 10108 | 9.1.09 | 60% | 2nd inspection on 14.03.2008 |
| 3. | b) IEI of 208 SFS DU’s Gr.II (balance work) | -do- | 9.10 | 19.92 | 10.108 | 63% | 65% | -do- |
| 4. | C/o 216. HIG DU’s (multistoried at Pitampura (near T.V. Tower) SH: C/o 72, HIG DU’s Multistoried superstructure including sanitary, installation, water supply, Sewerage drainage roads & paths and internal electrification all complete Gr.I. (composite tender) | M/s Ved Praksh Mittal & Sons | 22.57 Elect. Works | 56.05 | 25.10.06 | 24.10.08 | 49% | Composites tender awarded by EE/ND-5 Ist inspection on 15.6.2007 |
| 5. | C/o 216 HIG DU’s (multistoried) at Pitampura SH: C/o 144 HIG DU’s (multistoried super structure including sanitary installation water supply & internal electrification all complete Gr. II. & III (composite tender) | M/s Winner Constn, Pvt. Ltd | 45.18 | 73.01 Elect Works | 141206 | 13.1208 | 54% | Awarded by EE/ND Ist inspection on 25.7.07 |
| 6. | C/o 216 HIG DU’s (Multistoried i/c internal development at Pitampura near T.V. Tower completed (SH supplying & installation of lift for 144 flats in Gr.ii | M/s Schindler India & Pvt. Ltd | 105.59 | 103.50 | 91207 | 8808 | 80% | Nil |
| 7. | C/o 216 HIG DU’s (Multistoried) i/c intenral development at Pitampura near T.V. Tower completed (SH Supplying & installation of lift for 144 flats in Gr.II) | Do | 211.39 | 207.00 | 9.1207 | 8.808 | Nil | Nil |
| 8. | M/o completed work (NZ) M/s OTS (SH: Annual maintenance of lift at 320 M.S. flats at Motia Khan) | M/s OTIS Elevator Company Pvt. Ltd. | 5.08 5.16 | 30.6.08 29.6.09 | - | - | - | Nil |

- Details of deviation in works:

Details of deviations in works for the Month ending  July, 2008

| S. No. | Name of work | Name of Agency | Agreement No. | Estimated cost Tendered Amount | Amount (in lacs) |
| --- | --- | --- | --- | --- | --- |
| 1. | M/o sports complex near T.V. Tower Pitampura SH: shifting of security light pole. | M/s Gagan Projects | 22/EE/ED-8/DDA/2008-09 | 0.18 0.17 | Rs. 0.02 lacs |
| 2. | M/o Office building Vikas Minar. SH: EI & Fans wiring of lights power pts and building etc fitting in renovated reception Hall. Agmt. No. 61/EE/ED/DDA/2008-09 | M/s Pumps Engineering and Associate | 6/EE/ED/DDA/2008-09 | 1.17 0.99 | Rs. 0.18 lacs |
| 3. | M/o office building of Vikas Minar. SH: Annual maintenance of D.G. Sets, | M/s Lloyds Enterprises | 2/EE/ED-8/DDA/2007-08 | 0.67 0.65 | Rs. 0.10 lacs |
| 4. | M/o completed work (North Zone) SH; Annual maintenance of lift at 320 multistoried flat at Motia Khan block No. 2& 5 | M/s Otis Elevator Co. India. | 96 /EE/ED/DDA/2006-07 | 4.68 4.78 | Rs. 1.34 lacs |
| 5. | M/o completed scheme of N. A/c-II under S.W. Zone SH: Supply and Installation of additional submersible Pump set at DDA park Bhooli Bhaterari. Agmt. Agmt. No.13/EE/ED/DDA/2008-09 | M/s Gurman Bros | 13/EE/ED/DDA/2008-09 | 3.41 2.73 | Rs. 0.11 lacs |

- Restricted Call of Tenders.

Details of Restricted Call  of Tenders for the Month ending July, 2008

| S. No. | Name of work | Name of Agency | Amount (in lacs) |
| --- | --- | --- | --- |

-------------------------------------------------------------------------NIL ---------------------------------------------------------------------------------------------

5.	Rescinded Works:

Details of Rescinded Works- Status as on 31.07.08

| S. No. | Name of work | Agency | Agreement No. | Stipulated date of start Completion | Provisional extension granted upto | Date of rescission or work | Date of award of balance work | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | 2. | 3. | 4. | 5. | 6. | 7. | 8. | 9. |

------------------------------------------------------------------------------------------------------- Nil-----------------------------------------------------------------------

6.	Court Cases

A.	Details of Court Cases pending at the end July, 2008 Services matters.

| S. No. | Name of work | Agency | Agreement No. | Stipulated date of start Completion | Provisional extension granted upto | Date of rescission or work | Date of award of balance work | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | 2. | 3. | 4. | 5. | 6. | 7. | 8. | 9. |

------------------------------------------------------------------------------------------------------- Nil----------------------------------------------------------------------

6	Arbitration & related Court Cases.

B.	Details of Court Cases pending at the end July, 2008-Services matters

| S.L No. | File No | Name of Work | Name of Agency | Name of Court/ Suit No. | Name of Panel Lawyer | Nature of cases | Present position | Next | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |
| 1. | F 21 (122) 1999/ HC/Legal | C/o 448 MIG DUs at Pkt. KD Pitampura SH: IEI of 356 DUs in Gr.II | Bumbrah Elect Co V/s DDA | High Court CWO 2561/98 | Sh. D.S. Mahendru | Nil Arbrtn. Award challenged by agency in court | Argument continued | 27.8..2008 |  |
| 2. | F 12 (16) 1999/ TC/Legal | C/o 480 LIG houses at Pkt KD Pitampura SH: IEI | R.K. Angeja V/s DDA | Distt. Court 1996 A /95 | Sh. S.S. Mittal | Suit file for recovery of Rs. 97610/- levied as compensation | Argument continued | 08.09.08 |  |
| 3. | F 12 (429) 06/H C/Legal | Electrification of plot No. 4 Community Center Motia Khan | Rajesh Projects India Pvt. Ltd. V/s BSES Rajdhani Power Ltd. & others | WP (C) No. 8212/06 | Sh. Jag Mohan Sabherwal | Electrification of Community Center Motia Khan | Counter statement filed | 17.11.08 |  |
| 4. | F21(22)96/HC/Legal | D/o Land at JJR Colony Jahangirpuri SH: S/I of storm/ sewage pumps | Gita Pumps V/s DDA & MCD | OMP No. 1/96 | Sh. Bhupesh Narula | Arbitration award challenged | Argument continued | 22.10.08 |  |

7	Fire fighting Equipments (installed with locations)

| Sl. No. | Location | Electric driven pumps | Diesel driven pumps | Jocky pumps | Fire Extinguishers | Yard Hydrant | Fire Hydrant | Sprinkler |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |
| 1. | Rajendra Bhawan, Rajendera Place | 100HP-2 Nos. | 100BHP-1 No. | 20HP-I No. | 7 Nos. | 8 Nos | - | Provided in basement |
| 2. | Motia Khan (Ms housing) | 75HP- 1 No. | 100BHP-1 No. | 20HP-I No. | 5 Nos. | 12 Nos. | 20 Nos. | - |
| 3. | Jhandewallan | 75 HP-2 Nos | 75 BHP-i | 15HP-I | 2 Nos. | 7 Nos. | - | - |
| 4. | Vikas Minar | 100HP- 2 Nos. | 127 BHP-I No. | 25 HP-2 Nos. | 56 Nos. | 2 Nos. | 27 Nos. | Provided in basement & in all floors. ` |

8	EIS/EOT cases & Completion Certificate:

Details of EIS for the Month ending July, 2008

| S. No. | Name of work | Name of agency | Agreement No. | Estimated cost Tendered Amount | Stipulated Date of Start Stipulated Date of completion | Amount (in lacs) |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 |
| 1. | M/o office building Vikas Minar, Maintenance Air Conditioner & heaters, SH: S/I of Cossets type spreader A.Cs at Renovated reception Hall at vikas Minar. | M/s Air Puls | 26/EE/ED-8/DDA/2008-09 | 1.97 1.97 | 20.06.2008 30.06.2008 | 0.15 |
| 2. | M/o office building Vikas Minar . SH: EI & Fans wiring of light, power points and providing electrical fittings in renovated reception hall. | M/s Pumps Engineering & Associates | 6/EE/ED-8/DDA/2008-09 | 1.17 0.99 | 07.05.2008 13.06.2008 | 0.07 |
| 3. | M/o Remolding / redevelopment of Maharaja Suraj Mal Play ground at Nangloi. SH: Electrification of new cremation ground near Maharaja Suraj Mal Play ground. | M/s Satish Electricals | 91/EE/ED-8/DDA/2006-07 | 4.30 4.30 | 19.03.2007 20.06.2008 | 0.06 |
| 4. | M/o completed scheme NA-I under North Zone, MOEI & Fans at DDA Officers flats at B.D. road. SH: Repairing and servicing of Air-conditioners. | M/s Ritzy refrigeration and Air Conditioners | 12/EE/ED-8/DDA/2008-09 | 0.34 0.34 | 14.05.2008 24.05.2008 | 0.09 |

Details of EOT cases for the Month ending  July, 2008

| S. No. | Name of work | Agency | Agreement No. | Estt.Cost Ten. Amt. | EOT granted without levy of compensation | EOT granted with levy of compensation | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |
| 2. | M./o office building at Vikas Minar SH: Annual maintenance of D. G. Set | M/s Lloryds Enterprises | 2/EE/ED-8/DDA/2007-08 | 66523 65070 | 12/04.2008 to 19.6.2008 | - | - |
| 2. | M/o office Building at Vikas Minar : R/M/ of Air Conditioners , Coolers and Heaters SH: annual maintenance for water filter cum purifier) | M/s Fair Deal Technologies Pvt. Ltd. | 14/EE/ED-8/DDA/2007-08 | 28980 28224 | 20.05.08 to 19.06.2008 | - | - |
| 3. | M/o completed works (north Zone SH: Annual maintenance of lifts at 320 M.S. flats at Motia khan Block 2 & 5 | M/s Otis Elevator Company India Ltd. | 96/EE/ED-8/ DDA/2006-07 | 467808 477600 | 23.03.08 To 29.06.2008 | - | - |

9	Sanctioned Strength/In place/ vacancy

Position of Regular Staff

| S. No. | Designation | Sanction strength | Present strength | Shortfall |
| --- | --- | --- | --- | --- |
| 1. | Executive Engineer | 1 | 1 | Nil |
| 2. | Asst. Engineer | 5 | 5 | Nil |
| 3. | Junior Engineer | 17 | 13 | 4 |
| 4. | D/man Gr.II | 1 | 1 | Nil |
| 5. | AAO | 1 | 1 | Nil |
| 6. | Head Clerk/ Asst. | 1 | Nil | 1 |
| 7. | U.D.C. | 2 | 1 | 1 |
| 8. | I.D.C. | 7 | 5 | 2 |
| 9. | Steno | 1 | 1 | Nil |
| 10. | S.C. Driver | 2 | 2 | Nil |
| 11. | S/ Guard | 2 | 1 | 1 |
| 12. | Peon | 2 | 1 | 1 |

Sent to Director (System) through E-mail at

- ddatender@dda.org.in