DELHI DEVELOPMENT AUTHORITY

ELECTRICAL DIVISION NO. 8

LIST OF ACTIVITIES

1.	Details of Pending Final & non-refund of Security Deposits.

- Details of pending final bills for the Month ending August , 2008

| S. No. | Name of Work | Agency | Agreement No. | Stipulated date of start Completion | Actual date of completion | Date of payment of final bill | Reasons for delay in payment of final bill. |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | 2 | .3 | 4 | 5 | 6 | 7 | 8 |

.------------------------------------------------------------------------ NIL------------------------------------------------------------------------------------------------------------------

B.	Details of non-refund of Security Deposits for the Month ending August, 2008

| 0. | Name of Work | Agency | Agreement No. | Stipulated date of start Completion | Actual date of completion | Date of payment of final bill | Amount of Security Deposit deducted | Reasons for delay in refund of Security Deposit |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

.------------------------------------------------------------------------ NIL------------------------------------------------------------------------------------------------------------------

2.	Present status of work:

List of works costing more than Rs. 5.00 lacs for the month ending August, 2008

| S. No. | Name of Work | Agency | Estt. Cost Tendered amount (in lacs) | Stipulated date of start Completion | Actual Date of completion | Physical progress (in %age) | Reasons for delay in payment of final bill. |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | 2 | 3 | 4 | 5 | 6 | 7 | 8 |
| 1. | C/o 320/258 MS flats (SFS) at Motia Khan)` | M/s Goel Elect at work | 17.41 16.69 | 18.9.03 17.3.06 | Work in progress | 85% | — |
| 2. | C/o 560 SFS houses Cat.II in Blk, D Pkt. I, Shalimar Bagh SH: IEI of 192 SFS DU’s Gr.I (balance work) | M/w Goel Electrical | 7.06 15.48 | 10.1.08 9.1.09 | 9.1.09 | 67% | — |
| 3. | SH: IEI of 208 SFS DU’s Gr.II (balance work) | -do- | 9.10 1.92 | 10.01.08 09.01.09 | 63% | 72% | -do- |
| 4. | C/o 216. HIG DU’s (multistoried at Pitampura (near T.V. Tower) SH: C/o 72, HIG DU’s Multistoried superstructure including sanitary, installation, water supply, Sewerage drainage roads & paths and internal electrification all complete Gr.I. (composite tender) | M/s Ved Praksh Mittal & Sons | 22.57 50.50 Elect. Works | 25.10. 06 24.10.08 | 24.10.08 | 54% | Composites tender awarded by EE/ND-5 Ist inspection on 15.6.2007 |
| 5. | C/o 216 HIG DU’s (multistoried) at Pitampura SH: C/o 144 HIG DU’s (multistoried super structure including sanitary installation water supply & internal electrification all complete Gr. II. & (composite tender) | M/s Winner Constn, Pvt. Ltd | 45.18 73.08 Elect works | 14.12.06 13.12.08 | 13.1208 | 58% | Awarded by EE/ND Ist inspection on 25.7.07 |
| 6. | C/o 216 HIG DU’s (Multistoried i/c internal development at Pitampura near T.V. Tower completed (SH supplying & installation of lift for 144 flats in Gr.ii | M/s Schindler India & Pvt. Ltd | 105.59 103.50 | 09.12.07 08.09.08 |  | 80% | Complete material brought at site by agency |
| 7. | C/o 216 HIG DU’s (Multistoried) i/c intenral development at Pitampura near T.V. Tower completed (SH Supplying & installation of lift for 144 flats in Gr.II) | Do | 211.39 207.00 lacs | 09.12.07 08.09.08 | Work in progress | — | -do |
| 8. | M/o completed work (NZ) M/s OTS (SH: Annual maintenance of lift at 320 M.S. flats at Motia Khan) | M/s OTIS Elevator Company Pvt. Ltd. | 5.08 5.16 | 30.6.08 29.6.09 | - | Maintenance work | Nil |

- Details of deviation in works:

Details of deviations in works for the Month ending  August 2008

| S. No. | Name of work | Name of Agency | Agreement No. | Estimated cost Tendered Amount | Amount (in lacs) |
| --- | --- | --- | --- | --- | --- |
| 1. | Remodelling/Redevelopment of Maharaja Suraj Mal Play ground at Nangloi. SH: Electrification of new cremations ground near Maharaja Suraj Mal Play ground. | M/s-Satish Electricals | 91/EE/ED-8/DDA/2006-07 | 4.38 4.38 | Rs. 0.13 lacs |
| 2. | M/o completed works (N.Z.) SH:- Annual operation of lifts & D.G. Sets at 66 S.F.S. multistoried flats block B-1 motia Khan. | M/s Sudhir Elctricals | 23/EE/ED/DDA/2007-08 | 5.22 5.18 | Rs. 1.15 lacs |
| 3. | M/o completed scheme of N. A/c-II under S.W. Zone SH:- RMO of pumps and park lights Installed at Agrasen Park and Shastri Pard, in inder puri . | M/s S.k. Enterprises | 42/EE/ED-8/DDA/2007-08 | 1.32 0.84 | Rs. 0.4 lacs |
| 4. | M/o completed scheme of N. A/c-II under S.W. Zone SH:- RMO pumps fountains and park /path lights Installed at Prasad Nagar. | M/s S.K Enterprises | 43 /EE/ED/DDA/2007-08 | 1.72 1.21 | Rs. 0.05 lacs |
| 5. | M/o pump at various colonies under north zone SH:- ARMO at clear water p/set D.G.Set sub p/set at 560 S.F.S. houses cat- II Block-D Pkt-1 shalimar Bagh. | M/s Super System Engineers | 95 /EE/ED8/DDA/2006-07 | 3.31 3.75 | Rs. 0.93 lacs |
| 6. | M/o pump sets at various colonies under north zone SH:- ARMO at clear water p/set D.G.Set at Block-D Pkt-A shalimar Bagh. | M/s Super System Engineers | 4/EE/ED/8/DDA/2007-08 | 1.66 1.64 | Rs0.36 lacs |
| 7. | C/o Cricket Pavelion at sports complex Pitam pura near T.V. Tower Complex. SH: Providing Service cable and feeder pillar for cricket pavelions. | M/s Goeal Electric Works | 14//EE/ED/8/DDA/2008-09 | 4.80 3.16 | Rs.0.13 lacs |

- Restricted Call of Tenders.

Details of Restricted Call  of Tenders for the Month ending August, 2008

| S. No. | Name of work | Name of Agency | Amount (in lacs) |
| --- | --- | --- | --- |

-------------------------------------------------------------------------NIL ---------------------------------------------------------------------------------------------

5.	Rescinded Works:

Details of Rescinded Works- Status as on 31.08.08

| S. No. | Name of work | Agency | Agreement No. | Stipulated date of start Completion | Provisional extension granted upto | Date of rescission or work | Date of award of balance work | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | 2. | 3. | 4. | 5. | 6. | 7. | 8. | 9. |

------------------------------------------------------------------------------------------------------- Nil-----------------------------------------------------------------------

6.	Court Cases

A.	Details of Court Cases pending at the end August, 2008 Services matters.

| S. No. | Name of work | Agency | Agreement No. | Stipulated date of start Completion | Provisional extension granted upto | Date of rescission or work | Date of award of balance work | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | 2. | 3. | 4. | 5. | 6. | 7. | 8. | 9. |

------------------------------------------------------------------------------------------------------- Nil----------------------------------------------------------------------

6	Arbitration & related Court Cases.

B.	Details of Court Cases pending at the end August, 2008-Services matters

| S.L No. | File No | Name of Work | Name of Agency | Name of Court/ Suit No. | Name of Panel Lawyer | Nature of cases | Present position | Next | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |
| 1. | F 21 (122) 1999/ HC/Legal | C/o 448 MIG DUs at Pkt. KD Pitampura SH: IEI of 356 DUs in Gr.II | Bumbrah Elect Co V/s DDA | High Court CWO 2561/98 | Sh. D.S. Mahendru | Nil Arbrtn. Award challenged by agency in court | Argument continued | (Order issued for deputing the fresh arbtn, with in a 4 week) |  |
| 2. | F 12 (16) 1999/ TC/Legal | C/o 480 LIG houses at Pkt KD Pitampura SH: IEI | R.K. Angeja V/s DDA | Distt. Court 1996 A /95 | Sh. S.S. Mittal | Suit file for recovery of Rs. 97610/- levied as compensation | Argument continued | 06.10.08 |  |
| 3. | F 12 (429) 06/H C/Legal | Electrification of plot No. 4 Community Center Motia Khan | Rajesh Projects India Pvt. Ltd. V/s BSES Rajdhani Power Ltd. & others | WP (C) No. 8212/06 | Sh. Jag Mohan Sabherwal | Electrification of Community Center Motia Khan | Counter statement filed | 17.11.08 |  |
| 4. | F21(22)96/HC/Legal | D/o Land at JJR Colony Jahangirpuri SH: S/I of storm/ sewage pumps | Gita Pumps V/s DDA & MCD | OMP No. 1/96 | Sh. Bhupesh Narula | Arbitration award challenged | Argument continued | 22.10.08 |  |

7	Fire fighting Equipments (installed with locations)

| Sl. No. | Location | Electric driven pumps | Diesel driven pumps | Jocky pumps | Fire Extinguishers | Yard Hydrant | Fire Hydrant | Sprinkler |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |
| 1. | Rajendra Bhawan, Rajendera Place | 100HP-2 Nos. | 100BHP-1 No. | 20HP-I No. | 7 Nos. | 8 Nos | - | Provided in basement |
| 2. | Motia Khan (Ms housing) | 75HP- 1 No. | 100BHP-1 No. | 20HP-I No. | 5 Nos. | 12 Nos. | 20 Nos. | - |
| 3. | Jhandewallan | 75 HP-2 Nos | 75 BHP-i | 15HP-I | 2 Nos. | 7 Nos. | - | - |
| 4. | Vikas Minar | 100HP- 2 Nos. | 127 BHP-I No. | 25 HP-2 Nos. | 56 Nos. | 2 Nos. | 27 Nos. | Provided in basement & in all floors. ` |

8	EIS/EOT cases & Completion Certificate:

Details of EIS for the Month ending August, 2008

| S. No. | Name of work | Name of agency | Agreement No. | Estimated cost Tendered Amount | Stipulated Date of Start Stipulated Date of completion | Amount (in lacs) |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 |
| 1. | M/o Completed works North Zone. SH: Annual operation of lifts and DG sets, at 66 SFS flats Multistoried flats Block-B, Motia Khan. | M/s Sudhir Electricals | 23/EE/ED-8/DDA/2007-08 | 5.22 5.18 | 01.07.07 30.06.08 | 0.03 |
| 2. | C/o Cricket pavilion at Sport Complex Pitam Pura, Near TV Tower Complex. SH: Pdg. Service cable and feeder pillar for cricket pavilion. | M/s Goel Electric works | 14/EE/ED-8/DDA/2008-09 | 4.80 3.16 | 01.06.08 30.06.08 | 0.07 0.5 |
| 3. | M/o Completed works North Zone. SH: ARMO DG set, fire pump set and water supply pump set at 320 M.S. Flat under SFS at Motia Khan. | M/s N.K. Engg. Works | 68/EE/ED-8/DDA/2007-08 | 4.49 4.49 | 21.01.08 20.01.09 | 0.14 |
| 4. | M/o Various colonies under North Zone. SH: Operation & maintenance of clear water pump set at 656 MIG Houses at Jhangir Puri. | M/s Shiv Electric | 35/EE/ED-8/DDA/2007-08 | 1.73 0.78 | 08.10.07 08.10.08 | 0.7 |

Details of EOT cases for the Month ending  August, 2008

| S. No. | Name of work | Agency | Agreement No. | Estt.Cost Ten. Amt. | EOT granted without levy of compensation | EOT granted with levy of compensation | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |
| 1. | M./o office building at Vikas Minar- R/M of substation equipment and D.G. set SH:- supplying and laying of cable I/C providing adoptor box and top off box in rising-man. | M/s N.K.Engg. works | 76/EE/ED-8/DDA/2007-08 | 2.36 1.40 | 28/04.2008 to 07.07.2008 | - | - |
| 2. | M/o pump set at various colony under N.Z. SH:- Annual operation of clear water pump set and D.G. set at Block –D pkt-A Shalimar bagh. | M/s Super system Engineers | 4/EE/ED-8/DDA/2007-08 | 1.66 1.64 | 20.04.08 to 9.07.2008 | - | - |
| 3. | M/o pump set at various colony under N.Z. SH:- Annual Maintenance and operation of clear water pump set, DG set submersible pump set at 560 S.F.S houses category –II in Block –D Pkt-1 Shalimar bagh. | M/s Super system Engineers | 95/EE/ED-8/ DDA/2006-07 | 3.31 3.75 | 26.03.08 To 10.07.2008 | - | - |
| 4. | M/o completed works (N.Z.) SH:- Annual Operation of lifts & D.G. set at 66 S.F.S. Multistoryed Flats Block – B-1, Motia Khan . | M/s Sudhir Electricals. | 23/EE/ED-8/DDA/2007-08 | 5.22 5.18 | 30.06.2008 to 10.07.2008 |  |  |

9	Sanctioned Strength/In place/ vacancy

Position of Regular Staff

| S. No. | Designation | Sanction strength | Present strength | Shortfall | Excess |
| --- | --- | --- | --- | --- | --- |
| 1. | Executive Engineer | 1 | 1 | Nil |  |
| 2. | Asst. Engineer | 5 | 5 | Nil |  |
| 3. | Junior Engineer | 17 | 13 | 4 |  |
| 4. | D/man Gr.II | 1 | 1 | Nil |  |
| 5. | AAO | 1 | 1 | Nil |  |
| 6. | Head Clerk/ Asst. | 1 | Nil | 1 |  |
| 7. | U.D.C. | 2 | 1 | 1 |  |
| 8. | I.D.C. | 7 | 5 | 2 |  |
| 9. | Steno | 1 | 1 | Nil |  |
| 10. | S.C. Driver | 2 | 2 | Nil |  |
| 11. | S/ Guard | Nil | 1 | Nil | 1 |
| 12. | Peon | 2 | 2 | Nil |  |

Sent to Director (System) through E-mail at

- ddatender@dda.org.in