NIT

NIT No.	:	37(Re-invited)/EE/SWD-2/DDA/07-08

Name of Work	:	C/o 850 Mass Housing (170 HIG, 340 MIG, 340 LIG). Houses at Vasant Kunj, Near Sultangarhi.

S.H.	:	Design, Construct, Operate & Transfer of Mini S.T.P. of 0.30 M.L.D. (Interim Arrangement) Complete on Turnkey Basis.

Estimated Cost	:	Rs. 64,61,528/-

Earnest Money	:	Rs. 1,29,231/-

Cost of Tender	:	Rs. 1,000/-

Time Allowed	:	4 months

Particulars for Issue of Tender:-

Name of Contractor	:

Date of Application & Receipt

Tender issued on ________________ Cost of Tender _____________________

Date of opening of Tender

Executive Engineer

SWD-2, DDA

INDEX

S.No.	Particular of Document	Page No

1.	Press Tender Notice	1 - 3

2.	How to Apply/Method of Submission	5 - 9

3.	Background and Objective	9 - 11

4.	Scope of work		11

5.	General		13

6	Completion Schedule	15 - 17

7.	Stages of Payment	29

8.	General Rules & Directions	31 - 46

9.	Conditions (Clauses of Contract	447 – 208

10.	Sketch of Typical Cement Godown at site of Work	209

11.	Mile Stone		211

12.	Specimen form for Financial Bid	213 - 217

Executive Engineer

SWD-2, DDA

New Delhi

Delhi Development Authority

Press Tender Notice

NIT No. :

Sealed Tenders on turnkey basis are invited for the work of, Name of Work:- C/o 850 Mass Housing (170 HIG, 340 MIG, 340, LIG) houses at Vasant Kunj, Near Sultangarhi; S.H.: Design, Construct, Operate & Transfer of Mini S.T.P. of 0.30 M.L.D.  (Interim Arrangement) complete on Turnkey basis by Executive Engineer, SWD-2, DDA, Vasant Kunj, upto 3:00 p.m. on 26.04.2008 on behalf of DDA from the specialized agencies who fulfill the following conditions:

- Must have executed atleast one work of similar nature i..e construction & Commissioning of Sewage Treatment Plant.

- Should have a bank solvency not less than Rs. 30 Lacs.

by two bid system i.e. Technical bid & financial bid. The tender documents containing terms and conditions can be obtained from 11:00 a.m. to 5:00 p.m. on all working days from the office of EE – SWD-2, DDA Vasant Kunj, New Delhi on payment of Rs. 1000/- in Cash (Non-Refundable) as per time & schedule as under:-

Last date of Receipt of application for purchase of Tender form is 23.04.2008.

Last date of issue of tender upto 5:00 p.m. on 23.04.2008.

Estimated cost: Rs. 64,61,528/-

Time allowed: 4 Months

The sealed tender along with earnest money & necessary documents will be inserted in the tender will be inserted in the tender box placed at DDA Office, Vikas Sadan (Press Building) on 26.04.2008 upto 3:00 p.m. and some shall be opened on the same day at 3:30 p.m. in the presence of intending agencies or their authorized representatives.

The method of submission of tender is contained in the tender document.

The tender document can also be downloaded from DDA Website www.ddatender@dda.org.in. In that case the cost of tender and earnest money in the shape of demand draft drawn in favour of Sr. A.O. (CAU) SWZ shall accompany with tender documents & will be placed in the envelope of Technical bid.

Executive Engineer

SWD-2, DDA

1.0	How to Apply/Method of Submission

1.1	The tender shall be submitted by the intending agencies in two separate Envelopes ‘A’ and ‘B’.

1.1.1	The Envelope ‘A’ will contain the Technical Bid consisting of following documents

(i)	Tender form issued by DDA containing Terms & Conditions of Contract duly signed by the agency at appropriate places.

(ii)	Comprehensive Project Report as per Clause 2.0.0 (i) to (v) and 2.1.0 to 2.1.5

(iii)	List of similar type of works executed, mentioning the Technology employed, capacity of S.T.P. constructed & cost of construction.

(iv)	Performance report of client organisation

(v)	Latest Bank solvency report of amount not less than Rs. 30 Lacs

(vi)	Copy of Registration Certificate from Work Contract Cell of VAT Deptt. Of GNCTD and Certificate from agency that upto date returns have been filed along with copies of such return which have been submitted to Deptt of Trade & Taxes.

(vii)	List of Qualified Professionals with their biodata i..e Qualification and experience who will deal with this work.

(viii)	Earnest money in Cash Receipt deposit at Call receipt or fixed deposit receipt or demand draft of scheduled bank in favour of Sr. A.O. (CAU) SWZ either in full or minimum 50% in the shape of Currency Receipt/Treasury Challan Deposit/Deposit of Call Receipt or Fixed Deposit Receipt or Demand Draft of a

scheduled bank issued in favour of Sr. A.O. (CAU) SWZ/DDA and beyond 50% (Fifty percent) of earnest money in the shape of Bank Guarantee issued by a scheduled bank in favour of Sr. A.O. (CAU) SWZ can also be accepted.

(ix)	In case of tender documents obtained after downloading from DDA’s Website the cost of tender i.e. Rs. 1000/- in the shape of Demand Draft of a scheduled bank drawn in favour of Sr. A.O. (CAU) SWZ will also be attached.

1.1.2	(a)	The envelope ‘B’ will contain the Financial Bid, the rates will be quoted in the prescribed form & submitted separately

(b)	The agency should ensure that rate quoted should appear only in the financial bid and nowhere else. If rate are quoted elsewhere the tender will be summarily rejected.

1.1.3	Both the envelopes ‘A’ and ‘B’ shall be kept in a 3rd envelope marking the name of work, Date of opening, Name of firm, Name of Division on the face of envelope and will be inserted in tender box placed at DDA office Vikas Sadan.

1.1.4	The Technical Bid and Financial Bid shall be submitted simultaneously as explained above on due date. Only Technical Bid shall be opened on the day of opening of the tender, the Financial Bid shall be kept sealed.

1.1.5	The Technical Bid will be scrutinized first and approved by the Technical Bid Committee.

1.1.6	The Technical Bid will be sole property of DDA & will be approved by the Committee to be constituted by CE (SWZ)/SE CC-I whose decision shall be final & binding.

1.1.7	The Financial Bids shall be opened in respect of firms who are found qualified & meets the requirement of DDA

1.1.8	DDA reserve the right to accept or reject any or all applications and qualify or disqualify any or al applicants without assigning any reasons.

Delhi Development Authority

Invitation for Tender

2.0.0   Background & Objective:

DDA has constructed 850 Mass Housing consisting of 170 HIG, 340 MIG, 340 LIG houses at Vasant Kunj, near Sultangarhi. Before the flats are allotted to respective allottees DDA is committed to provide proper sewearage system. The internal sewerage in the housing scheme has already been laid by DDA along with construction of houses. At the present moment there is no outfall sewer line. The peripherial sewer line & STP are yet to be provided which is likely to take considerable time. After a long discussion at higher level it has been decided to provide STP capacity 0.30 MLD as an interim arrangement. For average discharge the required capacity of STP should have been kept 0.8 MLD, but as per the past experience as the houses are occupied gradually, so STP of capacity 0.30 MLD will serve the required purpose and has been decided as an interim arrangement. Ultimately the sewer line of housing will be connected to outfall sewer line which will be laid after the necessary approval of DJB. So DDA wants to construct a Mini STP having the following features.

- Should occupy minimum space.

- Since S.T.P. site is near houses, so the same should not emit any foul smell.

- Energy efficient upto the extent possible.

- Easy in operation and maintenance.

- The maintenance cost should be minimum as far as possible.

2.1.0	Scope of Work

2.1.1	Design construct, operate maintain for 3 years on Turnkey basis for the scheme of 850 Mass Houses at Vasant Kunj near Sultangarhi (actual No. of houses constructed 795). 1st Maintenance year will be free in accordance with clause-17 of Contract and subsequent 2 years will be paid on the basis of rates quoted under Financial bid.

2.1.2	The complete STP will be installed including the equalizing tank and the treated water effluent tank, the necessary arrangement for transferring the raw sewerage from the last manhole of the housing complex to the equalizing tank and further connection of STP to the treated water effluent tank will be made by the agency at their own cost. No sludge bed will be allowed to be constructed. The agency will be required to install sludge filter press. Keeping in view residential area nearby.

2.1.3	The cost of STP will include all works as explained above including cost of electrical, mechanical, plumbing works, sludge filter press, control panel, shed/room, cost of chemicals for treatment, skilled, unskilled workers, supervisory staff, T&P, errection and commissioning, laboratories facilities, lubricants, oil, grease etc.

2.1.4	For operation and maintenance of the STP the electric consumption will by borne by the department other consumable like chemicals etc. and staff for running and maintenance will be borne by the agency at their own cost.

2.1.5	The disposal/utilization of created gases will be made in such a way that it does not pose any Environmental problem/health hazard.

2.2.0	General

2.2.1	The depth of end manholes of sewer line will be 3.11 met (Approx) so STP will be designed accordingly.

2.2.2	The agency will be required to train the departmental staff also for future running & maintenance of plant before the same is handed over to DDA.

2.2.3	The agency will make all approaches to site, arrangement for storage of equipment/construction material during execution at his own cost.

2.2.4.	The agency is advised to visit the site also before tendering.

2.2.5	No change in design, structural arrangement of equipment as offered in the tender will be allowed subsequently except with the consent of Department in writing.

2.2.6	The agency will make his own arrangement of water and electricity for construction purposes at his own cost.

2.27.	The agency shall supply six sets of final drawing all cloth mounted & one set of original tracing of re-produceable quality of all approved drawings at appropriate stage for use of the authority. Till the time, the reproduceable drawings are supplied the agency will be liable to supply additional sets of drawings as may be required by the authority.

2.2.8	On completion of the project the agency shall provide two sets of CD of the entire project for future recordings of the authority.

2.2.9	The agency should offer the technology which is duly tested & STP on the technology is actually functional without emitting any kind of abnoxious smell.

2.3.0	Site Visit

The agency shall visit the site at the time of site demarcation, start at all important stages of progress of work to ensure for proper execution of design and details supplied by him. He shall also attend meeting as required by the Engineer in charge/Site Engineer or such other officer as the authority may authorize for this purposes at the respective officers or at the site in connection with the successful execution of the project. All local travelling expenses in connection with the preparation of drawings, site visits etc. for the successful execution of this scheme shall be borne by the agency.

3.0	Completion Schedule:

3.1	The work enumerated under scope of the service are to be completed in all respect within a period of 120 days from the day of the date of issue of acceptance letter by the authority as per schedule given below:

(i)	Submission of Layout plan for S.T.P. & Soil	30 days from date

Investigation Report	of award

(ii)	Submission of draft detailed structural &	45 days from date

architectural drawings & specification	of award

(iii)	Approval of draft detailed structural &	60 days from date

architectural drawing & specification by the	of award

Authority

(iv)	Installation of plant	105 days from

date of award

(v)	Final testing of plant i/c all services	120 days from

date of award

(vi)	Operation & maintenance (Free Service)	1 year after date

of completion

(vii)	Operations & Maintenance (Paid Service)	2 years beyond

(vi) above

3.2	If the Submission of drawing, soil investigation report etc gets delayed on any account beyond the consultant control, the period of completion shall be extended appropriately without any revision of financial term. However the time allowed for carrying the work as specified section 3.1 shall be strictly observed by the consultant and shall be deemed to be the essence of the agreement on the part of consultant. The work shall through out the stipulated period of the agreement (or such extended period the Engineer-in-charge may grant in writing for which agency shall request in advance giving the reason for the time extension required) be processed with all diligence and in the event of failure of the consultant to complete the work with in time schedule as specified above or extended period subsequently notified to him, the agency shall pay as compensation an amount equal to 1.50% per month of delay to be computed on per day basis of the accepted amount as the S.E. in Charge may decide on the total fee payable for such work remaining unfinished after the specified date subject to a maximum of 10% of the cost to be paid to the agency.

4.0	Payment:

The authority shall make payment to the agency towards the job incorporated in the scope of work.

@	(As per Annexure – II) of the cost of the project.

The break up of the payment is given in Annexure – I herein forming a part of this agreement.

5.4	Performance Guarantee:

(i)	The contractor shall submit an irrevocable performance guarantee of 5% (Five percent) of the tendered amount in addition to other deposit mentioned elsewhere in the contract for his proper performance of the contract agreement, (not withstanding and/or without prejudice to any

other provisions in the contract) within 15 days of issue of letter of intent. This period can be further extended by the Engineer-in-Charge upto a maximum period of 7 days on written request of the contractor stating the reason for delays in procuring the Bank Guarantee, to the satisfaction of the Engineer-in-Charge. The Guarantee shall be in the form of Government Securities or fixed deposit receipts or Guarantee Bonds of any Scheduled Bank of the State Bank of India in accordance with the form annexed hereto (Annexure-I). In case a fixed deposit receipt of any Bank is furnished by the contractor to the DDA as part of the performance guarantee and the bank is unable to make payment against the said fixed deposit receipt, the loss caused shall fall on the contractor and the contractor shall forthwith on demand furnished additional security to the DDA to make good the deficit.

(ii)	A letter of intent shall be issued in the first instance informing the successful tender for to the decision of the competent authority to accept his tender and the award letter shall be issued only after the Performance Guarantee in any of the prescribed form is received. In case of failure by the contractor to furnish the performance guarantee within the specified period Government shall without prejudice to any other right or remedy available in law, be at liberty to forfeit the earnest money absolutely.

(iii)	The Performance Guarantee shall be initially valid upto the stipulated date of a completion plus 60 days beyond that. In case the time for completion of works gets enlarged, the contractor shall get the validity of Performance Guarantee extended to cover such enlarged time for completion of work. After recording to the completion certificate for the work by the competent performance guarantee shall be returned to the contractor, without any interest.

(iv)	The Engineer-in-charge shall not make a claim under the performance guarantee for amounts to which the DDA is entitled under the contract (not withstanding and/or without prejudice to any other provisions in the contract agreement) in the event of:-

- Failure by the contractor to extend the validity of the Performance Guarantee as described of the herein above, in which event the Engineer-in-charge may claim the full amount of the Performance Guarantee.

(ii)	Failure by the contractor to pay DDA any amount due, either as agreed by the contractor or determined under any of the Clauses/Conditions of the agreements, within 30 days of the service of notice to this effect by Engineer-in-charge.

- In the event of the contract being determined or rescinded under provisions of any of the clause/condition of the agreement, the Performance Guarantee shall stand forfeited in full and shall be absolutely at the disposal of the DDA.

Annexure-I

Form of Performance Security

Bank Guaranty Bond

1.	In consideration of the Lt. Governor of Delhi (hereinafter called “The DDA”) having agreed under the terms and conditions of agreement no. ……………………………………dated………………… made between (hereinafter called “the said contractor(s)”)…………………………….. for the work……………………………………………………. (hereinafter called “the said agreement”) having agreed to production of a irrevocable Bank Guarantee for ………………………………. (Rupees…………………………………………………………………only) as a security/guarantee from the contractor(s) for compliance of his obligation in ……………………………… (hereinafter referred to as “the Bank”) (indicate the name of the bank) here undertake to pay to the DDA an amount not exceeding Rs. ………………………… (Rupees…………………………………………………………………. only) on demand by the DDA.

2.	We do hereby undertake to pay the amounts due (indicate the name of the Bank) and payable under this Guarantee without any demure, merely on a demand from the DDA stating that the amount claimed is required to met the recovery due or likely to be due from the said contractor(s). Any such demand made on the Bank shall be conclusive as regards the amount due and payable by the bank under this Guarantee. However, our liability under this guarantee shall be restricted to an amount not exceeding Rs. ……………............ (Rupees……………………………………………………………. only).

3.	We the said bank further undertake to pay to the DDA any money so demanded not withstanding any dispute or disputes raised by the contractor(s) in any suit or proceeding before any court or Tribunal relating thereto, our liability under this present being absolute and unequivalent. The payment so made by us under this bond shall be a valid discharge of our

liability for payment thereunder and the contractor(s) shall have no claim against us for making such payment.

4.	We……………………………………………. further agree that the guarantee herein (indicate the name of the Bank) contained shall remain in full force and effect during the period that would be taken for the performance of the said agreement and that it shall continue to be enforceable till all the dues of the DDA under or by virtue of the said agreement have been fully paid and its claim satisfied or discharged or till Engineer-in-Charge on behalf of the DDA certified that the terms and conditions of the said agreement have been fully and properly carried out by the said contractor(s) and accordingly discharge this guarantee.

5.	We…………………………………………………….. further agree with the DDA shall the (indicate the name of the Bank)……………………….. ………………………………………… fullest liberty without our consent and without effecting in any manner our obligations hereunder to vary any of the terms and conditions of the said agreement to extend time of performance by the said contractor(s) from time to time or to postpone for any time or from time to time any of the powers exercisable by the DDA against the said contractor(s) and to for bear or enforce any of the terms and conditions relating to the said agreement and we shall not be relieved from our liability by reason of any such variation, or extension being granted to the said contractor(s) or for any forbearance, act of omission on the part of the DDA or any indulgence by the DDA to the said contractor(s) or by any such matter or thing whatsoever which under the law relating to sureties would, but for this provisions have effect of so relieving us.

6.	This guarantee will not be discharge due to the change in the constitution of the Bank or the contractor(s).

7.	We……………………………………lastly undertake not to revoke this guarantee (indicate the name of the Bank) except with the previous consent of the DDA in writing.

8.	This guarantee shall be valid upto………………………………..unless extended on demand by DDA Notwithstanding anything mentioned above, our liability against this guarantee is restricted to Rs. …………... (Rupees………………………………………………………………….only) and unless a claim in writing is lodged with us within six months of the date of expiry or extended date of expiry of this guarantee all our liabilities under this guarantee shall stand discharged.

Date…………………………….. day of ………………………………. for ………..….………………………………. (indicate the name of the bank).

Annexure-II

Stages of Payment

| 1. | On submission of detailed layout & construction design of all elements of the scheme to DDA & approval by DDA | 5% |
| --- | --- | --- |
| 2. | On submission of Architectural, Structural drawings & specification. | 5% |
| 3. | On approval of Architectural & Structural drawings | 5% |
| 4. | On installation of plant | 50% |
| 5. | On final completion of the project i/c testing of plant & submission of one set of cloth mounted completion drawings two sets of CD of entire scheme | 25% |
| 6. | Running & Maintennace of plant to be maintained by the agency after completion of one year from date of completion | 10% |
| 7. | Operation of maintenance of plant for 2 years (Paid service) | As per accepted rate against quotation in Financial Bid |

Delhi Development Authority

General Rules & Directions

1.	In the event of tender being submitted by a firm, it must be signed separately by each partner thereof, or, the event of the absence of any partner, it must be signed on his behalf by a person holding a power of attorney authorizing him to do so, such power of attorney to be produced with the tender, and it must disclosed that the firm is duly registered under the Indian Partnership Act.

2.	Receipt for payments made on account of a work, when executed by a firm must also be signed by the several partners, except where the contractors are described in their tender as a firm, in which case the receipts must be signed in the name of the firm by one of the partners or by some other person having authority to give actual receipts for the firm.

3.	The Divisional Officer or his duly authorized assistant, will open tenders in the presence of any intending contractors who may be present at the time and will enter the amount of the several tenders in a Comparative Statement in a suitable form. In the event of a tenders being accepted a receipt for the earnest money forwarded therewith shall thereupon be given to the contractor who shall thereupon for the purpose of identification sign copies of the specifications and other documents mentioned in Rule 1 in the event of a tender being rejected, the earnest money forwarded with such unaccepted tender shall thereupon be returned to the contractor remitting the same.

4.	The officer inviting tenders shall have the right of rejecting all or any of the tender and will not be bound to accept the lowest tender.

5.	The receipt of an accountant or clerk for any money paid by the contractor will not be considered as an acknowledgement of payment to the Divisional Officer and the contractor shall be responsible for seeing that he procures a receipt signed by the Divisional Officer, or a duly authorized cashier CAU/SWZ/DDA.

6.	In the case of Item Rate Tenders, only rates quoted shall be considered. Any tender containing percentage below/above the rates quoted is liable to be rejected. Rates quoted by the contractor in item rates written in figure and words. However, if a discrepancy is found, the rate which correspond with the amount worked out by the contractor shall unless otherwise proved be taken as correct.

7.	Special care should be taken to write the rates in figures as well as in words and the amount in figures only in such a way that interpolation is not possible. The total amount should be written both in figures and in words. In case of figure the word Rs.                              Should be written before the figure of Rupees and ‘P’ after the decimal  figure e.g. Rs. 2.15 p. and in case of words the words Rupees should be precede and the word paise should be written at the end. Unless the rate is in whole Rupees and followed by the word only it should in variably be in two decimal places.

8.	On acceptance of the tender the name of the accredated representative of the contractor who would be responsible for taking instructions from the Engineer-in-charge shall be communicated to the Engineer-in-charge.

9.	Earnest money amounting to Rs. 1,29,231/- in Currency Receipt Challan/Call Deposit Receipt/Demand Draft of a Scheduled Bank Guaranteed by the Reserve Bank of India must accompany with each tender and each tender is taken sealed cover tender for above and address to EE.

(a)	The contractor whose tender is accepted shall execute an agreement on Rs. 50/- stamp paper regarding his acceptance of the execution of work on the rate and conditions as set in the contract document. The issue of tender form will be stopped i.e. (four) days before the date fixed for opening of tender.

10.	The person/persons, whose tender(s) may be accepted (hereinafter called the contractor) shall permit DDA at the time of making any payment to him for work done under the contract to deduct a sum at the rate of 10% of the gross amount of each running bill till the same along with the sum already deposited as earnest money. Will amount to security deposit of 5% of the tendered value of the work. Such deductions will be made and held by DDA byway of Security Deposit unless he/they has/have deposited the amount of Security at the rate mentioned above in cash or in the form of Government Security at the rate mentioned above in cash or in the form of Government Securities or fixed deposit receipts. In case a fixed deposit receipt of any Bank is furnished by the contractor to the DDA as part of the security deposit and the Bank is unable to make payment against the said fixed deposit receipt, the loss caused thereby shall be on the contractor and the contractor shall forthwith on demand furnish additional security to the DDA to make the deficit.

All compensations or the other sums of money payable by the contractor under the terms of this contract may be deducted from, or paid by the sale of a sufficient part of his security deposit or from the interest arising there from, or any sums which may be due to or may become due to the contractor by DDA on any account whatsoever and in the event of his Security Deposit is being reduced by reason of any such deductions or sale as Scheduled Banks or Government Securities (if deposited for more than 12 months) endorsed in favour of the Engineer-in-Charge, any sum or sums which may have been deducted from, or raised by sale of his security deposit or any part thereof, the Security Deposit shall be collected from the running bills of the contractor at the rates mentioned above and the Earnest Money if deposited in cash at the time of tenders will be treated a part of the Security Deposit.

(a)	Government papers tenders as security will be taken @ 5% (five percent) below its market price or at its face value, whichever is less. The market price of Government paper would be as curtailed by Divisional Officer at the time of collection of interest and the amount to interest of the extent of deficiency in value of the Government paper will be with-held if necessary.

(b)	Government securities will include all forms of securities mentioned in rule 274 of the G.F.R. except fidelity Bonds. This will be subject to the observance of the conditions mentioned in rule 274 of the G.F.R. except fidelity Bonds. This will be subject to the observance of the conditions mentioned under this rule against each form of security.

11.	The acceptance of the tender will rest with the competent authority who does not bind himself to accept the lowest tender and reserve himself the authority to reject any of all the tenders without assignment any reason all the Tenders which does not fulfill the prescribed condition or in any respect are liable to rejected.

12.	Canvassing in connection with tenders is strictly prohibited and the tender submitted by the contractor who resort to canvassing shall b liable to rejection.

13.	(a)	It may please be carefully noted that no condition whatsoever shall be accepted by the department and the contractor is not prepared to execute the work at the terms and conditions contained in the tender documents, he is requested not to tender for this work. It may be noted that if any contractor choose to submit conditional tender inspite of clear direction given above, his tender shall be liable to rejected summarily and his full earnest money shall stand forfeited. He will be liable for being debarred from tendering in DDA for a period of six months.

(b)	Monthly payment to the contractor will be made when the gross amount of the work done during the previous months is not less than indicated below:

Amount of contract		Gross value of works since

Previous bill should exceed

Over Rs. 10 lacs value		Rs. 25,000/-

14.	Sales tax, Cess tax, if any or any other tax on material in respect of this contract shall be payable by the contractor and DDA will not entertain any claim whatsoever in this respect

15.	A contractor shall not be permitted to tender for works in the DDA Zone responsible for award and execution of contracts) in which any of his near relatives is posted as Divisional Accountant or as an officer in any capacity between the grades of CE and JE (both inclusive) in the DDA. He shall intimate the names of the persons who are working with him in any capacity or who are subsequently employed by him and who are near relatives of any Group A, B or C officers in the DDA. Any breach of this condition by the contractor would render him liable to action under clause 3 of the agreement. In addition, he would also be liable  to be debarred from tendering in future.

16.	The contractor shall give a list of non-gazetted DDA employees related to him.

17.	No Engineer of Gazetted rank or other Gazetted officer employed in Engineering of Administrative duties in an Engineering Deptt. Of the Govt. of India/Delhi Development Authority is allowed to work as contractor for a period of two years of his retirement from Govt. Service/Delhi Development Authority. This contract is liable to be cancelled if either the contractor or any of his employees are found at any time to be such a person who had not obtained the permission of the Govt. of India/Delhi Development Authority as aforesaid before submission of the tender or engagement in the contractor’s service. The Engineering Deptt. of Govt. of India includes the Engineering Deptt. Of DDA, CPWD, MES, P&T.

18.	The tender for the work shall remain open for acceptance for a period of sixty days from the date of opening of tenders. If any tenderer withdraws his tender before the said period or issue of letter of acceptance, whichever is earlier, or makes any modifications in terms and conditions of the tender which are not acceptable to the department, then the DDA shall, without prejudice to any other right or remedy, be at liberty to forfeit 50% of the said earnest money as aforesaid.

19.		Case of Withdrawal     Action to be taken
	of offer

| (i) | If the contractors/ withdraw their offer within 60 days of quoting the rates | The 50% earnest money deposited by the contractor shall be forfeited absolutely |
| --- | --- | --- |
| (ii) | If the contractor withdraw his offer immediately after the award of work | The earnest money deposited by the contractor shall be forfeited absolutely |
| (iii) | If the contractor/agency withdraw his offer after award of work after taking over possession of site | It is deemed that the contractor has entered into contract and the action under clause 2 & 3 of the agreement i.e. taking up work at the risk and cost of the Contractor and to penalize the contractor for not completing the work within abandons the site after taking over the possession of the site. It is further clarified that action under clause 2&3 of the agreement is attracted even though the contractor fails to sign the agreement of Rs. 50/- non-judicial stamp paper but do not start the work from the tenth day after the date on which the order to commence the work is issued to contractor. The date of start of the work will be considered as date of taking over the possession of site. In case of tender for supply of material the documentary proof for start of work will be the submission of samples for approval to Engineer-in-charge i.e. in case the supply order is given to the contractor and if he fails to supply the materials then action under clause 2 and 3 is attracted. |
| (iv) | The quotation of the work shall remain open for a period of 60 days from the date of opening of quotation. The DDA shall without prejudice to any other right or remedy be at liberty to forfeit 50% of the earnest money if any quotationer withdraws his quotation before the said period or makes any modification in the terms & condition of the offer which are not acceptable to the department and to forfeit the whole of the earnest money (if the quotationer whose quotation is accepted fails to commence the work/supply specified in the NIT along with changes in the scope if any) in the prescribed time or abandons the work/supply before the completion, said period or makes any modification in the terms & condition of the offer which are not acceptable to the department and to forfeit the whole of the earnest money (if the quotationer whose quotation is accepted fails to commence the work/supply specified in the NIT along with changes in the scope if any) in the prescribed time or abandons the work/supply before its completion. |  |

20.	The tenderer shall engage the services of specialized consultant/agencies required with the planning/execution of the above project after obtaining written permission of the Divisional Officer.

21.	All the material required for completion of the project is to be arranged by the contractor and no material shall be supplied by the Delhi Development Authority.

22.	The contractor whose tender is accepted will be required to furnish the performance guarantee bond (unconditional) on the prescribed proforma (Annexed with tender document) in the shape of bank guarantee issued by a scheduled bank guaranteed by Reserve Bank of India for an amount equivalent to 5% of the contract value, as a security for compliance with his obligation in accordance with the contract within 15 days from the date of award of the work on Non-judicial stamp paper of Rs. 50/-.

Conditions of Contract

Definitions:

(1)	The contract means the documents forming the tender and acceptance there of and the formal agreement executed between the Delhi Development Authority and the Contractor, together with the documents referred to therein including these conditions, the specifications, designs, drawings and instructions, issued from time to time by the Engineer-in-charge and all these documents taken together, shall be deemed to form one contract and shall be complementary to one another.

(2)	In the contract the following expressions shall thereof unless the context otherwise required, have the meaning hereby respectively assigned to them.

(a)	The expression ‘Works’ or ‘Work’ shall there of unless there be something either in the subject or context repugnant to such construction, be constructed and taken to mean the work by or by virtue of the contract contracted to be executed whether temporary or permanent and whether original, altered, substituted or additional.

(b)	The ‘Site’ shall mean the land and/or other places on, into or through which work is to be executed under the contract or any adjacent land, path or street through which work is to be used for the purpose of carrying out the contract.

(c)	The ‘Contractor’ shall mean the individual of firm or company whether in corporate or not, undertaking the works and shall include the legal personal representative or such individual or the persons confirming such firm or company, or the successors of such firms or company and the permitted assignee of such individual or firms or company.

(d)	The ‘Authority’ or ‘DDA’ means Delhi Development Autohrity.

(e)	The ‘Engineer-in-Charge’ means the Divisional Officers who shall supervise and be incharge of the work and who shall sign the contract on behalf of the Delhi Development Authority.

(f)	‘Chairman, Government’ or ‘Government of India’ shall mean the V.C. DDA of Delhi.

(g)	The Term ‘Chief Engineer’ means concerned Zonal Chief Engineer Delhi Development Authority. Words imparting the singular number, include the plural number and Vice-Versa.

(h)	The Chief Technical Examiner/Technical Examiner means the Chief Technical Examiner, Central Vigilance Commission, Govt. of India.

3.	The several documents forming the contract are to be taken as mutually explanatory of one another, detailed drawings being followed in presence to small scale drawing and figured dimensions in preference to scale and special conditions in preference to General Conditions.

3.1	In the case of discrepancy between the schedule of Quantities, the Specifications and/or the Drawings, the following order of preference shall be observed:-

(1)	Description of Schedule of Quantities.

(2)	Particular specification and Special Condition, if any

(3)	Drawings

(4)	CPWD Specification

(5	Indian Standard Specifications of BIS

3.2	If there are varying are conflicting provisions made in any one document forming part of the contract the Accepting Authority shall be the deciding authority with regard to the intention of the documents and his decision shall be final and binding on the contractor.

3.3	Any error in description, quantity or rate in Schedule of Quantities or any omission there from shall not vitiate the Contract or release the Contractor from the execution of the whole or any part of the works comprised therein according to drawings and specifications or from any of his obligation under the contract.

Clause 1. The person/persons, whose tender(s) may be accepted (hereinafter called the contractor shall permit DDA at the time of making any payment to him for work done under the contract to deduct a sum at the rate of 10% of the gross amount of each running bill till the sum along with the sum already deposited as earnest money, will amount to security deposit of 5% of  the tendered, vale of the work . Such deductions will be made and held by DDA by way of Security Deposit unless he/they/has/have deposited the amount of Security at the rate mentioned above in cash or in the form of Government Security at the rate mentioned above in cash or in the form of Government Securities or fixed deposit receipts. In case a fixed deposit receipt of any Bank is furnished by the contractor to the DDA as part of the security deposit and the Bank is unable to make payment against the said fixed deposit receipt, the loss caused thereby shall fall on the contractor and the contractor shall forthwith on demand furnish additional security to the DDA to make good the deficit.

All compensations or the other sums of money payable by the contractor under the terms of this contract may be deducted from, or paid by the sale of a sufficient part of his security deposit or from the interest arising there from, or any sums which may be due to or may become due to the contractor by DDA on any account whatsoever and in the event of his Security Deposit being reduced by reason of any such deductions or sale  as aforesaid, the contractor  shall within 10 days make good in cash or fixed deposit receipt tendered by the State Bank of India or by Scheduled Banks or Government Securities (if deposited for more than 12 months) endorsed in favour of the Engineer-in-Charge, any sum or sums which may have been deducted from, or raised by sale of his security deposit or any part thereof, the Security Deposit shall be collected from the running bills of the contractor at the rates mentioned above  and the Earnest Money if deposited in cash at the time of tenders will be treated a part of the Security Deposit.

Note:	(1)	Government papers tendered as security will be taken @ 5% (five percent) below its market price or at its face value, whichever is less. The market price of Government paper would be as certained by Divisional Officer at the time of collection of interest and the amount to interest of the extent of deficiency in value of the Government paper will be with-held if necessary.

(2)	Government securities will include all forms of securities mentioned in rule 274 of the G.F.R. except fidelity Bonds. This will be subject to the observance of the conditions mentioned under this rule against each form of security.

Clause 1A. Performance Guarantee

(i) The contractor shall submit an irrecoverable performance guarantee of 5% (Five Percent), of the tendered amount in addition to other deposits mentioned elsewhere in the contract for the proper performance of the contract agreement, (not withstanding and/or without prejudice to any other provisions in the contract) within 15 days of issue of letter in intent. This period can be further extended by the Engineer-in-Charge upto a maximum period of 7 days on written request of the contractor stating the reason for delays in procuring the Bank Guarantee, to the satisfaction of the Engineer-in-Charge. This Guarantee shall be in the form of Government Securities or fixed deposit receipts or Guarantee Bonds of any Scheduled Bank or the State Bank of India in accordance with the form annexed hereto (Annexure-1). In case a fixed deposit receipt of any Bank is furnished by the contractor to the DDA, as part of the performance guarantee and the bank is unable to make payment against the said fixed deposit receipt, the loss caused shall fall on the contractor and the contractor shall forthwith on demand furnish additional security to the DDA to make good the deficit.

(ii) A letter of intent shall be issued in the first instance informing the successful tender for the decision of the competent authority to accept his tender and the award letter shall be issued only after the Performance Guarantee in any prescribed form is received. In case of failure by the contractor to furnish the performance guarantee within the specified period Government shall without prejudice to any other right or remedy available in law, be at liberty to forfeit the earnest money absolutely.

(iii) The Performance Guarantee shall be initially valid upto the stipulated date of completion plus 60 of beyond that. In case the time for completion of works gets enlarged, the contractor shall get validity of Performance Guarantee extended to cover such enlarged time of completion of work. After recording of the completion certificate for the work by the competent authority, the performance guarantee shall be returned to the contractor, without any interest.

(iv) The Engineer-in-charge shall not make a claim under the performance guarantee except for amounts to which the DDA is entitled under the contract (not withstanding and/or without prejudice to any other provisions in the contract agreement) in the event of:-

(a)	Failure by the contractor to extend the validity of the Performance Guarantee as described of the hereinabove, in which event the Engineer-in-Charge may claim the full amount of the Performance Guarantee.

(b)	Failure by the contractor to pay DDA any amount due, either as agreed by the contractor or determined under any of the Clauses/Conditions of the agreements, within 30 days of service of notice to the effect by Engineer-in-charge.

(v) In the event of the contract being determined or rescinded under provisions of any of the clause/condition of the agreement, the Performance Guarantee shall stand forfeited in full and shall be absolutely at the disposal of the DDA.

Note: Note 1 & 2 given under clause 1 shall be applicable for Clause 1A.

Clause 2. If the contractor fails to maintain the required progress in terms of clause 5 or to complete the work and clear the site on or before the contract or extend date of completion, he shall , without prejudice to any other right or remedy available under the law to the DDA on account of such breach, pay as agreed compensation the amount calculated at the rates stipulated below as the Superintending Engineer (Whose decision in writing shall be final and binding) may decide on the amount of tendered value of the work for every completed day/months (as applicable) that the progress remains below that specified in Clause 5 or that the work remains incomplete. This will also apply to items or group of items for which a separate period of completion has been specified. Compensation for delay of work @ 1.5% per month of delay to be computed on per day basis. Provided always that the total amount of compensation for delay to be paid under this condition shall not exceed. 10% of the Tendered value of work or to the Tendered Value of the item or group of items of work for which is separate period of completion is originally given.

The amount of compensation may be adjusted or set-off against any sum payable to the Contractor under this or any other contract with the DDA. In case, the contractor does not achieve a particular milestone mentioned in Annexure-II or the rescheduled milestone(s) in terms of Clause 5.4, the amount shown against that milestone shall be withheld, to be adjusted against the compensation levied at the final grant of extension of time. With-holding of this amount on failure to achieve a milestone, shall be automatic without any notice to the contractor. However, if the contractor catches up with the progress of work on the subsequent milestone(s), the withheld amount shall be released. In case the contractor fails to make up for the delay in subsequent milestone(s), amount mentioned against each milestone missed subsequently also shall be with-held. However, no interest, whatsoever, shall be payable on such withheld amount.

Clause 3. The Engineer-in-Charge may without prejudice to his right against the contractor in respect of any delay or interior workmanship or otherwise on to any claims for damage in respect of this contract or otherwise and whether the date for completion has or has not elapsed by notice in writing absolutely determine the contract in any of the following cases:

(i)	If the contractor having been given by the Engineer-in-Charge a notice in writing to rectify, reconstruct or replace any defective work or that the work is being performed in an inefficient or otherwise improper or unworkman like manner shall omit to comply with the requirements of such notice for a period of seven days thereafter.

(ii)	If the contractor being a company shall pass a resolution or the court shall make an order that the company shall be wound up or if a receiver or a manager on behalf of a creditor shall be appointed or if circumstances shall arise which entitled the court or the creditor to appoint a receiver or a manager any of or which entitle the court to make a winding up order.

(iii)	Deleted

(iv)	If the contractor has, without reasonable cause, suspended the progress of the work of has failed to proceed with the work with due diligence so that in the opinion of the Engineer-in-Charge (which shall be final and binding) he will be unable to secure completion of the work by the date for completion and continues to do so after a notice in writing of seven days from the Engineer-in-Charge.

(v)	If the contractor fails to complete the work within the stipulated dated or items of work with individual date of completion, if any stipulated, on or before such date(s) of completion and does not complete them within the period specified in a notice given in writing in that behalf by the Engineer-in-Charge.

(vi)	If the contractor persistently neglects to carry out his obligations under the contract and/or commits default in complying with any of the terms and conditions of the contract and does not remedy it or take effective steps to remedy it within 7 days after a notice in writing is given to him in that behalf by the Engineer-in-Charge.

(vii)	If` the contractor commits any acts mentioned in clause 21 hereof.

(viii)	If the work is not started by the contractor within, 1/8th of stipulated time. When the contractor has made himself liable for action under any of the cases aforesaid, the Engineer-in-Charge on behalf of the DDA shall have powers:

(a)	To determine to rescind the contract as aforesaid (of which termination or rescission notice in writing to the contractor under the hand of the Engineer-in-Charge shall be conclusive evidence). Upon such determination or rescission the Earnest Money deposit, Security Deposit already recovered and Performance Guarantee under contract shall be liable to be forfeited and shall be absolutely at the disposal of the DDA.

(b)	Deleted

(c)	After giving notice to the contractor to measure the work of the contractor and to take such while of the balance or part thereof, as shall be un-executed out of his hands and to give it to another contractor to complete the work. The contractor, whose contract is determined or rescinded as above, shall not be allowed to participate in the tendering process for the balance work.

In the event of above courses being adopted by the Engineer-in-Charge, the contractor shall have no claim to compensation for any loss sustained by him by reasons of his having purchases or procured any material or entered into any engagements or made any advances on account or with a view to the execution of the work or the performance of the contract. And in case action is taken under any of the provision aforesaid the contractor shall not be entitled to recover or be paid any sum for any work thereof or actually performed under this contract unless and until the Engineer-in-Charge has certified in writing the performance of the contract. And in case action is taken under any of the provision aforesaid the contractor shall not be entitled to recover or b paid any sum for any work thereof or actually performed under this contract unless and until the Engineer-in-Charge has certified in writing the performance of such work and the value payable. In respect thereof and he shall only be entitled to be paid the value so certified.

Clause 3A. 	In case, the work cannot be started due to reasons not within the control of the contractor within 1/8th of the stipulated time for completion of work, either party may close the contract. In such eventually, the Earnest Money Deposit and the Performance Guarantee of the contractor shall be refunded, but no payment on account of interest, loss of profit or damages etc. shall be payable at al.

Clause 4. In any case in which any of the powers conferred upon the Engineer-in-Charge by Clause 3 hereof, shall have become exercisable and the same are not be exercised, the non-exercise thereof shall not constitute waive of any of the conditions hereof and such power shall not withstanding be exercisable in the event of any of the conditions in the event of any future case of default by the contractor and the liability of the contractor for the compensation shall remain unaffected. In the event of the Engineer-in-Charge putting in force all or any of the power vested in him under the preceding clause  he may, if he so desires after giving a notice in writing to the contractor, take possession of (or at the sole  discretion of the Engineer-in-Charge putting in force all or any of the power vested in him under the preceding clause he may, if he so desires after giving a notice in writing to the contractor, take possession of (or at the sole discretion of the Engineer-in-Charge which shall be final) and binding on contractor use as on hire (the amount of the hire money being also in the final determination of the Engineer-in-Charge) all or any tools, plants, materials and stores, in or upon the works, or the site thereof, belonging to the contractor, or procured by the contractor and intended to be used for the execution of those work or any part thereof paying or allowing for the same in account at the contract rates or in the case of these not being applicable at current market rates to be certified by the Engineer-in-Charge, whose certificate there of shall be final and binding on contractor otherwise the Engineer-in-Charge by giving notice in writing may order the contractor, or his clerk of the work, foreman or other-authorised agent to remove such tools, plants, materials or stores from the premises (within a time to be specified in such notice) and in the event of the contractor failing to comply with any such requisition of the Engineer-in-Charge may  remove them at the contractor’s expense or sell them by auction or private shale on account of the contractor and at his risk in all respect and the certificate of the Engineer-in-Charge as to the expense of any such removal and the amount of the proceeds and expense of any such sale shall be final and conclusive against the contractor.

Clause 5. The time allowed for execution of the works as specified in the Annexure-II or the extended time in accordance with these conditions shall be the essence of the Contract. The execution of the works shall commence from the 15th Day or such time period as mentioned in letter of Award after the date on which the Engineer-in-Charge issue written orders to commerce the work or from the date of handing over of the site whichever is later. If the contractor commits default in commencing the execution of the work as aforesaid. DDA shall without prejudice to any other right or remedy available  in law, be at liberty to forfeit the earnest money & performance guarantee absolutely.

Clause 5.1. As soon as possible after the Contract is concluded the Contractor shall submit a Time & Progress Chart for each mile stone and get it approved by the Department. The Chart shall be prepared in direct relation to the time stated in the contract documents for completion of items of the works. It shall indicate the forecast of the dates of commencement and completion of various trades of sections of the work and may be amended as necessary by agreement between the Engineer-in-Charge and the Contractor within the limitations of time imposed in the contract documents, and further to ensure  good progress during the execution of the work, the contractor shall in all cases in which the time allowed for any work, exceeds one month (save for special jobs for which a separate programme has been agreed upon) complete the work as per milestones given in Annexure-II.

Clause 5.2. If the work(s) be delayed by:-

(i)	force majeure, or

(ii)	abnormally bad weather, or

(iii)	serious loss or damage by fire, or

(iv)	civil commotion, local commotion of workmen, strike or lockout, affecting any of the trades employed on the work, or

(v)	delay on the part of other contractors or tradesmen engaged by Engineer-in-Charge in executing work not forming part of the contract, or

(vi)	non-availability of stores, which are the responsibility of Government/DDA to supply or

(vii)	non-availability or break-down of tools and plant to be supplied or supplied by Government/DDA, or

(viii)	ay other cause which, in the absolute discretion of the authority mentioned in Annexure-II is beyond the contractor’s control.

then upon the happening of any such event causing delay, the contractor shall immediately give notice thereof in writing to the Engineer-in-Charge but shall nevertheless use constantly his best endeavours  to prevent or make good the delay and shall do all that may be reasonably required to the satisfaction of the Engineer-in-Charge to proceed with the works.

Clause 5.3. Request for rescheduling of mile stones and extension of time, to be eligible for consideration, shall be made by the contractor in writing within fourteen days of the happening of the event causing delay on the prescribed form. The Contractor may also, if practicable, indicate in such a request the period for which extension is desired.

Clause 5.4. In any such case the authority mentioned in Annexure-II may give a fair and reasonable extension of time and reschedule the milestones for completion of work. Such extension shall be communicated to the Contractor by the Engineer-in-Charge in writing, within 3 months of the date of receipt of such request, Non application by the contractor for extension of time shall not be a bar for giving a fair and reasonable extension by the Engineer-in-Charge and this shall be binding on the contractor

Clause 6. Within 10 days of the completion of the work the contractor shall give notice of such completion to the Engineer-in-Charge and within 10 days of the receipt of the such notice the Engineer-in-Charge shall inspect the work and if there is not defect in the work, he shall furnish the contractor with a certificate of completion, otherwise a provisional certificate indicating defect (a) to be rectified by the contractor and/or (b) for which payment will be made at reduced rates, shall be issued but not certificate of completion, provisional or otherwise, shall be issued nor shall the work be considered to be complete until the contractor shall have removed from the premises on which the work shall  have been erected or constructed by people on the site in connection with the execution of the work shall have been erected or constructed by the contractor(s) and cleaned of the dirt from all wood work, doors, windows, walls, floors or other parts of any building in upon or about which work is to the executed, or of which he may have had possession for the purpose of the execution thereof, and not until the work, doors, windows, walls, floors or other parts of any building in upon or about which work is to be executed, or of which he may have had possession for the purpose of the execution thereof, and not until the work is to be executed, or of which he may have had possession for the purpose of the execution thereof, and not until the work shall have been measured by the Engineer-in-Charge. If the contractor fails to comply with the requirements of this clause as to removal of scaffolding, surplus materials and rubbish and all huts and sanitary arrangements as aforesaid and cleaning of dirt on or before the date fixed for the completion of work in Engineer-in-Charge may at the expense of the contractor remove such scaffolding, surplus materials and rubbish etc. and dispose of same as he think fit and clean of such dirt as aforesaid, and the contractor shall have not claim in respect of any such scaffolding or surplus materials as aforesaid accept for any sum realized by the sale thereof.

Clause 7. No payment shall be made for a work estimated to cost rupees five thousand or less till after the whole of the work shall have been completed and certificate of completion given. But in the case of work estimated to cost more than Rs. Five thousand, the contractor shall, on submitting the bill be entitled to receive a monthly payment proportionate to the part thereof then executed to the satisfaction in of the Engineer-in-Charge, whose certificate of the sum so payable shall be regarded as payment by way of advance against the final payment only and not as payments for work actually done and completed and shall not preclude the requiring of bad, unsound and imperfect or unskilled work to be removed and taken away and reconstructed, or effected or be considered  as an admission of the due performance of the contract, or any part thereof, in any respect or the accrual of any claims, nor shall it conclude, determine, or affect in any way the powers of the Engineer-in-Charge under these conditions or any of them as to the final settlement and adjustment of the accounts or otherwise or in any other way very or affect the contract. The final bill shall be submitted by the contractor within one month of the date fixed  for completion of the work or of the date of the certificate of competition furnished by the Engineer-in-Charge  and payment shall be made within three months with amount of the contract pulsate of additional items is up to Rs. 2 lacs and in 6 months if the same exceeds Rs. 2 lacs of the submission of such bill. If there shall be any dispute about any items of the work than the undisputed items of items only shall be paid within the sad period of three months or six months or as the case may be. The contractor shall submit a list of the disputed items within thirty days from the disallowance thereof and if he fails to do this, his claim shall be deemed to have been fully waived and absolutely extinguished.

“Wherever there is likely to be delay in recording detailed measurements for making running payments in the case of residential building, advance payment without detailed measurements for works done (other than foundation and finishing items) upto (a) lintel level (including sun shade etc.) and (b) slab level, for each floor, worked out at 75% of the tendered rates may be made in running accounts bill by the Engineer-in-Charge at his discretion on the basis of certificate from the assistant Engineer to the effect that the work has been completed upto the level in question.

The advance payment so allowed shall be adjusted in the subsequent running bill by taking detailed measurement thereof. Final payment shall be made only on the basis of detailed measurements.

Clause 8. A bill shall be submitted by the contractor each month or before the date fixed by the Engineer-in-Charge for all work executed in the previous month, and the Engineer-in-Charge shall take or cause to be taken the requisite measurements for the purpose of having the same verified, and the claim, as far as admissible, adjusted as far as possible before the expiry of ten days from the presentation on the bill. If the contractor does not submit the bill within the time fixed as aforesaid, the Engineer-in-Charge may depute with in seven days of the date fixed as aforesaid, as subordinate to measure up his said work in presence of the contractor whose counter signature to measurement list will be sufficient warrant, and the Engineer-in-Charge may prepare a bill from such list.

Clause 8.A. Before taking any measurement of any work as has been referred to in Clause 6, 7 and 8 thereof the Engineer-in-Charge or a subordinate deputed by his shall give reasonable notice to the contractor. If the contractor fails to attend at the measurements after such notice or fails to countersign or to record the difference within a week from the date of measurement in the manner required by the Engineer-in-Charge  then in any such event the measurement taken by the Engineer-in-Charge or by the subordinate deputed by him as the case may be shall be final and binding on the contractor and the contractor shall have no right to dispute the same.

Clause 9. The contractor shall submit all bills on the printed forms, to be had on application at the office of the Engineer-in-Charge and the charges in the bills shall always be entered at rates specified in the tender or in the case of any extra work orders in pursuance of these conditions and not mentioned or provided for in the tender at the rates herein after provided for such work.

Clause 9.A. Payments due to the contractor may, if so desired by him be made to his bank instead of directed to him provided that the contractor furnishes to Engineer-in-Charge (1) an authorization in the form of a legally valid documents such as a power of attorney conferring authority on the bank to receive payment ad (2) his own acceptance of the correctness of amount made out as being due to him by Delhi Development Authority or his signature on the bill or other claim preferred against Delhi Development Authority before settlement by the Engineer-in-Charge of the amount of claim by payment to the ban, while the receipt given by such bank shall constitute a full and sufficient discharge for the payments the contractor should, wherever possible, present his bill duly accepted and discharge through his bankers.

Nothing herein contained shall operate credit in favour of the bank any rights or equalities vis-a-vise the Authority.

Clause 10. The Engineer-in-Charge shall have full powers to acquire the removal from the premises of all materials which in his opinion are not in accordance with the specifications and in case of default the Engineer-in-Charge shall be at liberty to employ other persons to remove the same without being answerable or accountable for any loss or damage that may happen or arise to such materials. The Engineer-in-Charge shall also have full power to require other proper materials to be substituted there and of and in case of default the Engineer-in-Charge may cause the same to be supplied and all costs which may arise due to such removal ad substitution are to be borne by the contractor.

Clause 10A. The contractor on signing an indenture in the form to be specified by the Engineer-in-Charge shall be entitled to be paid during the progress of the execution of the work upto 75% of estimated value of any materials which are in opinion of the Engineer-in-Charge non-perishable and are in accordance with the contract and which have bee brought on the site in connection there with and are adequately stored and protected against damage by weather or other causes but which have not at the time of advance been in corporate in the works. When materials on account of which an advance has been made under this sub clause are incorporated in the work the amount of such advance shall be deducted from the next payment made under any of the clause or clauses of this contract.

Clause 10B. If after submission of the tender the price of any material incorporated I the works (not being material supplied from the Engineer-in-Charge stores in accordance the clause 10 thereof) and or wages of labour increases as a direct result of coming in to force of any fresh law, or statutory rule or order (but not due to any changes in sales tax) and such increase in the price and/or wages prevailing at the time of the last stipulated date for receipt of the tenders including extensions if any for the work, and the contractor thereupon necessarily and properly pays in respect of that material (incorporated in the works) such increased price and/or in respect of labour engaged on the execution of the work such increased wages, then the amount of the contract shall accordingly be varied and provided further that any such increase shall not be payable if such increase has become operative after the stipulated date of completion of the work in question.

If after submission o the tender, the price of any material incorporated in the words (not being a material supplied from the Engineer-in-Charge’s stores in accordance with Clause 10 thereof) and/or wages of labour is decreased as a direct result of the coming into force of any fresh law or statutory rules  or order (but not due to any changes in sales tax) and such decrease in the price and/or waves prevailing at the time of receipt of the tenderfor the work DDA shall in respect of materials incorporated in the works (not being materials supplied form the Engineer-in-Charge’s stores in accordance with clause-10 thereof) and/or labour engaged on the execution of the work after the data of coming into force of such law statutory rule or order be entitled to deduct from the dues of the contact such amount as shall be equivalent to the difference between the prices of the materials and/or wages as prevailed at the time of the last stipu;ated date for receipt of tenders including extensions f any for the work and the prices of materials and/or wages of  labour on the coming into force of such law, statutory rule or order. The contractor shall, for the purpose of this condition, keep such books of account and other documents as are necessary to show the amount of any increase claimed or reduction available and shall allow inspection of the same by a duly authorized representative of the DDA, and further shall, at the request of the Engineer-in-Charge may require any documents so kept and such other information as the Engineer-in-Charge may require. The contractor shall, within a reasonable time of his becoming  aware of any alteration in the price of any such materials and/or wages of labour, give notice thereof to the Engineer-in-Charge  stating that the same is given pursuant to this condition together with all information relating thereto which he may be in position to supply.

Clause 10C. The contractor shall treat all materials obtained during Dismantling of structure in excavation of that site for a work etc. as Delhi Development Authority according to the  instructions in writing issued by the Engineer-in-Charge.

Clause 10D. In case, the empty cement bags are required by DDA for bonafied use in work, the executive Engineer-in-Charge of work shall have the power to collect the bags himself and the contractor shall have to return desired number of empty jute polybags in serviceable condition to him on the same condition and as per prevailing rates of DGS&D for bag collecting agents.

Clause 11. The contractor shall execute the whole and every part of the work in the mostsubstantial and work man like manner and both as regards material and otherwise in very respect in strict accordance with the specifications. The contractor shall also confirm exactly, fully and faithfully to the designs, drawings and instructions in writing in respect of the work signed by the Engineer-in-Charge and the contractor shall be furnished free of charge one copy of the contract documents together with specifications and of all such designs, drawing and instructions as are not included in the Central Public works Department compilation entitled” CPWD specification for work at Delhi 1996 Vol. _ I to VI with upto date correction slips with any and revised CPWD specifications 2002 for cement mortar, cement concrete and RCC work other printed publication on General Specification referred to else where in the contract or (CPWD General Specifications for Electrical Works Part-I (Int) 2005 and Part-II (Ext.) 1994 with upto date correction slips.)

Clause 12. (i) The work shall be executed as per detailed design and architectural/structural drawings to be prepared by the successful contractor confirming  to the required parameters and functional/design requirement and submitted to the department within the time given under Programme for completion. The contractor shall accordingly get the design/drawing approved by the department before taking up executors of the work.

In case any modification for nay reason is required by the department during course of execution. The duly authorized extras, omission and variation shall ot violate the contract but shall be executed, measured, valued and certified by the Divisional officer and added to or deducted from the amount of contract as the case may be. The valuation of such extras/substitution/reduction/deduction shall be based on the prevailing market rates.

(ii) Minor discrepancies and omissions can be sorted out through mutual consultation as far as possible but decision of Engineer-in-Charge shall be final and binding.

Clause 13. If at any time after the commencement of the work the Authority shall for any reason whatsoever not require the whole work  or part there of as specified in the tender to be carried out, the Engineer-in-Charge shall give notice I writing of the fact to account of any profit or advantage which he might have derived from the execution of the work not having been carried out, either shall he have any claim for compensation b reason of any instructions which shall involve any curtailment of the work as originally contemplated. Provided that  the contractor shall be paid the charges on the cartage only of rendered surplus as a result of the abandonment of curtailment of the work.

Clause 14. If it shall appear to the Engineer-in-Charge or his authorized subordinate in charge of the work or the Chief-Engineer, Superintending Engineer, Chief Technical Examiner/Technical Examiner of Central Vigilance Commission & Chief Engineer Quality Control DDA or by the Officer of the vigilance of the Authority that any work has been executed with unsound, imperfect or unskillful workman ship or with materials of any inferior description, or that any materials or articles provided by him for the execution for the work are unsound or of quality inferior to that contracted for or otherwise are not in accordance with the contract, the contractor shall on demand I writing which shall, be made within 6 months of the completion of the work from the Engineer-in-Charge specifying the work, materials or articles complained of not with standing that the same may have been passed certified and paid the forth with rectify or remove and reconstruct the work so specified in whole or in part as the case may required or as the case may be remove the materials or articles specified and provided other proper and suitable materials or articles at his own proper charge and cost, and in the event of his failing to do so within a period to be specified by the Engineer-in-Charge in his demand aforesaid than the contractor shall be liable to pay compensation at the rate of one percent o the estimated amount put to tender for every day not exceeding the days while his failure to do so shall continue and in the case of any such failure. The Engineer-in-Charge may rectify or removed and re-execute the work or remove and replace with other, the materials or articles complained of as the case may be at the risk and expense in all respects of the contractor.

Clause 15. All work under or in course of execution or executed in pursuance of the contract shall at all times be open to the inspection and supervision of the Engineer-in-Charge and his authorized, subordinates and the Central Vigilance commission or by the Chief Engineer quality Control DDA or his authorized subordinate officer and the contractor shall at all times during the usual working hours, and at all other times at which reasonable notice of he intention of the Engineer-in-Charge or has authorized subordinate to visit the works shall have been given to the contractors either himself be present to receive orders and instructions or have a reasonable agent duly accredited in writing present for that purpose. Order given to the contractor’s agent shall be considered to have the same force as if they had been given to the contactor him self. The work during its progress ca also be inspected by the Chief Technical Examiner/Technical Examiner of the Central Vigilance Commissioner or by Chief Engineer Quality control DDA or by an officer of the Vigilance Cell of the Authority on behalf o the Engineer-in-Charge or any official of higher level, commissioner or any official of quality control cell.

Clause 16. Contractor shall give not less than seven day notice in writing to the Engineer-in-Charge his authorized subordinate in charge of the work before covering up or otherwise placing beyond the reach of measurement any work in order that the same may be measured and correct dimension thereof be taken before the same is so covered up or placed beyond the each of measurement and shall not cover up & place beyond the reach of measurement any work without the consent in writing of the Engineer-in-Charge or his authorized subordinate in change of the work, and the Engineer-in-Charge or his authorized subordinate in charge or his authorized subordinate in charge of the work shall within the aforesaid period of sever days inspect the work, and if any work, shall be covered up or placed beyond the reach of measurement without such notice having been given or the Engineer-in-Charge’s consent being obtained the same shall be uncovered at the contractors expense or in default thereof no payment or allowance shall be made for such work or the materials  with which the same was executed.

Clause 17. If the contractor or his working people or servants shall break deface, injure or destroy any part of building in which they may be working or any building, road crub, fence, enclosure, water pipe, cables, drains, electric or telephone post or wires, frees, grass or grassland or cultivated ground contiguous to the premises on which the work or any part of it being executed or if any damage shall happen to the work while in progress from any cause whatever or if any defect shrinkage or other faults appear in the work within twelve months after a certificate final or otherwise of its completion shall have been given by the Engineer-in-Charge as aforesaid rising out of defective or proper materials or work manship the contractor  shall upon receipt of a notice in writing on that behalf make the same good at his own expense, or in default the Engineer-in-Charge may cause the same to be made good by other workmen and deduct the expense from ay sums that may be then or at any time there after may become due to the contractor, or from his security deposit.

Clause 17A. The security deposit of the contractor will be released after the expiry of 12 months from the date of completion recorded by the Engineer-in-Charge after adjusting necessary recoveries if any. The security will be released to the extent of 75% only. The balance 25% of the security will be released after expiry of 3 years from the date of completion. After the certificate has been recorded by the EE that the plant has been operated ad maintained satisfactorily during the last 3 years.

Clause 17B. Provided further that for defects relating to leakge from the roofts, the contractor shall be responsible for rectification of the same within a period fo one year or two rainy seasons (ending October) whichever is later, after the physical date of completion of the work as a whole, to be recorded by the deptt. and 10 (ten) percent of the security deposit of the contractor will be refunded after expiry of the above period.

Clause 18. The contractor shall provide at his own cost all materials plant, tools, appliances, implements, ladders, cordage, tackle, scaffolding  and temporary works requisite or proper for the proper execution of the work, whether original altered or substituted and whether include in the specification or other documents forming part of the contract or referred to in these conditions or nor or which may be necessary for the purpose of satisfying or complying with the requirement of the Engineer-in-Charge s to any matter as to which under these conditions he is entitled to be satisfied, or which he is entitled  to require together with carriage there of to and from the work. The Contractor shall also supply without charge the requisite number of person with the means and materials necessary for the purpose of setting outworks and counting weighing and assisting of the measurement or examination or any time and from time to time of the work of or materials Failing his so doing the same may be provide by the Engineer I charge at the expense may be deducted from any money due to the contractor under the contractor and/or from his security deposit or the proceeds of the sale there of, or of a sufficient portions  thereof.

Clause 18A. In every case in which by virtue  of the provisions of Sections 12. Sub section (i) of the workmen’s Compensation Act, 1923 Delhi Development Authority is obliged to compensate to a work employed by the contractor in execution of the works. Delhi Development Authority will recover from the contractor in execution of the works, Delhi Development Authority will recover from the contractor the amount of the compensations so paid and, without prejudice to the rights of Delhi Development Authority shall be at liberty to recover such amount or any part thereof by deducting it from the security deposit or from any sum due by Delhi Development Authority to contractor or otherwise. Delhi Development Authority to contractor whether under this contract or otherwise. Delhi Development Authority shall not be boud to contest any claim made against it under section 12 Sub-section (i) of the said Act, expected on the written request of the contractor, and upon his giving to Delhi Development Authority full security for all costs for which Delhi Development Authority might become liable in consequence of contesting labour such claim.

Clause 18B. In every case in which by virtue of the provision of the contract labour (Regulation & Abolition) Act 1970 and of the contract Labour (Regulation and Abolition) Central Rules, 1971. DDA is obliged to pay any amount of wages to workman employed by the contractor in the execution of the works, or to incur any expenditure in providing welfare and health amenities required to be provided under the above said Act, and Rules under clause 19-H or under the C.P.W.D., contractor Labour Regulations or under the rules framed by the Government from time to time for protection of health and sanitary arrangements for workers employed by DDA contractor. DDA will recover from the contractors the amount of wages so paid the amount of expenditure so incurred; and without prejudice to the right of the DDA under section 20 Sub-section (2) and Section (21) Sub-section (4) of the Contract Labour (Regulation & Abolition) Act, 1970, DDA shall be at liberty to recover such amount or any part there of by deducting it from the security deposit or from any sum due by DDA to the contractor whether under this agreement or otherwise DDA shall not be bound to contest any claim made against it under Section 20 Sub-Section (1) and Section (21) sub-section (4) of the said act, except on the written request of the contractor and upon his giving to the DDA full security for all cost for which DDA right become liable in contesting such claim.

Clause 19. The contractor shall obtain a valid license under the contract Labour (R&A), Act, 1970 and the Contract Labour (Regulations & Abolition) Central Rules, 1971 before the common cement of the work and continued to have a valid license until the completion of the work any failure of fulfil this requirement shall attract the Penal provision of this contract arising out of the retirement non executive of the work.

Clause 19A. No labourer below the age of fifteen years shall be employed on the work.

Clause 19B. Payment of wages to labourers:

(a)	The contractor shall pay not less than fair wage to labourers engaged by him on the work. Explanation:- “Fair Wages” means wage whether for time or piece work notified at the time of inviting tenders for the work, where such wages have not been so notified, the wages. Prescribed by the DDA for the district in which the work is done it will be notified prescribed by the DDA in consultation with the officer’s of the Industrial Relation Machinery located in the respective areas and will not be less than the minimum rates of wages fixed by the G.N.C.T.D. for that class of employee engaged on the same type of work in the same area.

(b)	The contractor shall not with standing the provisions of any contract to the contrary cause to be paid fair wage to labourers indirectly engaged on the work including any labour engaged by his sub-contractor in connection with the said work, as if the labourers had been immediately employed by him.

(c)	In respect of all labour directly or indirectly employed in the work for performance of the contractors part of this Agreement the contractor shall comply with or cause to be complied with the DDA contractor’s Labour Regulations made by G.N.C.T.D. from time to time in regard to payment of wages, to wage period deductions from wages, recovery of wages not paid and deductions unauthorisedly made, maintenance of wage book or wage slip, publication of scale of wages and other terms of employment, inspection and submission or periodical returns and all other matters of a like nature or as the provision of the contract labour (regulation and Abolition) Act, 1970 and Labour contact (Regulation and Abolition) Central Rule 1971 whichever is applicable.

(d)	The Engineer-in-Charge concerned shall have the right to deduct, from the money due to the contractor any sum required or estimated to be required for making good the loss suffered by a worker or workers by reason and of non-fulfilment of the condition of the contract for the benefit of the workers, non-payment of wages or of deductions made from his or their wages which are not justified by their terms of the contract or non-observance of the Regulations.

(e)	Under the provision of the Minimum Wages Act 1948 and Minimum wages (Central) Rules 1950 the contractor is bound to allow or cause to be allowed to the labourers directly oir indirectly employed in the works one days rest for six days continuous work and pay wages at the same rate as for duty in the event of default the Engineer-in-Charge shall have the right to deduct the sum or sums not paid on account of wages for weekly holiday to any labours and pay the same to the person entitled there to, from any money due to contractor by the  Engineer-in-Charge concerned. In the case of N.C.T. of Delhi as the all inclusive minimum daily rates of wages fixed under the latest Delhi Govt. Notification F-12(1)88/MW/LAB/1961-98 28-4-89 and F12(142)188NW/LAB/1961-1968 dt. 28-04-1989 F12(14290/MW/ LAB/792 dt. 1-8-90 F12 dt. 4-2-91 revised vide No. F 12(142)98/MW/LAB/2087 dt. 2-6-97 and F-12/142/92/MW/LAB/116 dt. 26-3-99 or as amended from time to time and latest F-12/142702M20/ Lab/97 dt. 20-6-03.

(f)	Vis-à-vis the Delhi Development Authority the contractor shall be primarily liable to all payament to be made under and for the observance of the Regulations aforesaid without prejudice to his right to claim indemnity from his subcontractor.

(g)	The regulations aforesaid shall be deemed to be a part of this contract and any breach there of shall be deemed to be a breach of this contract.

Clause 19C. In respect of all labour directly or indirectly employed in the work for the performance of the contractor part of this agreement, the contractor shall at his own expense arrange for the safety provisions as per Safety Code framed from time to time and shall at his own expense arrange for the safety provisions as per Safety Code framed from time to time and shall at his own expenses provided for all facilities as aforesaid he shall be liable to pay a penalty of Rs. 50 for each default and in condition the Engineer-in-Charge shall be at liberty to make arrangement and provide facilities as aforesaid and recover the costs incurred in that on behalf of the contractor.

Clause 19D. The contractor shall submit by the 4th and 19th of every month to the Engineer-in-Charge a true statement showing in respect of the second half of the preceding month and the first half of the current month, respectively and upto date.

(1)	The number of labours employed by him on the work.

(2)	Their working hours

(3)	The wages paid to them.

(4)	The accidents that occurred during the said fort night showing the circumstances under which they happened and the extent of damage and injury caused by them and.

(5)	The number of female workers who have been allowed Maternity Benefit according to clause 19F and the amount paid on them failing which the contractor shall be liable to pay to DDA a sum not exceeding Rs. 50/- per each default or maternity incorrect statement. The decision of the Divisional Officer shall be final in deducting from any bill due to contractor the amount levied as fine and be binding on contracts.

Clause 19E. In respect of all labour directly or indirectly employed in works for the performance of the Contractor’s part of this agreement. The contractor shall comply with or cause to be complied with all rules framed by Govt. from time to time for the protection of health and sanitary arrangement for works employed by the Delhi Development Authority.

Clause 19F. Leave and during leave shall be regulared as follows:-

1.	Leave:-

i.	in the case of delivery maternity leave not exceeding 8 weeks, 4 weeks upto and including the day of delivery and 4 weeks following that day.

ii.	in case of miscarriage upto 3 weeks form the date of miscarriage.

2.	Pay:-

i.	in case of delivery leave pay during maternity leave will be at the rate of the women’s average daily earning calculated on the total wages earned on the days when fully time work was done during a period of 3 months immediately preceding the date on which she gives notice that she expect to be confined or at the rate of Rupees one only a day whichever is greater.

ii.	in case of miscarriage leave pay at the rate of average daily earning calculated on the total wages earned on the days when fully time work during a period of 3 months immediately preceding the date of such marriage.

3.	Conditions for the grant of Maternity Leave. No maternity leave benefit shall be admissible to a woman unless she has been employed for a total period of not less than 6 months immediately preceding the date on which she proceeds on leave.

4.	The contractor shall maintain a register of maternity (benefit) in the prescribed form as shown below and the same shall be kept at the place of work.

Register of Maternity Benefit

Name & Address of the contractor(s)

Name and location of work

Name of	Father’s/Husband’s	Nature of	Period of actual

Employee	Name	employment	appointment

1	2	3	4

Date on which notice	Date of Delivery	Date on which maternity leave

of confinement given	miscarriage	come need and ended

In case of	In case of

Commenced	Ended	Delivery	miscarriage

5	6	7	8	9	10

Leave pay paid to the employees

In case of delivery	in case of miscarriage

Rate of leave pay	Amount paid	Rate of leave paid	Amount paid

11	12	13	14

Specimen form of the Register regarding maternity benefit admissible to contractor labour in Delhi Development Authority work

Name of Work				Name of the contractor

1.	Name of the woman and her Husband name

2.	Designation

3.	Date of appointment

4.	Date with months and years in which she is employed

5.	Date of discharge dismissal if any

6.	Date of production of certificate in respect of pregnancy

7.	Date on which woman informs about the expected delivery

8.	Date of delivery miscarriage death

9.	Date of production of certificate in respect of delivery miscarriage

10.	Date with the amount of maternity death, benefit if paid in advance of expected delivery.

11.	Date with the amount of subsequent payment of maternity benefit

12.	Name of the person nominated by the woman to receive the payment of the maternity benefit after her death.

13.	Name of the person nominated by the woman to receive the payment of the maternity benefit after was paid the amount there of and the date of payment.

14.	Signature of the contractor for the use of Inspection Officer.

15.	Remarks column for the use of Inspection Officer.

Clause 19G. Model Rules:- In the event of contractor(s) committing a default or breach of any of the provisions of the DDA Contractor Labour regulation and Model Rules for the protection of health and sanitary arrangement for the worker amendment from time to time or furnishing any information or submitting or filing any statement under the provision of the above Regulation and Rules which is materially incorrect, he/they shall without prejudice to any other liability pay to the Delhi Development of Authority a sum not exceeding Rs. 50/- for every default breach or funishing making submitting filling such materials incorrect statement and in the event of the contractor(s) defaulting continuously in this respect the penalty may be enchanting to Rs. 50/- per day of each of default subject to a maximum of 5 percent of the estimated cost of the work put to tender. The decision of the Engineer-in-Charge shall be final and binding on the parties.

Should it appear to the Engineer-in-Charge that the Contractor(s) is/are not properly observing and complying with the Provision of DDA contractor Labour regulations and model rules and the provision of contractor labour (Regulations & Abolition) Central Rule 1971 for the protection of health and sanitary arrangements for work people employed by the power to give notice in writing to the contractors(s) requiring that the said rules be complied with and the amenities prescribed their in provided to the work people in a reasonable time to be specified in the notice to comply with and observe the said rule and to provide the amenities to the work people within reasonable time to be specified in the notice. If the contractor(s) shall have the power to provide the amenities to the work people as aforesaid the Engineer-in-Charge shall have the power to provide the amenities to the work people as aforesaid the Engineer-in-Charge shall have the power to provide the amenities here-in-before mentioned at the cost of the contractor(s). The contractor shall erect make a maintain at his their own expenses and according to approved standards all necessary tent and sanitary arrangements required  for his/their work people on the site in connection with the execution of the works and if the same shall not been erected or constructed according to approve standards the Engineer-in-Charge shall have power to give notice in writing to the contractor requiring that the said tents and sanitary arrangement be remodeled and/or reconstructed such tents and sanitary arrangement be remodeled and/or reconstructed such tents and sanitary arrangement according to approved standard within the period specification in the notice the Engineer-in-Charge shall have the power to removed or reconstruct such tents and sanitary arrangements according to approved standards at the cost of the contractor(s).

Construction of labour huts near the work sites shall be avoided as far as possible Whenever labour huts are pitched the Engineer-in-Charge will prepare a plan of area to be occupied by the labour of the construction agency reflecting there up on the number of huts to be constructed. The Engineer-in-Charge shall obtain an undertaking from the work has been completed in the following proforma:

I/We hereby undertaken that:

1.	Full site free from any encroachment has been handed over to me/us on…………………………

2.	The labour huts………………………..in nos. pitches/constructed by me/us at site as shown on the site plan an duty signed by me/us belong top me/us.

These shall be removed from the site before the completion of the work. In case of failure to do so, the department can get same removed at my risk and cost.

The contract shall not be finalized till the Engineer-in-Charge gives a certificate that the area occupied by the labour of the contractor has been cleared/vacated by the contractor.

Clause 19H. The contractor shall at his/their labour with a sufficient number of tents of the following specification on a suitable plot of land to be approved by the Engineer-in-Charge.

a.	The minimum height of each tent will be at the roof level shall be 2.10 metre (7-0) and the floor area to be provided will be at the rate of 2.7 Sq.ft. for each number of the workers family staying with the labour.

b.	The contractor shall in addition construct real suitable cooking place having a minimum area of (1.8m × 1.5m) (6 feet × 5 feet) adjacent to the hut for each family.

c.	The contractor shall construct temporary latrines and urinals for the use of the labours each on the scale of not less than four pen each one hundred of the total strength separate latrines and urinals being provided for women.

d.	The contractor shall sufficient number of bathing and was hing places one unit for every 25 persons residents in the camp. These bathing and places will be suitable screened.

e.	The contractor shall provide hut with proper ventilation all door, windows and ventilators shall be provided with suitable levels for security purpose.

2.a	The floor shall be in bricks and shall be at least 6 above the surrounding ground the huts shall be with any other material canvas cloth as may be approved by the engineer-in-charge and the contractor shall ensure that though out the period of their occupation the huts remain water tight.

b.	There shall be kept an open of atleast 8 yards (7.2 m) between the rows of Tents which may be reduced to 20 ft (6m) according to the availability of site with the approval of the Engineer-in-charge back to back construction will be allowed.

3.	Water supply. The contractor shall be provide adequate of water for the use labours. The provisions shall not be less than 2 gallons of pure and whole some water per head per day for drinking purpose and 3 gallons of clean water supply is available supply shall be stands posts and where the supply is forms wells or river also at his/their own cost make arrangements for laying pipe line for water supply to his/their labour camp from the existence mains wherever available and shall pay all Fees and charges thereof.

4.	The site selection for the camp shall be on high ground removed from jungle.

5.	Disposal of Excreta. The contractor shall make necessary arrangements for the disposal of excreta from the latrines by trenching or incineration wish shall be according to the requirements laid down by Local Health Authority if trenching or incineration is not allowed the contractor shall made arrangements for removal of the excerata through the Municipal Committee/authority and inform it about the no. of labours employed so that arrangements may be made by such committee/authority for the removal of the excreta. All charges on this account shall be borne by the contractor and paid date by him to the Municipal Authority. The contractor shall provide one sweeper for every seats in case of dry system.

6.	Drainage. The contractor shall provide efficient arrangements for draining away sullage water so as to keep the camp neat and tidy.

7.	The contractor shall make necessary arrangements for keeping the camp are sufficient lighted to avoid accidents to the workers.

8.	Sanitation. The contractor shall make arrangements for conservancy and sanitation in the labour camps according to the rule of the Local Public Health and Medical Authority.

9.	Wherever electric connection from Delhi Electric Supply Co. is readily available the contractor would provide sufficient street for the labour camp, as per the Engineer-in-Charge would provide sufficient street for the labour camp, as per directions of the Engineer-in-Charge.

Clause 19I. The Engineer-in-Charge may require the contractor to dismiss or remove from the site of the work any person or persons in the contractor(s) employment on the work who may be incompetent or misconduct himself and the contractor shall forthwith comply with such requirement.

Clause 19J. It shall be the responsibility of the contractor(s) to see that the building under construction is not occupied by any body unauthorisedly during construction, and to hand over to the Engineer-in-Charge vacant possession of complete building. If such building though completed, is occupied illegally, then the Engineer-in-Charge will have the option to refuse to accept the said building/buildings in that position and delay in acceptance on this account will be treated as delay in completion and to such delay a levy upto 5% of the estimated cost put to tender may be imposed by the Superintending Engineer, whose decision shall be final both with regard to the justification and quantum. However, the Superintending Engineer may required the contractor through a notice to remove the illegal occupation any time on or before construction and delivery.

Clause 20. The contractor shall comply with all the provisions of the Minimum Wages Act, 1948 and Contractor Labour (Regulation & Abolition Act) 1970 & rules framed there under & other labour laws affecting the contract labour that may be brought into force from time to time.

Clause 21. The contract shall not be assigned or sublet without the written approval of the Engineer-in-Charge. And if the contractor shall assign or sublet his contract or attempt to do so, or become insolvent or commence any insolvency proceedings or make any composition with his creditors or attempt to do so advantage pecuniary or attempt to do so or if any bribe gratuity, gift, loan, perquisits offered by the contractor or any of his servants or agents to any public officer or any of his servants or agents to any public officer or person sin the employment of Delhi Development Authority in any way relating to his office employment or if any such Officer or person shall become in any way directly or indirectly interested in the contract the Engineer in Charge on behalf of the Authority shall have power to adopt any of the courses specified in Clause 3 as he may deem best suited in the interest of Delhi Development Authority and in the event of these courses being adopted the consequence specified in the said Clause 3 shall ensure payable.

Clause 22. All sums payable by way of compensation under any of these condition shall be consider as reasonable compensation to the applied to this use of Delhi Development Authority without reference to the actual loss or damage sustained and whether or not any damage shall have been sustained.

Clause 23. Where the contractor is partnership firm the previous approval in writing of the Engineer-in-Charge shall be obtained before any charge is made in the constitution. Where the contractor is an individual or Hindu undivided family business such concern such approval as aforesaid shall likewise be obtained before the contractors enters into any partnership agreement where under the Partnership firm would have the right to carry the work. If previous approval as aforesaid is not obtained the contractor shall be deemed to have been assigned in contravention of Clause 21 here of end the same action may be taken and same obsequence shall ensure as provided in the said clause 21.

Clause 24. All works to be executed under the contract shall be executed under the direction and subjected to the approval in all respects of the Engineer-in-Charge who shall be entitled to direct at what point of points and in what manner they are to be commenced, and from time to time carried on.

Clause 25. The decision of the superintending Engineer regarding the quantum of reduction as well as justification thereof in respect of rates of substandard work which may be decided to be accepted will be final and binding and will not be open to arbitration.

Clause 26. The contractor shall fully indemnify the Delhi Development Authority against any action claim or proceeding relating to infringement of use of any patent or design or any alleged patent or design rights and shall pay any roaylities may be payable in respect of any article part there of include in the contractor in the event ofe any such matters as aforesaid the contractor shall be at liberty at his own expenses to settle any dispute or to conduct any indemnity the Delhi Development if the infringement of the patent or design or any alleged patent or design right is the direct result of an order passed by the Engineer-in-Charge in this behalf.

Clause 27. The contractor shall neither be entitled nor shall he claim damages, loss of profit or compensation against the authority on any account, whatsoever except the amounts specifically provided to be paid to him against the stages. In respect to the execution of the work, interpretation of the clauses of this agreement as well as the tendered documents and communication existing between the parties, the decision of the Zonal Chief Engineer, DDA thereon shall be final and binding on the contractor.

Clause 28. In case of any class of work for which there is no such specification as is mentioned in Rule 1 such work shall be carried out in accordance with the district specifications then in such case the work shall be carried out in all respects in accordance with the instructions and requirements of the Engineer-in-Charge.

Clause 29(i). Whenever any claim or claims for payment of any sum of money arise of or under the contract against the contractor  Engineer-in-Charge or the DDA shall be entitled to withhold and also have lien to retain such sum or sums in whole in part from the security if any deposit by the contractor and for the purpose aforesaid, the Engineer-in-Charge or the DDA shall be entitled to withhold the security deposit if any furnished as the case may be and also have alien over the same pending finalization for adjudication of any such claim in the event of the security being insufficient to cover the claimed amount or amounts of if no security have been taken from the contractor the Engineer-in-Charge or the DDA shall be entitled to withhold and have lien to retain to the extent of such claimed amount or amounts Referred to abovefrom any sum or sums found payable or which at any time thereafter may become payable to the contractor under the same contract or any other contract with the Engineer-in-Charge of the DDA or any contracting person through the Engineer-in-Charge pending finalization or adjudication of any such claim.

It is an agreed term of the contract the sums of money so withheld r retaining under the lien referred to above by the Engineer-in-Charge or DDA till the claim arising out of or under the contract is determined by the Arbitrator (if the contract is governed by the Arbitration Clause) or by the competent court as the cause may be an that the contractor will have no claim for interest or damage whatever of any account in respect of such withholding or retention under the lien referred to above and duly notified as such to the contractor. For the purpose of this clauses where the contractor is a partnership firm of a limited company the Engineer-in-Charge of the DDA shall be entitled to withhold and also have a lien to retain towards such claimed amount or amounts in whole or in part from any sum found payable to any partner/limited company as the case may be whether in his individual capacity or otherwise.

Clause 29 (ii). Delhi Development Authority shall have right to cause an audit technical examination of the work as and the final bills of the contractor including all supporting vouchers abstract sum is found to have been over paid in respect of any work done by the contractor under the contractor or any work claimed by him to have been done by him under the contract and found not to have been executed, the contractor shall believable to refund the amount of over payment and it shall be lawful for Delhi Development Authority to recover the same from him in the manner legally prescribed in sub-clause (1) of this clause or in any other manner permissible and if it is found the contractor was paid less than was due to him under the contract in respect of any work executed by him, under it the amount of such under payment shall be duly paid by Delhi Development Authority to the contractor without any interest what so ever.

Provided that Delhi Development Authority shall not be entitled to recover any sum over paid not the contractor shall be entitled of payment of any sum paid short there such payment has been agreed upon between the Chief Engineer or Executive Engineer on the one hand and the contractor on the under any term of the contract permitting payment for work after assessment by the Chief Engineer or the Executive Engineer.

Clause 30. Any sum of money due and payable to the contractor (including the security deposit returnable to him) under the contract may be with held or retained by way or lien by the Engineer-in-Charge or the D.D.A. or any other contracting person or persons through Engineer-in-Charge against any claim of the Engineer-in-Charge or D.D.A. with such other person or persons in respect of payment of sum of money arising out or under any other contract made by the contractor made with the Engineer-in-Charge or D.D.A. or with such other person or persons.

It is an agreed term of the contract that sum of money so with held or retained under this clause by the Engineer-in-Charge or DDA will be kept with held or retained as such by Engineer-in-Charge or DDA till his claim arising out of the same contract or any other contract is either mutually settled determined by the Arbitrator (if the contract is governed by the Arbitration clause) or by the competent Court, as the case may be and that the contractor shall have no claim for interest or damage whatsoever on his account or any other ground in respect of any sum of money with held or retained under the clause and duly notified as such to the contractor.

Clause 31. The contractor shall make his/their own arrangements for water as per specifications required for the work and nothing will be paid for same. This will subject to the following conditions.

That the water used by the contractor shall be fit for  construction purpose to the satisfaction of the Engineer-in-Charge cost of testing shall be paid by the contractor.

Clause 32. Not withstanding anything contained to the contrary in any or all the clauses of this contract are procured with assistance of Delhi Development Authority either by issue from Delhi Development Authority stock or purchase made under orders or permits or licensed issued by Delhi Development Authority the contractor shall hold the said materials economically and society for the purpose of the contact and not disposed of them without the permission of the Delhi Development Authority and return if required by the Engineer-in-Charge shall determine having due regard to the condition of the materials. The price allowed to the contractor however shall not exceed the amount charged to him including to the element of storage charges. The decision of the Engineer-in-Charge shall be final and himself open to acting for contravention of the terms of the licence or permit and or for criminal reach of trust, be liable to Delhi Development Authority its for all money advantage or profits resulting or which in the usual course would have resulted to him by reason of such breach.

Clause 33. Contractors Superintendence, Supervision, Technical Staff & Employees

(i)	The contractor shall provide all necessary superintendence during execution of the work and as along thereafter as may be necessary for proper fulfilling of the obligations under the contract. The contractor shall immediately after receiving letter of acceptance of the tender and before commencement of the work, intimate in writing to the Engineer-in-Charge the name, qualification, experience, age, address and other particulars along with certificate, of the principal technical  representative to be in charge of the work. Such qualifications and experience shall not be lower than specified in Clause 33 (i). The Engineer-in-Charge shall within 15 days of receipt of such communication intimate in writing his approval may or otherwise of such a representative to the contractor. Any such approval may at any time be withdrawn and in case of such withdrawal the contractor shall appoint another such representative according to the provisions of this clause. Decision of the tender accepting authority shall be final and binding on the contractor in this respect. Such a principal technical representative shall be appointed by the contractor soon after receipt of the approval from Engineer-in-Charge and shall be available at site within fifteen days of start of work.

If the contractor (or any partner in case of firm/company) who himself has such qualification, it will not be necessary for the said contractor to appoint such a principal technical representative but the contractor shall designate and appoint a responsible agent to represent him and to be present at the work whenever the contractor is not in a position to be so present. All the provisions applicable to the principal technical representative under the Clause will also be applicable in such a case to contractor or his responsible agent. The principal technical representative and/or the contractor shall on receiving reasonable notice from the Engineer-in-Charge or his designated representative(s) in charge of the work in writing or in person or otherwise, present himself to the Engineer-in-Charge and/or site of work, as required, to take instructions. Instruction given to the principal technical representative or the responsible agent shall be deemed to have the same force as if these have been given to the contractor. The principle technical representative and/or the contractor or his responsible authorized agent shall beactually available at site atleast two working days every week, these days shall be determined in consultation with the Engineer-in-Charge as well as fully during important stages of execution of work, during recording of measurement of works and whenever so required by the Engineer-in-Charge by a notice as aforesaid and shall also not down instructions conveyed by the Engineer-in-Charge or his designated representative in the site order book and shall affix his signature in token of nothing down the instructions and in token of acceptance of measurement. There shall be no objection if the representative/agent looks after more than one work and not more than three works in same station provided these details and disclosed to the Engineer-in-Charge and he shall be satisfied that the provisions and the purpose of this clause are fulfilled satisfactorily.

If the Engineer-in-Charge, whose decision in this respect is final and binding on the contractor, is convinced that no such technical representative or agent is effectively attending of fulfilling the provisions of this clause, a recovery shall be effected from the contractor as specified in Clause 33(i) and the decision on the Engineer-in-Charge as recorded in the site order book and measurement recorded in Measurement Books shall be final and binding on the contractor. Further, if the contractor fails to appoint a suitable technical representative or responsible agent and if such appointed persons are not effectively present or do not discharge their responsibilities satisfactorily, the Engineer-in-Charge shall have full powers suspend the execution of the work until such date as a suitable agent is appointed to and the contractor shall be held responsible for the delay so caused to the work. The contractor shall submit a certificate of employment of the technical representative/responsible agent alongwith every on account bill/fixed bill and shall produce evidence if at any time soi required by the Engineer-in-Charge.

(ii)	The contractor shall provide and employ on the site only such technical assistants as are skilled and experienced in their respective fields and such foremen and supervisory staff as are competent to give proper supervision to the work.

The contractor shall provide and employ skilled, semiskilled and unskilled labour as in necessary for proper and timely execution of the work.

The Engineer-in-Charge shall be at liberty to object to and require the contractor to remove from the works and person who in his opinion misconduct himself, or is incompetent or negligent in the performance of his duties or whose employment is otherwise considered by the Engineer-in-Charge to be undesirable. Such person shall not be employed again at works site without the written permission of the Engineer-in-Charge and the persons so removed shall be replaced as soon as possible by competent substitutes.

Clause 33(i).

Minimum Qualification & experience required for Principal Technical Representative.

(a)	For works with estimated cost put to tender more than

| (i) Rs. 10 Lakhs for Civil work/Biotechnology. | Graduate or retired AE possessing |
| --- | --- |
| (ii) Rs. 5 Lakhs for Elect/Mech. Works | At least recognized diploma |
| (iii) Discipline to which the Principal Technical Representative should belong | Civil/Elect./Mech/ Biotechnology/Chemical |
| (iv) Minimum experience of work | Three years |
| (v) Recovery to be effected from the contractor in the event of not fulfilling provisions of clause 33(i) | Rs. 20,000/- p.m. |

Clause 34. In pursuant to our under any law, notification or order any royalty cess or the like become payable by the DDA and does not at any time becomes payable by the contractor to the state Government/Local authority in respect of any materials used by the contractor on the work there in then in such case; it shall be lawful for the DDA and it will have right and entitled to recover the amount paid in circumstances as aforesaid from the dues of the contractor.

1.	Sales tax or any other tax if any on materials in respect of this contract shall be payable by contractor and Delhi Development Authority shall not entertain any claim whatsoever in this respect in case of any default the Engineer-in-Charges shall effect recovery.

2.	All Government Departments, Public Undertaking and other Government Bodies carrying out any building or other construction works which are covered under section 2(d) of the main Act shall in case the work is carried out through a contractor, deduct mandatory 1% of the amount of cost approved as per the tender notification from the bills at the time of making payment to the contractors.

Clause 35. Without prejudice to any remedies under this contract if the contractor  dies, the Divisional Officer on behalf of the Delhi Development Authority shall have the option of terminating the contract without compensation to the heirs of the contractor.

Clause 36 (i). After completion of the work the theoretical quantity of cement to be issued in work shall be calculated on the basis of statement showing quantity of cement to be issued in different items of work provided in Delhi Schedule of Rate, 2002 with upto date correction slip. In case any item is executed for which the standard constants for the consumption of cement are not available in the above mentioned statement or can not be derived from this statement the same shall be calculated on the basis of standard formula to be laid down by the Superintending Engineer of the circle concerned. Over this theoretical quantity of cement shall be allowed a variation upto 2% plus/minus for works the estimated cost of which put to tender is more than Rs. 5 lacs. For excess consumption nothing extra will be payable. Where the consumption is below minus 2% the work will note be accepted.

(ii) The contractor shall construct suitable godowns at the site of work for storing the materials safe against damages the sun, rian, dampness, fire, theft etc. He shall also employ necessary watch and ward establishment for the purpose.

(iii) Cement bags shall be stored in separate godowns as per typical godowns sketch attached, with pucca floor and weather proof roofs and walls. Each godown shall be provided with a single door with two locks. The keys of one lock shall remain with Delhi Development Authority’s Junior Engineer-in-Charge of work, and that of the other lock with the authorized agent of the contractor at the site of work, so that the cement is removed from the godown according to the daily requirement with the knowledge of both the parties. The cement bags shall be stacked on proper floors consisting of two layers of dry bricks laid on well consolidated each at a level of atleast one foot above ground level. These stacks shall be in rows of 2 and 10 bags height with a minimum 2’9” clear space around the bags should be placed horizontally continuous in each line as shown in the accompanying sketch. The day to day receipt and issue accounts of cement shall be maintained by the junior Engineer-in-Charge and signed daily by the contractor or his authorized agent (as per specimen of register attached).

Clause 37. The work (whether fully constructed or not) and all materials machines, tools and plants scaffolding temporary building and other things connected there with shall be at the risk of contractor until the work has been delivered to the Engineer-in-Charge and the certificate from him to that effect obtained. In the event of the work or any materials properly brought to the site for incorporation for the work being damage or destroyed in consequence of hospitalizes of war-like operation, the contractor shall when ordered in writing by the Engineer-in-Charge remove any debris from the site collect and properly stack or remove in the store all serviceable materials salvages from the damage work shall be paid at the contract rate in accordance with provision of this agreement for the work of clearing the site of debris stacking or removal of serviceable materials and for the reconstruction of all work ordered by the Engineer-in-Charge such payment being in addition to compensation shall be assessed by the Divisional Officer 5 upto Rs. 5,000/- and by the Chief Engineer for a higher amount. The contractor shall be paid for the damage destruction suffered and for storing the materials at the rates based on the analysis of the rates tender for in accordance with the provision of this agreement. The certificate of the engineer in charge regarding the quantity and quantity of materials and the purpose for which they were collected shall be final and binding on all parties to the contract.

Provided always that no compensation shall be payable for any loss in consequence of hostilities or war like operation unless (a) the contractor has taken all such precautions against air raid as are deemed necessary by the A.R.P. Officer or the Engineer-in-Charge (b) for any materials etc. not on site of the work for any tools and plants machinery scaffolding temporary building and other things not intended for the work.

In the event of the contractor having carried out reconstruction as aforesaid he shall be allowed such extension on times for its completion as is considered reasonable by the Divisional Officer.

Clause 38. Security deposit shall not be refunded till clearance certificate from the labour officer is obtained by the contractor.

Clause 39. The contractor shall comply with the provision of the Apprentice Act, 1961 and the contractor shall also be liable for any pecuniary liability arising on account of any violation by him of the provision of the Act.

Clause 40. Anti Malaria Measures. The contractor shall at his own expenses makes necessary arrangement for under taking Anti-Malaria measures including drainage at place such as abandoned Howdies, Water tanks, excavated etc. where water likely to stagnate and cause mosquito breeding. The contractor shall comply with every reasonable directions of the Engineer-in-Charge.

Safety Code

1.	Suitable scaffolds should be provided for workmen for all works that can not safely be done from the ground of form the ground or from solid construction except such short period work as can be safely from ladders. When a ladder is used an extra mazdoor or shall be suitable foot holds and hand holds shall be provided on the ladder and the ladder shall be given an inclination not steeper than 1/4 to 1 (1/4 horizontal and 1 vertical)

2.	Scaffolding or staging more than twelve feet above the ground or floor swung or suspending from an overhead support or erected with stationary support shall have a guard rail properly attached or support or errect4ed with stationery support shall have a guard rail properly attached bolted, braced and otherwise secured at least 3 feet high above the floor or platform of such scaffolding or staging and extending along the entire length of the outside and ends thereof with only such opening as may be necessary for the delivery of materials such scaffolding or staging shall be so fastened as to prevent it from swaying from the building or structure.

3.	Working platform gangways and stairways should be so constructed they should not sagunduly unequally and if the height of the platform or gangway or the stairway is more than 12 feet above ground level or floor level they should be closely boarded should have adequate width and should be suitably fastened as described in (2) above.

4.	Every opening in the floor of a building or to all working platform be provided with suitable means to prevent the fall of person or materials by the providing suitable fencing or railing whose minimum height shall be 3’0” (90 cm)

5.	Safe means of access shall be provided to all working platform and other working places. Every ladder shall be securely fixed. No portable single ladder shall be over 30 feet (9 mtr.) in length while the width between side rails in hug ladder shall in no case be less than 11 ½” (29 cm) for ladder upto and including 3.05 mtr. in length. For longer ladder this widths should be increased at least 6mm for each additional foot of length. Uniform step spacing shall not exceed 30 cm Adequate precautions shall be taken to prevent danger from electrical equipment. The materials on any of the sites of work shall not be stacked or placed as to cause danger or inconveniencing to any person or Public. The contractor shall provide all necessary fencing and lights to protect the public from accident and shall be bound to bear the expenses of defence of every suit action or other proceeding at law that may be brought by any person for injury sustained owing to neglect of the above precaution and to pay and damages and cost which may be awarded in any such suit, action or proceedings to any such person or which may with the consent of the contractor be paid to compensate any claim by any such person.

6.	Excavation and Trenching All trenches four feet or more in depth shall at all times be supplied with at least at one ladder for each 30 mtr. in length or fraction thereof Ladder of the ground. The side of trenches least to at 90 cm above the surface of the ground. The side of the trenches which are or more in depth shall be stepped back to give suitable stop or securely held by timber branching so as to avoid to danger of sides to collapse. The excavation materials shall not be placed within 1.50 mtr. of the edges of the trench or half of the depth of the trench whichever is more. Cutting shall be done from top to bottom. Under no circumstances under mining or under cutting shall be done.

7.	Demolition Before any demolition work is commenced and also during the process of the work.

(a)	All roads are open areas adjacent to the work site shall either be closed or suitably protected.

(b)	No electric cable or apparatus which is liable to be sources of danger over a cable or apparatus used by the operator shall remain electrically charged.

(c)	All practical steps shall taken to prevent danger to person employed from risk of fire or explosion or folding. No floor roof or other part of the building shall be so overloaded with debris or materials as to render to unsafe.

8.	All necessary personal safely equipment as considered adequate by the Engineer-in-Charge should be kept available for the use of the person employed on the site and maintained in a condition suitable for immediate use and the contractor should take adequate steps to ensure proper use of equipment by those concerned the following safety equipments immediately be provided.

(a)	Workers employed on mixing asphaltic materials cement and lime mortars shall be provided with protective footwear and protective goggles.

(b)	Those engaged in white washing and mixing or stacking of cement bags or any materials which is injuries to the eyes shall be provided with protective goggles.

(c)	Those engaged in welding works shall be provided with welder’s protective eye shields.

(d)	Stone breakers shall be provided with protective goggles and protective clothing and seated at sufficiently safe intervals.

(e)	When workers and employed in sewers and storm water pipe drains and manholes which hare in active use the contractor shall ensure that the following safety measures as adhered to:

(i)	Entry for workers into the line shall not be allowed except under supervision of the JE or any other higher officer.

(ii)	At least 5 to 6 manholes upstream and downstream should be kept open for at least 2 to 3 hours before any man is allowed to enter into the manholes for working inside.

(iii)	Before entry, presence of Toxic gasses should be tested by inserting wet lead acetate paper, which changes colour in the presence of such gases and gives indication of their presence.

(iv)	Presence of Oxygen should be verified by the lowering a detector into the manholes. In case no oxygen is found inside the sewer line workers should be sent only with Oxygen Kit.

(v)	Safely belt with rope should be provided to the workers. While working inside the manholes such rope should be handled by two men standing outside to enable him to be pulled out during emergency.

(vi)	The area should be barricaded of cordoned or by suitable means to avoid mishaps of any kind Proper warning signs should be displayed or the safety of the public whenever clearing works undertaken during nigh or day.

(vii)	The malba obtained on account of cleaning of blocked manholes and sewer lines should be immediately removed to avoid accidents on account of slippery nature of the malba.

(viii)	No smoking or open flames shall be allowed near the blocked manholes being cleaned.

(ix)	Workers should not be allowed to work inside the manholes. They should be given rest intermittently. The Engineer-in-Charge may decide the time up to which a worker may be allowed to work continuously inside the manhole.

(x)	Gas masks with oxygen Cylinder should be kept at site for use in emergency.

(xi)	Gas masks with oxygen Cylinder should be kept or fresh air through manholes whenever called for. Portable air blowers are recommended for ventilating the manholes. The motors for these shall be vapour proof and of totally enclosed type. Non-sparkling gas engine also could be used but they should be placed at least 2 meters away from the opening and on the lowered side protected from wind so that they will not be source of friction on any inflammable gas that might be present.

(xii)	The workers engaged for cleaning the manholes sewers should be proper trained before allowing to work in the manholes.

(xiii)	The worker shall be provided with Gumboots or non-sparking shoes bump helmets and gloves non-sparkling tools safely lights and gas marks supplied with barrier cream for anointing the limbs before working inside the sewer lines.

(xiv)	If a man has received a physical injury he should be brought out of the sewer immediately and adequate medical and should be provided to him.

(xv)	The extent to which these precautions are to be taken depend on individual situation but the decision of the Engineer-in-Charge regarding the steps to be taken in an individual.

9.	The contractor shall not employ men below the age of 18 years and women on the work of planting with products containing lead in any form. Wherever men above the age of 18 years are employed on the work of lead painting the following precaution should be taken:-

a.	No paint containing lead products shall be used except in the form of paste or readymade paint.

b.	Suitable face masks should be supplied for use by the workers when paint is applied in the form of spray or a surface having lead paint dry rubbed and scrapped.

c.	Overalls the safety equipment shall be supplied by the contractors to the workmen when paint is applied in the form of spray or a surface having lead paint dry rubbed and scrapped.

(i)	Overalls all the safety equipment shall be supplied by the contractors to the workmen and adequate facilities shall be provided to enable the working painters to wash during the execution of works.

d.	(i)	White lead sulphate of lead or product containing these pigment shall not be used in painting operation except in the form of pastes or of paint ready to use.

(ii)	Precautionary Measure shall be taken whenever required in order to prevent danger arising from the application of a plant in the form of spray.

(iii)	Precautionary Measure shall be taken whenever required in order to prevent danger arising from dust caused by dry rubbing down and scrapping.

e.	(i)	Adequate facilities shall be provided to enable working painters to wash during and on cessation of work.

(ii)	Overall shall be worn up by working painters during the whole of the working period.

(iii)	Suitable arrangements shall be made to prevent clothing put of during working hours being spoiled by painting materials.

f.	(i)	Cases of lead poisoning and suspected lead poisoning shall be notified and shall be subsequence verified by a medical man appointed by the competent Authority of DDA.

(ii)	The DDA may require when necessary medical examination of workers.

(iii)	Instructions with regard to special hygienic precautions to be taken in the painting trade shall be distributed to working painters

10.	When the work is done near any place where there is risk or drowning all necessary equipments should be provided and kept ready for all necessary steps taken prompt rescue of any persons in danger and adequate provision should be made for prompt first aid treatment of all injuries likely to be susta9ined during the course of work.

11.	Use of hoisting machines and tackle including their attachments anchorage and supports shall conform to the following standard or conditions.

(a)	(i)	These shall be of good mechanical construction, sound material and adequate strength and free from patent defect and shall be kept in good condition and in good working order

(ii)	Every rope used in hoisting or lowering materials or as a means of suspension shall be or durable quality and adequate strength and free from patent defects.

(b)	Every crane driver or hoisting appliance operator shall be properly qualified and not person under the age of 21 years should be in charge of any hoisting machine including any scaffolding which give singals to operator.

(c)	In case of every hoisting machine and of every chain ring hook, shackle swivel and pulley block used in hoisting or as means of suspension the safe working load shall be plainly marked with the safe working load. In case of hoisting machine having a variable safe working load, each safe working load and the conditions under which it is applicable shall be clearly indicated. No part of any machines or any gear referred to above in this paragraph shall be loaded beyond the safe working load except for the purpose of testing.

In case of departmental machines, the safe working load shall be notified by the Electrical Engineer-in-Charge. As regards contractors machines the contractors shall notify the safe working load of the machine to the Engineer-in-Charge whenever he brings any machinery to site of work and get it verified by the Electrical Engineer concerned.

12.	Motors gearing, transmission, electric wiring and other dangerous parts of hoisting appliances should be provided with efficient safeguards, hoisting appliances should be provided with such means as will reduce to the minimum the risk of accidental descent of the load adequate precautions should be taken to reduce to the minimum the risk of any part of the suspended load becoming accidentally displaced. When workers employed on electrical installations which are already energized, insulating mats, wearing appear/such as gloves sleeves and boos as may be necessary should be provided. The worker should not wear any rings, watches, and carry keys or other materials which are good conductors of electrically.

13.	All scaffolds, ladders and other safety devices mentioned or described herein shall be maintained in safe condition and no scaffold, ladder of equipment shall be altered or removed while it is in use. Adequate washing facilities should be provided at or near places or works.

14.	These safety provisions should be brought to the notice of all concerned by display on notice board at a prominent place at work spot. The person responsible for the compliance of the safety code shall be named therein by the contractor.

15.	To ensure effective enforcement of the rules and regulations to safety precautions, the arrangements made by the contractor shall be open to inspection by the Labour Officer Engineer-in-Charge of the Authority or their representative.

16.	Notwithstanding the above Clause from (1) to (15) there is nothing in these to exempt the contractor from the operations of the other Act or rules in force in the Republic of Inida.

Model Rules for the Protection of Health and Sanitary Arrangements for Workers employed by DDA or its Contractors

1.	Application:

These rules shall apply to all building and construction works in charge of Delhi Development Authority.

2.	Definitions:

(a)	“Work place” means a place when an average, fifty or more workers are employed in connection with construction work.

(b)	“Large work place” means a place at which, at an average 500 or more workers are employed in connection with construction work.

3.	First Aid:

(a)	At every work place, there shall be provided and maintained in an easily accessible place first aid appliance including an adequate supply of sterillised dressing and sterillised cotton wool. The appliance shall be kept in good order and, in large work place they shall be placed under the charge of a responsible person who shall be readily available during working hours.

(b)	AT large work place, where hospital facilities are not available with in easy distance of the works, First Aid posts shall be established and be run by a trained compounder.

(c)	Where large work places are remote from regular hospitals, an indoor ward shall be provided with one bed for every 250 employees.

(d)	Where large work place are situated in cities, town or in their suburbs and no beds are considered necessary owing to the proximity of city or town hospitals, suitable transport shall be provided to facilitate removal of urgent cases to the hospitals. At other work place some conveyance facilities, shall as a car, shall be kept readily available to take injured person or persons suddenly taken serious to the nearest hospital.

4.	Drinking water:

Condition No. 4 of Model Rules

The contractor shall supply only potable water in the labour camp sample of water shall be drawn from the source of water supply in the labour camps every months and got tested from the MCD lab by the contractor. Wherever drinking water is supplied to the labour camps through tankers. Sample shall be drawn from the tankers and got tested. Water storage tanks chlorine tablets shall be added from time to time as per requirement so that potability of water remain intact. No extra payment shall be made on this account.

(a)	In every work place, there shall be provided and maintained at suitable places, easily accessible to labour, a sufficient supply of cold water fit for drinking.

(b)	Where drinking water is obtained from an intermittent public water supply each work place shall be provided with storage where such drinking water shall be stored.

(c)	Every water supply of storage shall be a distance of not less tan 15 metre from any latrine, drain or other source of pollution. Where water has to be drawn from an existing well which is within such proximity of latrine, drain or any other source of pollution, the well shall be properly chlorinated before water is drawn from it for drinking. All such wells shall be entirely closed in and provided with a trap-doors which shall be dust and water proof.

(d)	A reliable pump shall be fitted to each covered well, the trap-door shall be kept locked and opened only for cleaning or inspection which shall be done at least once a month.

5.	Washing and Bathing place:

(a)	Adequate washing and bathing place shall be provided, separately for men and women.

(b)	Such places shall be kept in clean and in dried condition.

6.	Scale of Accommodation in Latrine and urinals:

These shall be provided within the premises of every work place latrines and urinals in an accessible for each of them shall not be less than the following scale.

No. of seats.

(a)	Where the number of persons does not exceeds 50	2

(b)	Where the number of persons exceeds 50, but	3

does not exceed 100

(c)	For every additional 100 persons	3 per 100

In particular cases the Executive Engineer shall have the powers to vary the scale where necessary.

7.	Latrines and urinals for women:

If women are employed, separate latrines and urinals, screened from those for men and marked in the vernacular in conspicuous letters “For women only” shall be provided on the scale laid in rule 6. Those of men shall be similarly marked “For men only”. A poster showing the figure of a man and a women shall also be exhibited at the entrance of latrines, for each sex. There shall be adequate supply of water close to the urinals and latrines.

8.	Latrines and Urinals:

Except  in work places provided with water flushed latrines, connected with a water borne sewage system all latrines shall be provided with receptacles on dry each system which shall be cleaned at least four times daily and at least, twice during working hours and kept in a strictly sanitary condition. The receptacles shall be tarred inside and outside at least once a year.

9.	Construction of Latrines:

the inside well shall be constructed of masonry of some suitable heat resisting non-absorbent material and shall be cement washed inside and outside at least once a year. The dates of cement washing shall be noted in a register maintained for this purpose and kept available for inspection. Latrine will not be of a standard lower than borehole system and should have thatched roofs.

10.	Disposal of Excreta:

Unless otherwise arranged for by the local sanitary authority, arrangements for proper disposal of excreta by incineration at the work place shall be made by means of a suitable incinerator approved by the Assistant Director of Public Health or the Municipal Officer of Health, as the case may be, in whose jurisdiction the work place is situated. Alternatively, excreta may be disposed off by putting a layer of night soil at the bottom of pucca tank prepared for the purpose and covering it with 6” layer of waste or refuse than covering it up with a layer of earth for a fortnight (when layer of waste or refuse and then covering it up with a layer of each for a fortnight (when it will turn into manure).

11.	Provision of shelter during rest:

At every work place there shall be provided free of cost to suitable sheds, one of meals and the other for rest separately for men and women for the use of labour. The height of each of the shelters shall not be less then 11 feet (3.35 m) from the floor level to the lowest part of the roof. The sheds should be roofed with atleast thatch and mud flooring will be provided with a dwarf wall around not less than 2-1/2 feet (76 cm). Sheds should be kept clean and the space should be on the basis of at least 5 square feet (0.46 sqm) per head.

12.	Creches:

(a)	At every work place at which 50 or more women workers are ordinarily employed thee shall be provided two tents for the use of children under the age of 6 years, belonging to such women. One tent should be used for infants games and play and the other as their bed room. The tents shall not be constructed on a lower standard than the following:

(i)	Thatched roof

(ii)	Mud floor;

planks spread over the mud floor and covered with matting;

The huts shall be provided with suitable and sufficient opening for light and ventilation. There shall be provided with suitable and sufficient opening for light and ventilation. There shall be adequate provisions of sweeper to keep the places clean. There shall be two Dais in attendance. Sanitary utensils shall be provided to the satisfaction of the Health Officer of the area concerned. The use of the tent shall be restricted to children, their attendants and mother of the children.

(b)	Where the number of women workers is more than 25 but less than 50, the contractors shall provide at least one tent and one Dais to look after the children of women workers.

(c)	The size of crèche shall vary according to the number of women workers.

(d)	The crèche shall be properly maintained and necessary equipment like toys etc. shall be provided.

13.	Canteen:

A cooked food canteen on a moderate scale shall be provided for the benefit of workers-wherever it is considered expedient.

14.	The above rules shall be incorporated in the contract and in the notice inviting tenders and shall from integral part of the contracts.

Contractors Labour Regulations

Short title:

These regulations, may be called the “Delhi Development Authority contractor’s Labour Regulations.”

1.	Definition-in these regulations, unless otherwise expressed or indicated, the following words and expressions shall have the meaning hereby assigned to them respectively that is to say.

(a)	“Labour means workers employed by a Delhi Development Authority Contractor directly or indirectly through a sub-contractor or other persons or by an agent on his behalf on a payment not exceeding 
Rs. 400/- per month and will not include supervisory staff like Overseers etc. and will not be less than minimum rates of wages fixed by the latest Delhi Govt. and Plus upto date variable dearness allowance on applicable for minimum wages/on the basis of cost vide modification by Delhi Administration time to time for the class of employee engaged on the same type of work circulated vide number at the time of tender.

(b)	“Fair Wages” means wages whether for time or pieces work notified at the time of inviting tenders for the work and where such wages have not been so notified, the wages prescribed by the DDA for the District in which the work is done. It will notified as prescribed the DDA is consultation with the officer or the industrial Relations Machinery located in the respective areas and will not be less than minimum rates of wages fixed by the latest Delhi Govt. and plus upto date variable deamess allowance as applicable for minimum wages on the basis of coat vide notification by Delhi Administration time to time for that class of employed engaged on the same type of work.

(c)	“Contractor” shall include every person whether a subcontractor or head man or agent employing labour on the work taken on contract.

(d)	“Wages” shall have the same meaning as defined in the payment of wages Act and includes time  and piece rate wages.

2. (a)	Normally working hours of an adult employee should not exceed 8 hours a day and in case of a child 4-1/2 hours a day. Working day shall be so arranged that inclusive of interval for rest, it shall not spread more than 12 hours on any day.

(b)	When an adult worker is made to work for more than 9 hours any day or for more than 48 hours in any week, he shall be overtime for the extra hours put in by him at double the ordinary rate wages. Children shall not be made to work extra hours.

(c)	Every worker shall given a weekly holiday normally on Sunday in accordance with the provision of the minimum wages (Central) Rules 1950 as amended from time to time irrespective of whether such worker is governed by the minimum wages act 1948 or not.”

3.	Display of notice regarding wages etc.. The Contractor shall:

(a)	Before the commences his work on contract display and correctly maintain and continue to display and correctly maintain in a clean and legible condition in conspicuous places on the work notice in English and in the Local Indian Langauge spoken by the majority of the workers given the rate of wages which have been certified by the Executive Engineer, the Chief Engineer or Regional Labour Commissioner as fair wages and the hours of work for which such wages are earned and; the actual wages being paid.

(b)	Send a copy of such notices to the certifying Officer i/e E.E./C.E. and Regional Lab Commissioner:

4.	Payment of wages:

(a)	Wages due to every worker shall be paid to him direct.

(b)	All wages shall be paid in current coin or currency or in both.

(c)	Arrears claimed after 3 months after the completion of the work shall not be entertained.

5.	Fixation of wage periods:

The contractor shall fix the wage periods in respect of which the wages shall be payable:

(a)	No wages period shall exceed one month.

(b)	Wages of every worker employed on the contract shall be paid (i) in case establishment in which wages period is one week, within three days from the end of the wage period and (b) in the case of other establishments before the expiry of 7th day or 10th day from the end of the wages period according as the number of workers emplyed in such establishment does not exceed 1000.

(c)	When the employment of any worker is terminated by or on behalf of the contractor the wages earned by him shall be paid before the expiry of the day succeeding the one on which his employment is terminated.

(d)	All payments of wages shall be made on a working day except when the work is completed before the expiry of the wages period in which case final  payment shall be made with 48 hours of the last working day at work site and during the working time

Note: The term “Working Day” means a day on which the work which the labour employee is in progress.

6.

(a)	The contractor shall maintain a Wage Book of each worker in such form as may be convenient at the place of work but the same shall include the following particular:-

(i)	Name of worker

(ii)	Rate of daily or monthly wages

(iii)	Nature of work on which employed

(iv)	Total number of days worked during each wage period

(v)	Dates and period for which worked overtime

(vi)	Gross wages payable for the work during wage period

(vii)	All deductions made from the wage with an indication. In each case of the ground for which the deductions is made

(viii)	Wage actually paid for each wage period

(b)	Signature of thumb impression of the worker

(c)	The Contractor shall also issue a wage slip containing the aforesaid particulars to each worker employed by him on the work at least a day prior to the day of disbursement of wages.

(d)	The contractor shall issue an Employment Card in the prescribed form III to each worker on the day of work or entry into his employment. If the worker has already any such card with from the previous employer, the contractor shall merely endorse that Employment Card with relevant entries. On termination of employment Card shall again be endorsed by the contractor and returned to the worker.

(e)	“The Contractor shall issue an Attendance cum Wage Card as per Form IV enclosed to each worker on the day of work or entry into the employment”.

7.	Register of unpaid Wages:

The contractor shall maintain a Register of unpaid wages in such form as may be convenient at the place of work but the same shall include the following particulars.:

(a)	Full particulars of the labourers whose wages have not been paid

(b)	Reference number of the muster roll and wages register

(c)	Rate of wages

(d)	Wage period

(e)	Total amount not paid

(f)	Reason for not making payment

(g)	How the amount of unpaid wages was utilized

(h)	Acquittance with date

8.	Register of Accidents:

The contractor shall maintain a register of accidents in such form as may be convenient at the work place but the same shall include the following particulars:-

(a)	Full particulars of the labourers who met with accident

(b)	Rate of wages

(c)	Sex

(d)	Age

(e)	Nature of accident and cause of accident

(f)	Time and date of accident

(g)	Date & time when admitted in hospital

(h)	Date of Discharge from the hospital

(i)	Period of treatment and result of treatment

(j)	Percentage of loss of earning capacity and disability as assessed by Medical Officer

(k)	Claim required to be paid under Workmen’s Compensation Act

(l)	Date of payment of details of the person to who the same was paid

(m)	Amount paid with details of the person to whom the same was paid

(n)	Authority by whom the compensation was assessed.

(o)	Remarks

9.	Fines and Deductions which may be made from Wages:

(a)	The wages of workers shall  be paid to him without any deductions of any kind except the following.

(i)	Fines. List of Acts and Omission for which fine can be imposed:-

•	Will full in subordination of disobedience, whether alone or in combination with another.

•	Theft, fraud or dishonesty in connection with contractor’s business or property of this DDA

•	Taking or giving bribes or any illegal gratification

•	Habitual late attendance

•	Drunkenness, fighting, riotious or disorderly or incident bheaviour

•	Smoking near or around the area where combustible or other materials are staked.

•	Habitual negligence

•	Habitual indiscipline

•	Causing damage to work in progress or to property of the DDA or the contractor

•	Sleeping on duty

•	Malingering or slowing down work

•	Giving false information regarding name, age, father’s name etc.

•	Habitual loss of wage cards supplied by the Employers

•	Unauthorised used to employer’s property or manufacturing or making of unauthorized articles at the work places

•	Bad workmanship in constructions and maintenance by skilled workers which is not approved by the Department and for which contractors are compelled to undertake rectification.

•	Making false complaints and or misleading statements

•	Engaging the trade within the premises of the establishment

•	Any unauthorized divulgence of business affairs of the employees.

•	Collection or canvassing for the collection of any money within the premises of any establishment unless authorized by the employers.

•	Holding meeting inside the premises without previous sanction of the employers.

•	Threatening or intimidating any workman or employees during the working hours within the premises.

(ii)	Deduction for absence from the duty i.e. from the place or places where by the terms of his employment he is required to work. The amount of deduction shall be in his employment he is required to work. The amount of deduction shall be in proportion to the period for which he was absent.

(iii)	Deduction for damage to or loss of goods expressly entrusted to the employed person for custody, or for loss of money or any other deduction, which he is required to account where such damages or losses are directly attributable to his neglect or default.

(iv)	Deduction for recovery of advances or for adjustment or over payment or wages advance granted shall be entered in a registrar.

(v)	Any other deduction, which the Central Government may from time to time allow.

(b)	No fine should be imposed on a worker in respect of such acts and omission on his part as have been approved of by the Chief Labour Commissioner.

(c)	No fine shall be imposed on a worker and no deduction for damage or loss shall be made from his wages until the worker has been given an opportunity of showing cause against such fine or deductions.

(d)	The total amount of fine which may be imposed in any one wages period on a worker shall not exceed an amount equal to three naye paise in a rupee of the wages payable to him in respect of that period.

(e)	No fine imposed on any worker shall be recovered from him by installment or after the expiry of sixty days from the date on which it was imposed.

(f)	Every fine shall be deemed to have been imposed on the day of omission of fact in respect of it which was imposed.

10.	Register of fines, etc.

(a)	The contractor shall maintain a register of fines and a register of deduction for damage of loss in Form Nos. 1 and 2 respectively which should be kept at the place of work.

(b)	The Contractor shall maintain in both, English and the local Indian Language a list approved by the Chief Labour Commissioner clearly stating the act and omission for which penalty of fine may be imposed on a workman and display it in a good condition in a conspicuous place on the work.

11.	Preservation of Registers: The wage book, the wages slips, the register of unpaid wages, the registers of accidents, the registers of fines, reductions required to be maintained under these regulations required to be maintained under these regulations shall be preserved for 12 months after the date of last entry made in them and shall be made available for inspection by the Engineer-in-Charge, to labour Welfare Officer or any other officer authorized by Ministry of W.H. &S. on the behalf.

12.	Power of Labour Welfare Officer to make investigations of Enquiry. The Laobur Welfare Officer or any other person authorized by the Central Government on their behalf shall have power to make enquiry with a view to as certaining and enforcing due and proper observance of the fare wages clauses and the provisions of regulations. He shall investigate into any complaint regarding the default made by the contractor or subcontractor in regard to such provisions.

13.	Report of Labour Welfare Officer – The Labour Welfare Officer or other persons authorized as aforesaid shall submit a report of the result of his investigation or enquiries to the Executive Engineer concerned indicating the extent, if any to which the default has been committed. With a note that necessary deduction from the contractor’s bill be made and the wages and other dues by paid to the labourers concerned in case an appeal is made by the contractor under Clause 14 of these regulations actual payment to laborers will be made by the Executive Engineer after the Regional Labour Commissioner has given his decision on such appeal.

(a)	The Executive Engineer shall arrange payment to the Labourer concerned within 45 days from the receipt of the report from the Labour Welfare Officer or the Regional Labour Commissioner as the case may be.

14.	Appeal against the decision of Labour Welfare Officer. Any person aggrieved by the decision and recommendations of the Labour Welfare Officer or other person so authorized may appeal against such decision to the Regional Labour Commissioner concerned within 30 days from the date of decision, forwarding simultaneously a copy of his appeal to the Executive Engineer concerned but subject to such appeal the decision the Officer shall be final and binding upon the contractor.

15.	Prohibition regarding Representation:

(a)	A workman shall be entitled to be represented in any investigation or enquiry under these regulations by:-

(i)	An office of a federation of trade union of which he is a member

(ii)	An officer of a federation of trade union to which the trade unions referred to in clause (a) is affiliated.

(iii)	Where the employer is not a member of any registered trade unions, by an officer of a registered trade union connected with or by any other workman employed in the industry in which the worker is employed.

(b)	An employer shall be entitled to be represented in any investigation or enquiry under these regulations by:-

(i)	An officer of an association of employer of which he is member.

(ii)	An office of a federation of employer to which the trade unions referred to in clause (a) is affiliated.

(iii)	Where the employer is not a member of any association of employer connected with or by an any other employer engaged in the industry in which the employer is engaged.

(c)	No party shall be entitled to be represented by legal practitioner in any investigation or enquiry under these regulations.

16.	Inspection of books and slips – The contractor shall allow inspection of the wages books and the wages slips, the register or unpaid wages, the register of accident, and the register of fines and deductions to any of his workers or to his agent at a convenient time and place after the due notice is received from the Labour Welfare Office or any other person autohrised by the Central Government on his behalf.

17.	Submission of Return:

The contractor shall  submit periodically return as may be specified from time to time

18.	Amendments:

The Central Government may from time to time add to or amendment the regulations and on any question as to the application interpretation or effect of those regulations to the decisions of the Chief Labour Commissioner or Deputy Labour Commissioner to the Government of India or any other person authorised by the Central Government on that behalf shall be final.

Annexure to Additional condition 34(i) showing quantities of materials of areas of road roller of surfacing to be considered for working out the minimum period for which hire charges are to be recovered.

General Specification and Conditions

General:

1.	The contractor must get acquainted with the proposed site for the works and study specifications and conditions carefully before tendering. The work shall be executed as per programme approved by the Engineer-in-Charge. If part of site is not available for any reason or there is some unavoidable delay, the programme of construction shall be modified accordingly and the contractor shall have no claim for any extras or compensation on this account.

2.	Periphery of works areas shall be the area shown in the layout plan of the scheme.

Specification:

3.1	Specification to be followed for execution of work shall be:-

3.1.1	Specifications as approve din tender will be adopted.

3.1.2	The Civil work shall be done as per CPWD specification 1996 Vol-1 to VI upto date correction slip, most specification and Revised CPWD specification 2002 for cement, concrete, RCC and cement mortar or General Specifications for Electrical works (Part-I int. 2005) and (Part-II Ext. 1994) with upto date C-S till date of opening of tender

The specifications for any item are not available in the CPWD Specifications referred above, relevant B.I.S. specifications shall be followed. In case B.I.S. Specification are also not available, the decision of the Engineer-in-Charge shall be final. Whenever any reference to any Indian Standard Specifications occurs in the documents relating to the contract the same shall be inclusive of all the amendment issued there to or relating to the contract the same shall be inclusive of all the amendments issued there to or revisions thereof if any, upto the date of receipt of tenders.

3.1.3	Samples of all building materials and other articles required for execution of works shall be got approved from Engineer-in-Charge. Article manufactured by firms repute and approved by the Engineer-in-Charge shall only be used. Articles classified as first quality by the manufacturer shall be used unless otherwise specified.

Preference shall be given to those articles which bear I.S.I. Certification mark. In case articles bearing I.S.I. Certification mark are not available, the quality of samples brought by the contractor shall be judged by the standard laid down in the relevant I.S.I. Specifications. All material and articles brought by the contradictor to the site for use shall confirm to the samples approved which shall be preserved till the completion of the work.

3.1.4	The work will be carried out in the manner complying in all respects with the requirement of relevant by laws of the local body under the Jurisdiction of which the work is to be executed or as directed by the Engineer-in-Charge and nothing extra will be paid on this account.

3.1.5	The contractor shall have a performance tests for the entire installations as per standards/specifications before the work is finally accepted and nothing whatsoever shall be payable to the contractor without such test.

3.1.6	The junior Engineer should maintain the Register for cement paint and other Registers as required by the Engineer-in-Charge and these should be signed by the contractor or his authorized agent and the Junior Engineer-in-Charge of the work.

3.1.7	The contractor shall leave such recesses, holes, openings etc. as may be required for the electric and sanitary work by providing P.V.C. scrubs at appropriate level and direction and nothing extra shall be paid on the work.

3.1.8	The contractor shall make his own arrangement for temporary electric connection if required and make necessary payment for it direct to the department concerned.

3.2	The bricks brought by the contractor including these classified as first class in the local market shall be used.

3.3	Material bearing B.I.S. Marks shall be given first preference for incorporation in the work. Whenever ISI marked materials are available the same only shall be used. In case where articles of different makes and designs bearing B.I.S. mark are available in the market the decision of the Engineer-in-Charge about a particular make and design to be used in the work shall be final and binding. In case where articles with B.I.S. mark are not available in the market, the quality shall have to confirm to relevant B.I.S. specification.

3.4	Materials for which B.I.S. has lincensed use of B.I.S. certification mark only material bearing B.I.S. Certificate mark only material bearing ISI certification mark are available the decision of the Engineer-in-Charge about the design to be used in the work shall be final and binding on the contractor where articles with B.I.S. certification mark are not available the quantity shall confirm to the relevant CPWD specification/ISI specification or as approve by the Engineer-in-Charge.

3.5	Immediately after the award of works, the contractor shall produce samples of all materials be used and incorporated in the works for approval samples shall used in the works.

3.6	The structural and architectural drawings shall, at all times, be properly correlated for executing any work. Architecture requirement shall be fully satisfied here specific mention is made of Architects design. Architects approval etc. Samples shall be prepared for approval before starting the work on any item specified by the Engineer-in-Charge.

3.7	Fr all precast concrete work on an unyielding platform with smooth finished surface shall be mae. The member shall have to be caset in approved rigid moulds. Use of bricks. loose plank used for compaction of concrete. All faces of the members must come out smooth. Curing shall be either under water or by covering with wet gunny bags for minimum 14 days. For all types of cement work with Hopper mixer shall be used in the work.

(a)	For all type of Cement work, Hopper mixture shall be used in the work.

4.	Appliances. The contractor shall at no extra cost, provide at site appliances such as weighing scale graduated cylinder standard service slump cones. CI or MS test tube moulds, caliper tapes etc. for site testing of materials and works.

5.	Bricks. The contractor will make his own arrangement for the entire quantity of bricks required for the work quality of bricks shall be judged as per specification and bricks work so to be done with F.P.S. Bricks.

6.	Labour Tents. The contractor shall put the tents for labour as per the conditions of contract, only in the area indicated on the plan and demarcated on the ground by the Engineer-in-Charge. The final bill shall not be paid unless all the tents and cleared from the site.

7.	Shops. Restaurants tea shops or kiosks shall not be allowed to be put up by the contractor in the works area in the labour tents area. Temporary kiosks put up by the Engineer-in-Charge shall be taken by the contractor  on lease to be terminated on the date of completion of termination of contract whichever is earlier and all the rate of Rs. 300/- per kiosks per month to be recovered from the bill paid. On the date of completion of the work or termination of contract which is earlier the kiosks shall be vacated by the contractor and vacant possession given over to the Engineer-in-Charge failing with penalty shall be levied on the contractor at the rate of Rs. 1500/- per day of delay involved.

8.	Testing of Materials. For the tests conducted in DDA labs the testing charges will not be borne by the agency however when tests are conducted from Lab other than DDA the testing charges shall be borne by the agency in case they fail  otherwise they will be borne by DDA. The packing, transportation, cost of material will be borne by the agency/contractor any testing charges of field tests done at site will be borne by the agency. Water testing charges if any shall be borne by the contractor. This supersedes all other conditions regarding testing of material.

9.	The contractor shall be required to submit the detailed programme for completion of work within the stipulated period in the form of a Bar Chart, covering all major modification to the Engineer-in-Charge with the 15 days from the date of start of work of modification suggested by the Engineer-in-Charge shall be incorporated in the Bar Chart. It will be ensured by the contractor that the time schedule will laid down the aforesaid Bar Chart is adhered to. In case of any slippage the time lost will be made good by the contractor by speeding up the activities. In such cases he shall be bound to follow the revised programme decided by the Engineer-in-Charge.

10.	The contractor shall be required to use only mechanical mixre(s) with lifting hopper(s) for mixing cement concrete required for R.C.c. works/Cements concrete work.

11.	The contractor shall bear all incidental charges for cartage storage and safe custody of materials.

12.	No payment will be made to the contractor for damage caused by rains and other natural climates during the execution of work and no such claims on the account will be entertained.

13.	The water will be tested with regard to its suitability for use in R.C.C. works and nothing extra shall be paid on this accord.

14.	The scaffolding for doing the brick work for all properly. The support shall be sound and strong, tied together will be horizontal pieces. The holes for horizontal scaffolding pole shall be provided only in the header course. The holes in the masonry work for supporting the scaffolding shall be filled and made good before plastering. The contractor shall be responsible for providing and maintaining sufficiently strong scarf folding so as to withstand all loads likely to come upon it. Nothing extra is payable on the account.

Due cares shall be taken by the contractor to ensure the execution of brick masonry walls in plumbs. The outer face of the building should be kept as true face.

15.	Levy of taxes.

(i)	“Tendered rates are inclusive of all taxes and levies payable under the respective statutes. However pursuant to the constitution act, 1982, if any further tax or levy is imposed by after date of receipt of tenders and the contractors thereupon necessarily and properly pays such taxes/levies the contractor shall be reimbursed the amount so paid provided such payment if any, is not, in the opinion of Superintending Engineer (whose decision shall be final and binding) attribute to delay in execution of work within the control of the contractor.

(ii)	the contractor shall keep necessary books of account and other document for the purpose of this condition as may be duly authorized representative of Govt. and further shall furnish such other information/documents as the Engineer-in-Charge may require.

(iii)	The contractor shall within a period of 30 days of imposition of any further tax or levy, the pursuance to the constitution Act 1982 give a written notice thereof to the Engineer-in-Charge that the same is given pursuant to this condition together with all necessary information relating thereto.

16.	Barricading of excavated trenches on both side of the trench to the heights of 1.60 mtr. With galvanized steel plain sheet of 1.00mm thick (Class-1) fixed on 100mm dia. Sal Balliee 3m apart with nails etc. will be done by contractor as a safety measure and nothing extra will be paid for. He will also provide red strips on sheet with aluminium paint 75mm vide alternatively on outside of sheets vertically and no extra payment will be made on this account.

17.	The contractor shall give a performance test of the Entire installation as per standard specification before the work is finally accepted and nothing extra whatsoever shall be payable to the contractor for the test.

18.	(a)	The field staff shall keep the record of initial levels and final levels of all low lying area.

(b)	The field staff shall ensure that the quantity of excavation earth disposed off by mechanical transport is dumped in the areas certified by EE as low laying area shown on the enclosed layout.

19.	Access to site. The contractor is to include in his rates the cost of forming access to the site with all temporary roads and gangways require for the works.

20.	Access for inspection. The contractor is to provide, at all times during the progress of the works and the maintenance period, proper means of access, with leaders, gangways etc. and other necessary attendant to move and adopt as directed for the inspection or measurement of the words by the Engineer-in-Charge or his authorized representatives.

21.	Instrument and Equipment. The contractor shall make the following available readily and in good working condition at site to ensure proper quality of work: Theodolite, Dumpy level with staff, steel tapes, stop watch, platform type weighing machine of 200 kgs. capacity, steel balance with weights. Spring balance, slumpcone with tamping rod, 15cm cube moulds Plumb Bob, spirit level Vernier/Micrometer Calibrated cylinders, Hammers.

22.	Storage of Materials. The contractor shall store all materials in proper manner so as to avoid contamination and deterioration. The places at site where materials are to be stored shall be subject to the approval of the Engineer-in-Charge. Store the place where the materals are stored by the contractor be required by the Engineer-in-Charge for any other purpose, the contractor shall make arrangements to clear the space within such time as may be instructed by the Engineer-in-Charge.

23.	Permanent Bench Marks. Where directed by the Engineer-in-Charge, the contractor shall provide permanent bench marks. Likewise, any other levels or lines or points specifically required by the Engineer-in-Charge shall be built in. The contractor shall carefully protect and preserve such important mark during execution of the work.

24.	Testing of Materials. The tests shall be got carried out by the contractor in laboratories approved by the Engineer-in-Charge and as often as he may consider them necessary.

25.	Safety Measures. The contractor shall provide necessary barriers, warning signals and other safety measures while cutting roads or laying pipe lines etc. or wherever otherwise necessary, so as to avoid accidents. He shall also indemnify the employer against claims for compensation arising out of negligence in this respect. These provisions are in addition to the safety measures already mentioned elsewhere.

26.	All soil, fifth or other matter of an offensive/obnoxious nature, taken out of any trench sewer, drains cess pool or other place, shall not be deposited on the surface, but shall at once be carted away by the contractor to some pit or place provided to him and as approved by the Engineer-in-Charge.

27.	Water for Construction Purposes. The water to be used for construction shall have to satisfy the requirements as per the Bureau at Indian standard Codes. As soon as the Contractor has decided or located source of water, he shall be required to send samples of water for testing to laboratory approved by the Engineer-in-Charge. Water shall be allowed for use for construction purposes only if it satisfies the requirements of Indian Standard codes. In case, the water is found unsuitable for construction purposes. The contractor shall have to arrange water from alternative source. The samples for water have to be tested at least once in every three months or earlier the testing charges shall be borne by the contractor.

28.	Water Proofing. All areas where water proofing is to be done the water proofing shall be got done through firm specialized in water proofing work.

The water proofing works shall be guaranteed against seepage/leakage for a period of ten years. The contractor shall have to execute a performance bond in the prescribed proforma enclosed on page no…………… of tender documents water proofing compound of approval brand shall be used.

29.	The proportion of the water proofing compound of approval mark to be used in cement shall be 2% by weight i.e. 1 kg of chemical approval quality and manufacture shall be mixed with 100 kg of cement or in the proportion recommended by the manufactures.

30.	Coordination with other agencies. The work of internal/external electrical installation lifts fire fighting installations etc. having work etc shall to be carried out by the Department through other agencies with whom proper work co-ordination as per direction of the Engineer-in-Charge shall be carried out.

31.	Testing of Lines. All pipes lines laid by the contractor shall be required under the specification to the entire satisfaction of the Engineer-in-Charge. The work shall not be treated as completed unless the lines are so tested.

32.	It is obligatory on the part of the contractor to remove/shift the labour immediately after the work has been completed and the final payment shall be released only thereafter. No claim in finalization of Contractor’s bill shall be entertained on account of above.

33.	The contractor shall be responsible for any activity, authorized or unauthorized going on within the site area handed over to him by the department for construction development maintenance or for any other purposes. The contractor shall also be responsible for informing the Engineer-in-Charge in writing wherever their supervision is essential. Further this shall not be ground for seeking time extension in completion of the work and/or for claiming any loss and/or damage by the contractor if at all this clause prologation of completion of work.

It is obligatory on the part of the contractor to remove/shift the labour immediately after the work has been completed and the final payment shall be released only thereafter no claim in finalization of contractors bill shall be entertained of account.

34.	Adjustment of Tax consequent upon Amendment to constitution Tendered rates are inclusive of all taxes and levies payable under the respective statutes. However pursuant to the constitution (Forty Sixth amendment) Act, 1982 if any further tax or levy is imposed b y statue after the date of receipt of tender and the concrete shall be reimbursed the amount so paid provided such payment of any is attributable to delay in execution of work within the control of the contractor.

(i)	The contractor shall keep necessary books of account and other documents for the purpose of this condition as may be necessary and shall allowed inspection of the same by a duly authorized representative of Govt. and further shall furnish such other information/documents as the Engineer-in-Charge may require.

(ii)	The contractive shall within a period of 30 days of imposition of any further tax or levy pursuant to the constitution Forty Six amendment Act, 1982 given a written notice together will all necessary information relating thereto.

Proforma for performance Bond

The agreement made this……………..day of………………. Two Thousand… …………………………….. between son of …………………………… one part_ and the Chairman, Delhi Development Authority. Hereinafter called the Delhi Development Authority of the other part.) Whereas This agreement is supplementary to a contract hereinafter called the Contractor dated…………... other part whereby the contractor interalia undertook to a contract (hereinafter called the Contractor) dated………………………….. and made between the Guarantor of this one part and the Delhi Development Authority of the other part whereby the contractor interalia, undertook to render the buildings and structured in the said contractor received completely water and leak-proof.

AND WHEREAS The Guarantor agreed to give a guaranteed to the effect that the said structure will remain water proofing treatment.

NOW THE GUARANTOR hereby guarantees that water proofing treatment given by him will render the structure completely leak-proofing and the minimum life of such water proofing treatment shall be ten years to be reckoned from the date after the maintenance period prescribed in the contract.

Provided that the guarantor will not be responsible for leakage caused by earthquake or structural defects or misuse of roof or alteration and for such purpose.

(a) Misuse of rule shall means any operation which will damage water proofing treatment like chopping of fire wood and things of the same nature which might caused damage to roof.

(b) Alteration shall mean construction of an additional story or a part of the root or construction adjoining to existing roof where by water proofing treatment is removal in part.

(c) The decision of the Engineer-in-Charge calling upon him to rectify the defects failing which the work shall be got done by the department by some other contractor all the GUARANTOR cost and risk. The decision of the Engineer-in-Charge as to the cost payable by the guarantor shall be final and binding. That if Guarantor fails to execute the water proofing or commits breach there under then the Guarantor will immediately the Principle and his successors against all loss damage cost expense or otherwise which may be incurred by him by reason of any default on the part of the GUARANTOR in performance and observance of this supplementary agreement. As to the amount of loss and/or damage and/or cost incurred by the Delhi Development Authority the decision of the Engineer-in-Charge will be final and binding on the parties.

In witness whereof these presents have been executed by the Obligor………………. And by ……………………. And for and on behalf of the Delhi Development Authority on the day month and year first above written.

Signed Sealed and Delivered by OBLIGOR in the presence of

1……………………………

2…………………………

Signed for and behalf of the Delhi Development Authority by

……………………… in the presence of

1…………………………………….

2……………………………………..

Annexure – III

Table of Mile Stone(s)

| Sr. No. | Description of Milestone (Physical) | Time allowed in days (from date of start) | Amount to be withheld in case of nonachievement of milestone |
| --- | --- | --- | --- |
| 1 | Refer completion period Vide 3.1 (i) to (v) On Page 15 |  | In the event of not achieving the necessary progress as assessed from the running payment 1% of contract value will be withheld for failure of each mile stone. |

Specimen of Financial bid to be submitted separately

Name of Work	:	C/o 850 Mass Housing (170 HIG, 340 MIG, 340 LIG). Houses at Vasant Kunj, Near Sultangarhi.

S.H.	:	Design, Construct, Operate & Transfer of Mini S.T.P. of M.L.D. (Interim Arrangement) Complete on Turnkey Basis.

| Item No | Description of Item | Qty | Unit | Rate | Amount |
| --- | --- | --- | --- | --- | --- |
| 1 | Preparation of general arrangement drawings, detailed architectural, structural drawings & design, of civil/electrical/ mechanical/chemical works, specifications for non-schedule item complete including consultancy and installation, commissioning sewage treatment plant and making all necessary arrangement etc. & maintaining for one year from date of completion. | 1 No. Job | Each Job |  |  |
| 2. | Operation & maintenance of S.T.P. beyond the Guarantee Period of 12 month after date of completion including all cost of labour & all consumables, except electrical consumption | 24 months | Each month |  |  |

Note:	(i) The rates not to be filled here

(ii) On the above specimen, the rates to be quoted on separate sheet & sealed in evenlope ‘B’

Should this tender be accepted, in whole or in part, I/We hereby agree:

(i)	To abide by and fulfill all terms and provisions of the said conditions annexed hereto and all the terms and provisions contained in the Notice inviting Tender so far as applicable and/or in default there of to forfeit and pay to the Delhi Development Authority or their successors the sum of money mentioned in the said conditions.

A sum of Rs……………………………… has been deposited in cash / receipt Treasury Challan / Deposits at Call receipt of a scheduled Bank/Fixed Deposit receipt of a scheduled bank / demand draft of a scheduled bank / bank guarantee as earnest money as per provisions laid down in para 4 above in favour of AO/CAU ____________________ Zone/DDA. If I/We fail to furnish the prescribed performance guarantee within the prescribed period I/We agree that the said DDA or his successors in office shall without prejudice to any other right or remedy, be at liberty to forfeit the said earnest money absolutely. Further, I/We fail to commence work as specified, I/We agree that Chairman, DDA or his successor in office shall without prejudice to any other right or remedy available in law, be at liberty to forfeit the said earnest money and the performance guarantee absolutely otherwise the said earnest money shall be retained by him towards security deposit to execute all the works referred to in the tender documents upon the terms and conditions contained or referred to therein and to carry out such deviations as may be ordered.

Rebate Conditions

It may please be carefully noted that no conditions whatsoever (beyond the tender documents placed below) shall be accepted by the Deptt. and the contractors are strictly prohibited from giving conditional tenders. If any contractor is not prepared to execute the work at the terms and conditions contained in the tender documents, he is requested not to tender for this work. It may be noted that if any contractor chooses to submit conditional tender, inspite of clear directions given

above, his tender shall be liable to be rejected summarily and his full earnest money shall stand forfeited. He will also be liable for being debarred from tendering in DDA for a period of six months.

Dated the ______________ day of ___________________ 200______

Signature of Contractor before

Submission of tender

Witness……………………………….

Address…………………………………

Signature of Witness to Contractor’s

Signature

Occupation………………………….

The above tender for the sum of Rs. ______________ Rupees ___________ __________________________________________________ only) is hereby accepted by me ____________________ Engineer __________________ Division___________________ on behalf of the Delhi Development Authority.

Dated the ______________ day of ___________________ 200______

Signature of …………………………. Engineer

Important Note:

Specimen Page No.                   to                         be get separately typed by contractor and filled and placed in Envelope B of Financial Bid.