Details of Contractor Concluded During the Month of August & September, 2010

DIVISION NO. SED-11/DDA

| 1. | 2. | 3. | 4. | 5. | 6. | 7. | 8. | 9. | 10. | 11. | 12. | 13. | 14. | 15. | 16. | 17. | 18. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Tender No. | Item nature of work | Made of tender Enquiry | Dt. Of public action of NIT | Type of Bidding (Single/ -two Bid System) | Last Dt. Of receipt of tender | Nos. of tenders recd | Nos. & name of parties not qualified after technical evaluation | Whether contractor awarded to lowest tender evaluated LI | Contract No. & Date | Name of Contract | Name of Contractor | Value of contract | Schedule dt. Of completion of supplies contract | Actual dt. Of start of work | Actual dt. Of completion | Reasons for delay if any | Remarks |
| 58/SED-11/09-10 | Maint work | Item rate | 10.11.09 | Single | 21.11.09 | 4 Nos | N.A | Yes | Agmt. 88 SED-11/ 09-10 | SH: Renovation of Toilets of B – 2 Side at Vikas Sadan. | Shri Rajender Kumar | 16,14,841/- | 24.10.10 | 01.02.10 | 21.04.10 | -- | -- |
| 119/SED-11/09-10 | Dev. work | Item rate | 22.03.10 | Single | 31.03.2010 | Single | N.A | Yes | Agmt. 10 SED-11/ 10-11 | SH: Pest Control and anti termite treatment of Office of CE (CWG) 2010 at AGVC. | M/s Dinamic Pest & Rodent Control | 9,040/- | 02.06.10 | 03.05.10 | 01.06.10 | -- | -- |
| 120/SED-11/9-10 | Maint work | Item rate | 22.03.10 | Single | 31.03.10 | 2 Nos. | N.A | Yes | Agmt. 9 SED-11/ 10-11 | SH: Pest Control and anti termite treatment of Staff Flats at AGVC. | M/s Dinamic Pest & Rodent Control. | 23,357/- | 02.06.10 | 03.05.10 | 01.06.10 | -- | -- |
| 12/SED-11/09-10 | Maint work | Item rate | 05.05.09 | Single | 26.05.09 | 4 Nos | N.A | Yes | Agmt.21 SED-11/ 09-10 | SH: upkeep of Office furniture at Vikas Sadan | Shri Amit Kumar Sharma | 4,25,914/- | 24.01.10 | 25.07.09 | 24.01.10 | -- | -- |
| 112/SED-11/09-10 | Maint work | Item rate | 26.02.10 | Single | 06.03.2010 | 6 Nos | N.A | Yes | Agmt.6 SED-11/ 10-11 | SH: Pdg. Missing link of water supply line at Tuglakabad. | Shri Mange Ram | 1,49,638/- | 24.05.10 | 25.04.10 | 21.05.10 | -- | -- |
| 104/SED-11/09-10 | Maint work | Item rate | 19.01.10 | Single | 30.01.10 | 2 Nos | N.A | Yes | Agmt.103 SED-11/ 09-10 | SH: Repair of pota cabin, Green House and supply of banches at Millennium park Sarai Kale Khan | M/S Arch Constn. | 5,58,733/- | 06.05.10 | 07.03.10 | 15.04.10 | -- | -- |
| 101/SED-11/09-10 | Maint work | Item rate | 04.02.10 | Single | 12.02.10 | 3 Nos | N.A | Yes | Agmt.107 SED-11/ 09-10 | SH: Renovation of Entrance Gate for bus Parking Millennium Park at Sarai Kale Khan. | M/S Arch Constn. | 13,63,027/- | 27.04.10 | 14.03.10 | 16.04.10 | -- | -- |
| 52/SED-11/09-10 | Maint work | Item rate | 11.12.09 | Single | 19.12.09 | 2 Nos | N.A | Yes | Agmt.83 SED-11/ 09-10 | SH: Pdg. & installation of Material testing equipment for Quality Control Lab in Village Complex Khal Goan. | M/s Slandered Scientific Co. | 4,58,069/- | 20.02.10 | 21.01.10 | 19.02.10 | -- | -- |
| 115/SED-11/09-10 | Maint work | Item rate | 29.03.10 | Single | 09.04.10 | 4 Nos | N.A | Yes | Agmt.18 SED-11/ 10-11 | SH: Street scaping & Beatification of Road from Vikas Sadan to Safarjung Terminal by premixing. | M/S Road Tech | 27,56,049/- | 09.09.10 | 10.06.10 | 18.07.10 | -- | -- |
| 94/SED-11/09-10 | Maint work | Item rate | 20.01.10 | Single | 02.02.10 | 8 Nos | N.A | Yes | Agmt.113 SED-11/ 09-10 | SH: Constn. of repair of Boundary wall at M.P. Green area along 100 ft wide Road left hand side at Ladha Sarai. | M/S Reyansh Constn. | 10,95,685/- | 20.06.10 | 21.03.10 | 10.08.10 | -- | EOT granted without lavy of compensation |
| 96/SED-11/09-10 | Maint work | Item rate | 08.01.10 | Single | 20.01.10 | 4 Nos | N.A | Yes | Agmt.115SED-11/ 09-10 | SH: Painting & White washing in rooms and corridors at Vikas Sadan | M/s S.V Enterprises | 1,60,835/- | 24.09.10 | 25.03.10 | 24.09.10 | -- | -- |
| 113/SED-11/09-10 | Maint work | Item rate | 26.02.10 | Single | 06.03.10 | 6 Nos | N.A | Yes | Agmt.16 SED-11/ 10-11 | SH: P/F of barricates and road side speed bracker at Gitanjali Enclave Road. | Shri Ram Sharan | 1,56,080/- | 30.05.10 | 11.05.10 | 28.05.10 | -- | -- |
| 102/SED-11/09-10 | Maint work | Item rate | 06.02.10 | Single | 12.02.10 | 3 Nos | N.A | Yes | Agmt.12 SED-11/ 10-11 | SH: Structural & rehabilitation of R.C.C work of Basement and Offices at different floors of Vikas Sadan | Shri Anil Kumar | 8,44,002/- | 05.09.10 | 06.05.10 | 04.09.10 | -- | -- |
| 8/SED-11/10-11 | Maint work | Item rate | 17.06.10 | Single | 26.06.10 | 2 Nos | N.A | Yes | Agmt.26 SED-11/ 10-11 | SH:- Repair of Rain Shelter (3 Nos)at Millennium Park along Ring Road between ISBT Sarai Kale Khan & Bhairon Road. | M/s R.K. Constn Co. | 1,88,952/- | 26.10.10 | 13.08.10 | 18.09.10 | -- | -- |
| 7/SED-11/10-11 | Maint work | Item rate | 28.06.10 | Single | 09.07.10 | 3 Nos | N.A | Yes | Agmt.25 SED-11/ 10-11 | SH:- Renovation of Poly House for nursery at Millennium Park along Ring Road between ISBT Sarai Kale Khan & Bhairon Raod. | M/s R.K. Constn. Co. | 8,08,165/- | 11.11.10 | 12.08.10 | Work in progress | -- | -- |
| 08/SED-11/10-11 | Maint work | Item rate | 17.06.10 | Single | 26.06.10 | 2 Nos | N.A | Yes | Agmt.26 SED-11/ 10-11 | SH:- Repair of Rain Shelter (3 Nos) at Millennium Park along Ring Road between ISBT Sarai Kale Khan & Bhairon Road. | M/s R.K. Constn Co. | 1,97,111/- | 26.09.10 | 13.08.10 | Do | -- | -- |
| 05/SED-11/10-11 | Maint work | Item rate | 04.06.10 | Single | 16.06.10 | 2 Nos | N.A | Yes | Agmt.27 SED-11/ 10-11 | SH:- Removal of malba/garbage form dustbin in C – Block Parking Vikas Sadan. | M/s S.V. Sons | 2,82,750/- | 05.09.10 | 06.08.10 | Work in progress | -- | -- |
| 11/SED-11/10-11 | Maint work | Item rate | 06.07.10 | Single | 14.07.10 | 3 Nos | N.A | Yes | Agmt.28 SED-11/ 10-11 | SH:- Renovation of Chief Legal Advisor Office in ‘B’ Block 6th floor, Vikas Sadan. | Shri Surender Bhardwaj | 2,40,167/- | 20.09.10 | 21.08.10 | Do | -- | -- |
| 12/SED-11/10-11 | Maint work | Item rate | 12.07.10 | Single | 21.07.10 | 2 Nos | N.A | Yes | Agmt.30 SED-11/ 10-11 | SH:- Scavenging of circulation area & upkeep of drainage system at Vikas Sadan. | Shri Surender Bhardwaj | 1,33,200/- | 01.03.11 | 02.09.10 | Do | -- | -- |
| 121/SED-11/09-10 | Maint work | Item rate | 21.07.10 | Single | 28.07.10 | 4 Nos | N.A | Yes | Agmt.32 SED-11/ 10-11 | SH:- Repair of foot path from Safdarjung Flyover to Rajya Sabha Awas near Vikas Sadan | Shri Sanjeev Kumar | 5,33,660/- | 30.10.10 | 16.09.10 | Do | -- | -- |
| 13/SED-11/10-11 | Maint work | Item rate | 19.07.10 | Single | 28.07.10 | 3 Nos | N.A | Yes | Agmt.33 SED-11/ 10-11 | SH: Repair of water line at Millennium Park Sarai Kale Khan. | M/s Arch Constn. | 3,45,957/- | 02.11.10 | 19.09.10 | Do | -- | -- |
| 03/SED-11/10-11 | Maint work | Item rate | 21.07.10 | Single | 31.07.10 | 6 Nos | N.A | Yes | Agmt.34 SED-11/ 10-11 | SH: Renovation of Entry gate of Block A,B,C& C4 at Vikas Sadan. | M/s Sukhdev Sehgal | 4,53,139/- | 25.010.10 | 26.09.10 | Do | -- | -- |
| 14/SED-11/10-11 | Maint work | Item rate | 05.08.10 | Single | 13.08.10 | 6 Nos | N.A | Yes | Agmt.35 SED-11/ 10-11 | SH: Repair & relaying of interlocking paver block in parking area & foot path etc. | M/s Arch Constn. | 6,00,000/- | 29.10.10 | 30.09.10 | Do | -- | -- |
| 16/SED-11/10-11 | Maint work | Item rate | 05.08.10 | Single | 13.08.10 | 7 Nos | N.A | Yes | Agmt.36 SED-11/ 10-11 | SH: Repair of stone wall at Millennium Park Sarai Kale Khan. | M/s Arch Constn. | 4,00,000/- | 13.11.10 | 30.09.10 | Do | -- | -- |
| 44/SED-11/10-11 | Maint work | Item rate | 26.08.10 | Single | 04.09.10 | 2 Nos | N.A | Yes | Agmt.37 SED-11/ 10-11 | SH: P/F Modular furniture in C.V.O. Office at Vikas Sadan. | M/s Newwaege furniture innovations Pvt. Ltd. | 5,61,150/- | 26.10.10 | 07.10.10 | Do | -- | -- |
| 31/SED-11/10-11 | Maint work | Item rate | 17.08.10 | Single | 28.08.10 | 4 Nos | N.A | Yes | Agmt.38 SED-11/ 10-11 | SH: Water proofing for Block –B VIIth floor at Vikas Sadan. | Shri Harinder Singh | 6,14,308/- | 18.10.10 | 09.10.10 | Do | -- | -- |